## Contents - NRM 3 L&L Table
RICS NRM 3 Logic and Level Tables (January 2026)
Contents
This NRM 3 publication is released in an Excel document format, and contents on the following TABS are:
Tab No. | Tab Name / NRM Description | Description / Purpose
1 | Release Copy of NRM 3 tables January 2026 | Communication notes - what has changed since previous version
2 | Explaining the NRM 3 Logic & Level Tables (2025) | Guidance and instructions for using the Logic & Level tables
3 | NRM 3 Logic and Level Table 2021 (2nd edition) | Elemental life cycle cost planning structure (2021 version)
4 | NRM 3 Logic and Level Table 2026 (Release of 3rd Edition) | Elemental structure (aligning to other data standards, SFG20/CIBSE GM)
5 | NRM 3 Appendix C - List of Function Types | Functional types and associated units of measurement
6 | NRM Table 3.2 - Elemental Structure | Elemental breakdown for cost estimating and cost planning
7 | NRM 3 Table 3.4 – Order of Estimating Template | Template for order of estimate constituents
8 | NRM 3 Table 4.2 - Cost Planning Template | Template for cost planning constituents
9 | NRM 3 Table 5.4 – Maintain Cost Model Off Asset Register | Example cost plan generated from asset maintenance register
10 | NRM 3 Renewal – IWE Off Construction Cost Plans | Worked example: renewal costs from construction cost plans
11 | NRM 3 Renewal - IWE Off of As Built Data | Worked example ; renewal costs plan using as built data
12 | NRM 3 Renewal – IWE Off Asset Condition Surveys | Worked example: renewal costs from asset condition surveys
13 | NRM 3 Level 1 Reporting Template | Reporting template for Level 1 elemental cost plans
14 | NRM 3 Level 2 Reporting Template | Reporting template for Level 2 elemental cost plans
Refer to the 2021 2nd edition of NRM 3 new rules of measurement for the detailed guidance on how to use the content of this Excel document.

## 1. NRM 3 Release Copy 2026
RICS NRM 3 Logic and Level Table (2026)
RICS has updated the NRM 3 logic and level tables (January 2026), in order to align the NRM 3 cost structure with the
latest SFG20 maintenance task schedules and CIBSE Guide M life cycle costing (for the MEP reference service life tables).
This is the third iteration of the NRM 3 logic and level tables, the first being for the 1st edition NRM 3, published in January 2015.
The 2nd Edition of NRM 3 updated the logic and level tables, which were published in Excel format in January 2021.
2026 version summary
This 2026 version of the NRM 3 logic and level tables has updated the 2nd edition version as follows.
Group element, element and sub element |  | NO CHANGE | NRM 1 and NRM 3 cost structure unaltered
Maintainable asset descriptions |  | EXTENDED | NRM 3 list aligns with all SFG20 tasks
Unit of measure for renewals |  | NO CHANGE | NRM 1 and NRM 3 unit of measure unaltered
Unit of measure for maintain |  | NEW | NRM 3 now lists the maintain unit of measure separately
Material type |  | NEW | NRM 3-specific information needed for life cycle costing
Work groups |  | NO CHANGE | NRM 3 16 elements (as previous version)
NRM 3 coding |  | REVISED | NRM 3 coding of all levels, down to lowest maintainable assets
Rationale behind changes since NRM 3 2nd edition
The rationale behind NRM 3, Order of cost estimating and cost planning for building maintenance works, is to provide the
standardised basis to integrate capital construction cost management (NRM 1) with life cycle renewals and maintenance works (NRM 3).
To provide this, NRM 1 and NRM 3 have exactly the same group, element and sub element cost breakdown structure.
The list of maintainable asset descriptions in NRM 3 has been established by the alignment between NRM 3 and SFG20 tasks.
The extended list of maintainable assets/components has been updated, as new SFG20 maintenance task schedules have been created since 2021.
NRM 3 provides the bridge between the capital and revenue. NRM 3 has been adopted and used in the CIBSE Guide M 11 -
Indicative Economic Life Expectancy table, linking the NRM 3 cost breakdown structure to the reference service life (in years) of each individual
building engineering assets.
NRM 3 has also been mapped to the Uniclass systems and products. NRM 3 codes have been incorporated in Uniclass classification tables
As the result of the alignment of the NRM 3 logic and level tables with these industry data standards, it now provides:
1 | a common data structure for use not just for capital projects, but for the entire asset life cycle through to disposal
2 | a common language for all the maintainable asset descriptions (such as chiller, boiler, or air handling unit)
3 | alignment of NRM 3 with applicable operation and maintenance tasks (by linking to SFG20 task schedule/codes)
which provides the basis to standardise asset registers for maintenance planning, while also standardising the use of asset renewal plans
(combined with maintain)
4 | an asset breakdown structure by linking the NRM cost breakdown structure with Uniclass,
which enables the quantification and extraction of costs and whole life carbon assesment off of BIM models
5 | a connection down to lowest maintainable assets through NRM 3's element and sub-element structure;
this is important to create one asset register that can be used for multiple purposes (such as, planned preventative maintenance,
net zero carbon and asset life renewals), and
6 | NRM 3 work groupings that can be used to procure relevant packages of work (such as, life safety systems, electrical works, or lifts)
Informative worked examples
The NRM 3 logic and level tables Excel document includes the following informative worked examples:
TAB 9 | NRM 3 Maintain - cost model from an asset register
TAB 10 | NRM 3 Renewals – from construction cost plans
TAB 11 | NRM 3 Renewals - from as built data
TAB 12 | NRM 3 Renewals – from asset condition surveys
Acknowledgements
The NRM 3 logic and level tables have been updated by a industry collaboration between the industry data standards bodies:
RICS | the NRM 3 technical author updated the tables, which were validated by the NRM 1 technical author.
CIBSE | members adopted the NRM 3 structure in the latest economic life expectancy tables for Guide M technical standards.
SFG20 | the technical standards team supported the alignment of NRM 3 with the latest SFG20 task schedules and service groupings.
Uniclass | the technical classification team incorporated NRM 3 codification to align with Uniclass systems and product tables.
Statement from the technical Author of NRM 3
Since the 1st edition of NRM 3 was published in 2015, NRM 3 has provided the basis to enable data interoperability between projects and
operation and maintenance (that is, maintain and renewals), as well as be used in the application of digital enabled life cycle costing
and the procurement of supply contracts.
NRM 3 provides a common data classification and common language that can be used throughout the entire asset life cycle - cradle to grave.
Using NRM 3 as the basis to align with the other data standards will be a game changer and assist with the wider use of life cycle costing across all
stages of capital projects and during the operational in-use phase, driving a standardised, robust and effective method of cost management.
This has been made possible by collaboration with other data standards bodies, which has also improved all of their classification and data standards'
Andrew Green - Technical Author of NRM 3, and the technical author for CIBSE's Guide M11 Life cycle costing (2023)

## 2. Explaining NRM 3 L&L Tables
RICS NRM 3 Logic and Level Table (2026)
Explaining the Logic and Levels Table
Purpose of the NRM 3 logic and level table (in Excel release format)
The NRM 3 logic and level table provides the cost management structure for the quantification and description of maintenance works for the purpose of preparing initial order of cost estimates during the building project stages, elemental cost plans during design and construction stages and detailed asset specific cost plans (post construction). Also to use for maintenance and renewal cost modelling throughout the in use phases of a building or facilities. The NRM 3 also aids the procurement process and the life cycle cost control of the building maintenance works.
The NRM 3 logic and level table provides the framework for life cycle costing as it has the same group element and sub elements as the NRM 1 structure. NRM 3 explicitly defines the renewal and maintenance rules for cost estimation, cost planning and cost control of capital renewals and maintenance works - enabling more effective and accurate cost advice, facilitate procurement, optimise contract costing and benchmarking.
NRM 3 logic and level table (2025) has provided the bridge to link to the other industry data standards to enable the following: 1. Quantification of costs and carbon assessments off a capital projects by incorporating NRM 3 codes into Uniclass classification tables. 2. Quantification of maintainable assets for costing and planning maintenance work, by aligning NRM 3 to SFG20 PPM task schedules. 3. Quantification of renewal works (also known as life cycle replacement plans) - by aligning NRM 3 to CIBSE Guide M life expectancy tables
The NRM3 Logic and Level Table (2025) published in this excel document - include informative worked examples of how to use for: 1. Maintenance cost model off of Asset Registers (as TAB 9) 2. Renewal cost plan off of the Construction cost plans (as TAB 10) 3. Renewal cost plan off of elemental / sub element and detailed Asset Registers (as TAB 11)
Templates for reporting level 1 and level 2 renewal and maintenance works are provided (as TABs 13 and 14) in this excel document
Explaining the NRM 3 logic and level tables (Release January 2026) in TAB 4 | Changes
Column 1 - the level 1,2 and 3 NRM 3 classification codes for the cost breakdown structure at group, element, sub-element and maintainable assets | Revised
Column 2 - the level 1 group element heading, with a list of group elements | No change
Column 3 - the level 2 element heading, with a list of elements | No change
Column 4 - the level 3 sub element or system heading, with a list of sub elements and systems for construction ( C ) and renewal ( R ) | No change
Column 5 - the maintainable asset description heading, with a list of maintainable asset descriptions for maintain and renewal | Extended
Column 6 - the Unit of Measure for maintainable assets for routine maintenance works (where they differ from renewal units of measure) | New
Column 7 - the Unit of Measure for maintainable assets for renewal works | Revised
Column 8 - the product and material type heading (where this information is required for life cycle costing of the renewal and maintenance works) | New
Column 9 - the work package heading, for the grouping of components (which can be used for procurement and work planning purposes) | Revised
Refer to the 2021 2nd edition of RICS NRM 3 new rules of measurement for the detailed guidance on how to use the content of this Excel document.

## 3.NRM3 Logic levels Table 2021
NRM 3
Logic and levels for elemental life cycle cost planning of the Construct (C), Renewal (R) and Maintain (M) Works | [5 empty] | No responsibility for loss or damage caused to any person through the use of this template can be accepted by the authors or RICS. |  |  | 2nd Edition of the NRM 3 Logic and Level Table (Released January 2021)
Maintainable asset descriptor (at lowest maintainable component level 3, 4 or Level 5)
C O D E | GROUP ELEMENT | C O D E | ELEMENT | C O D E | SUB-ELEMENT | CODE | MAINTAIN & RENEWAL COMPONENT | CODE | MAINTAIN & RENEWAL COMPONENTS | NRM 3 CODE | Level | Spec Y/N | Maintainable Asset Descriptor (M&R Common Language) | Example of Work Packages
| Level 1 – (as NRM 1) |  | Level 2 (aligned to NRM 1) |  | Level 3 (aligned to NRM 1 structure) |  | Level 4 – Included system or components (included in NRM 3 structure) |  | Level 4 or 5 – Other included components and their subcomponents
0 | Facilitating works (FW) | 1 | Toxic or hazardous contaminated material treatment | 1 | Toxic or hazardous material removal | 1 | Toxic or hazardous material removal (e.g. control of asbestos materials) |  |  | 0.1.1.1 | 4 | 0 | FW – Asbestos | 13 – Specialist
0 |  | 1 |  | 1 |  | 2 | Toxic or hazardous insulations from existing services installations |  |  | 0.1.1.2 | 4 | 0 | FW – Toxic or hazardous insulations from existing services installations | 13 – Specialist
0 |  | 1 |  | 1 |  | 3 | Control of chemical hazardous materials |  |  | 0.1.1.3 | 4 | 0 | FW – Control of chemical hazardous materials | 13 – Specialist
0 |  | 1 |  | 1 |  | 4 | Safe disposal (included with items 1 to 3) |  |  | 0.1.1.4 | 4 | 0 | FW – Safe disposal (included with items 1 to 3) | 13 – Specialist
0 |  | 1 |  | 2 | Contaminated land | N/A | Not covered by NRM 3 |  |  | 0.1.2 | 3 | 0 | N/A | NOT APPLICABLE
0 |  | 1 |  | 3 | Eradication of plant growth | 1 | Note: applying herbicides – taken in 8.3.2.1 |  |  | 0.1.3.1 | 4 | 0 | N/A | NOT APPLICABLE
0 |  | 1 |  | 3 |  | 2 | Eradication by chemical treatment |  |  | 0.1.3.2 | 4 | 0 | FW – Eradication by chemical treatment | 13 – Specialist
0 |  | 2 | Major demolition works | 1 | Demolition works | N/A | Not covered by NRM 3 |  |  | 0.2.1 | 4 | 0 | N/A | NOT APPLICABLE
0 |  | 2 |  | 2 | Soft strip works | N/A | Not covered by NRM 3 |  |  | 0.2.2 | 4 | 0 | N/A | NOT APPLICABLE
0 |  | 3 | Temporary support to adjacent structures | 1 | Temporary support to adjacent structures | N/A | Not covered by NRM 3 |  |  | 0.3.1 | 4 | 0 | N/A | NOT APPLICABLE
0 |  | 4 | Specialist groundworks | 1 | Site dewatering and pumping | 1 | Site dewatering | 1 | Forming well points and well point equipment | 0.4.1.1.1 | 5 | 0 | FW – Forming well points and well point equipment | 13 – Specialist
0 |  | 4 |  | 1 |  | 1 |  | 3 | Drain tubes and ring mains | 0.4.1.1.3 | 5 | 0 | FW – Drain tubes and ring mains | 13 – Specialist
0 |  | 4 |  | 1 |  | 1 |  | 4 | Sumps | 0.4.1.1.4 | 5 | 0 | FW – Sumps | 13 – Specialist
0 |  | 4 |  | 1 |  | 1 |  | 5 | Supplementary list (pumps) | 0.4.1.1.5 | 5 | 0 | FW – Pumps | 13 – Specialist
0 |  | 4 |  | 2 | Soil stabilisation measures | N/A | Not covered by NRM 3 |  |  | 0.4.2 | 4 | 0 | N/A | NOT APPLICABLE
0 |  | 4 |  | 3 | Ground gas venting measures | 1 | Ground gas venting measures | 1 | Gas venting measures | 0.4.3.1.1 | 5 | 0 | FW – Gas venting measures | 13 – Specialist
0 |  | 4 |  | 3 |  | 1 |  | 2 | Radon sumps | 0.4.3.1.2 | 5 | 0 | FW – Radon sumps | 13 – Specialist
0 |  | 4 |  | 3 |  | 1 |  | 3 | Vent pipes | 0.4.3.1.3 | 5 | 0 | FW – Vent pipes | 13 – Specialist
0 |  | 5 | Temporary diversion works | 1 | Temporary diversion works | N/A | Taken elsewhere |  |  | 0.5.1 | 4 | 0 | N/A | NOT APPLICABLE
0 |  | 5 |  | 2 | Temporary diversion to services | N/A | Taken elsewhere |  |  | 0.5.2 | 4 | 0 | N/A | NOT APPLICABLE
0 |  | 5 |  | 3 | Temporary diversion of waterways | N/A | Taken elsewhere |  |  | 0.5.3 | 4 | 0 | N/A | NOT APPLICABLE
0 |  | 6 | Extraordinary site investigation works | 1 | Archaeological investigation | N/A | Taken elsewhere |  |  | 0.6.1 | 4 | 0 | N/A | NOT APPLICABLE
0 |  | 6 |  | 2 | Reptile/wildlife mitigation measures | N/A | Not covered by NRM 3 |  |  | 0.6.2 | 4 | 0 | N/A | NOT APPLICABLE
0 |  | 6 |  | 3 | Other extraordinary site investigation works | 1 | Physical site investigation works | 1 | Extraordinary site investigation measures | 0.6.3.1.1 | 5 | 0 | FW – Extraordinary site investigation measures | 13 – Specialist
0 |  | 6 |  | 3 |  | 2 | Temporary screens, fences, barriers, etc. | 2 | Temporary screens, fences and barriers | 0.6.3.2.2 | 5 | 0 | FW – Temporary screens, fences and barriers | 13 – Specialist
1 | Substructure (SUB) | 1 | Substructure | 1 | Standard foundations | N/A | Not covered by NRM 3 |  |  | 1.1.1 | 4 | 0 | N/A | NOT APPLICABLE
1 |  | 1 |  | 1 |  | 1 |  | 15 | Filling cavities | 1.1.1.1.15 | 5 | 0 | SUB – Filling cavities | 13 – Specialist
1 |  | 1 |  | 1 |  | 1 |  | 16 | Thermal insulation to cavities | 1.1.1.1.16 | 5 | 0 | SUB – Thermal insulation to cavities | 13 – Specialist
1 |  | 1 |  | 1 |  | 1 |  | 17 | Damp proofing courses | 1.1.1.1.17 | 5 | 0 | SUB – Damp proofing courses | 13 – Specialist
1 |  | 1 |  | 2 | Specialist foundations | 14 | Underpinning works | 1 | Monitoring subsidence | 1.1.2.14.1 | 5 | 0 | SUB – Monitoring subsidence | 13 – Specialist
1 |  | 1 |  | 3 | Lowest floor construction | N/A | Not covered by NRM3 |  |  | 1.1.3 | 4 | 0 | N/A | NOT APPLICABLE
1 |  | 1 |  | 3 |  | 6 | Design joints | 22 | Design joints to floor slabs | 1.1.3.6.22 | 5 | 0 | SUB – Design joints to floor slabs | 13 – Specialist
1 |  | 1 |  | 3 |  | 8 | Gullies, floor outlets | 29 | Floor outlets | 1.1.3.8.29 | 5 | 0 | SUB – Floor outlets | 7 – Plumbing and Sanitary
1 |  | 1 |  | 3 |  | 8 |  | 30 | Prefabricated floor channels | 1.1.3.8.30 | 5 | 0 | SUB – Prefabricated floor channels | 7 – Plumbing and Sanitary
1 |  | 1 |  | 3 |  | 9 | Internal manholes | 28 | Internal manholes | 1.1.3.9.28 | 5 | 0 | SUB – Internal manholes | 7 – Plumbing and Sanitary
1 |  | 1 |  | 4 | Basement excavation | N/A | Not covered by NRM 3 |  |  | 1.1.4 | 4 | 0 | N/A | NOT APPLICABLE
1 |  | 1 |  | 5 | Basement retaining walls | 1 | Basement retaining walls | 19 | Instrumentation and monitoring | 1.1.5.1.19 | 5 | 0 | SUB – Instrumentation and monitoring | 13 – Specialist
1 |  | 1 |  | 5 | Basement retaining walls | 1 | Basement retaining walls | 7 | Waterproof tanking | 1.1.5.1.7 | 5 | 0 | SUB – Waterproof tanking | 13 – Specialist
1 |  | 1 |  | 5 |  | 1 |  | 8 | Protective external tanking | 1.1.5.1.8 | 5 | 0 | SUB – Protective external tanking | 13 – Specialist
1 |  | 1 |  | 5 |  | 1 |  | 9 | Damp proofing and vapour barriers | 1.1.5.1.9 | 5 | 0 | SUB – Damp proofing and vapour barriers | 13 – Specialist
1 |  | 1 |  | 5 |  | 2 | Embedded basement retaining walls | 9 | Instrumentation and monitoring | 1.1.5.2.9 | 5 | 0 | SUB – Instrumentation and monitoring | 13 – Specialist
2 | Superstructure | 1 | Frame | 1 | Steel frames | 1 | Frame – structural steel |  |  | 2.1.1.1 | 4 | 0 | Frame – Structural steel | 1 – Building Structure
2 |  | 1 |  | 1 |  | 2 | Fire protection to steel frame | 6 | Fire protective coating | 2.1.1.2.6 | 5 | 0 | Frame – Fire protective coating | 1 – Building Structure
2 |  | 1 |  | 2 | Space frames / decks | 1 | Frame – space deck |  |  | 2.1.2.1 | 4 | 0 | Frame – Space deck | 1 – Building Structure
2 |  | 1 |  | 2 |  | 2 | Fire protection to steel frame | 5 | Fire protective coating | 2.1.2.2.5 | 5 | 0 | Frame – Fire protective coating | 1 – Building Structure
2 |  | 1 |  | 3 | Concrete casings to steel frames | 1 | Frames – concrete casings |  |  | 2.1.3.1 | 4 | 0 | Frame – Concrete casings | 1 – Building Structure
2 |  | 1 |  | 4 | Concrete frames | 1 | Frames – concrete columns |  |  | 2.1.4.1 | 4 | 0 | Frame – Concrete columns | 1 – Building Structure
2 |  | 1 |  | 4 |  | 2 | Frames – concrete beams |  |  | 2.1.4.2 | 4 | 0 | Frame – Concrete beams | 1 – Building Structure
2 |  | 1 |  | 4 |  | 3 | Frames – concrete walls |  |  | 2.1.4.3 | 4 | 0 | Frame – Concrete walls | 1 – Building Structure
2 |  | 1 |  | 4 |  | 4 | Frames – concrete forming openings |  |  | 2.1.4.4 | 4 | 0 | Frame – Concrete forming openings | 1 – Building Structure
2 |  | 1 |  | 4 |  | 5 | Designed joints | 9 | Designed joints | 2.1.4.5.9 | 5 | 0 | Frame – Designed joints | 1 – Building Structure
2 |  | 1 |  | 5 | Timber frames | 1 | Frame – timber |  |  | 2.1.5.1 | 4 | 0 | Frame – Timber | 1 – Building Structure
2 |  | 1 |  | 5 |  | 1 |  | 8 | Treatment to timber | 2.1.5.1.8 | 5 | 0 | Frame – Treatment to timber | 1 – Building Structure
2 |  | 1 |  | 5 |  | 1 |  | 9 | Site applied fire retarding paint | 2.1.5.1.9 | 5 | 0 | Frame – Site applied fire retarding paint | 1 – Building Structure
2 |  | 1 |  | 6 | Specialist frames | 1 | Frame – specialist |  |  | 2.1.6.1 | 4 | 0 | Frame – Specialist | 1 – Building Structure
2 |  | 1 |  | 6 |  | 1 |  | 8 | Protective treatment | 2.1.6.1.8 | 5 | 0 | Frame – Protective treatment | 1 – Building Structure
2 |  | 2 | Upper floors (UF) | 1 | Floors | 1 | Concrete suspended floors |  |  | 2.2.1.1 | 4 | 0 | UF – Concrete suspended floors | 1 – Building Structure
2 |  | 2 |  | 1 |  | 3 | Designed joints | 6 | Design joints | 2.2.1.3.6 | 5 | 0 | UF – Design joints | 1 – Building Structure
2 |  | 2 |  | 1 |  | 5 | Precast composite decking – concrete |  |  | 2.2.1.5 | 4 | 0 | UF – Precast composite decking (concrete) | 1 – Building Structure
2 |  | 2 |  | 1 |  | 5 |  | 11 | Re-grouting joints | 2.2.1.5.11 | 5 | 0 | UF – Re-grouting joints | 1 – Building Structure
2 |  | 2 |  | 1 |  | 6 | Timber floors |  |  | 2.2.1.6 | 4 | 0 | UF – Timber floors | 1 – Building Structure
2 |  | 2 |  | 1 |  | 7 | Structural screeds |  |  | 2.2.1.7 | 4 | 0 | UF – Structural screeds | 1 – Building Structure
2 |  | 2 |  | 2 | Balconies | 1 | Balconies – purpose made |  |  | 2.2.2.1 | 4 | 0 | UF – Balconies (purpose made) | 1 – Building Structure
2 |  | 2 |  | 3 | Drainage to balconies | 1 | Rainwater downpipes |  |  | 2.2.3.1 | 4 | 0 | UF – Rainwater downpipes | 7 – Plumbing and Sanitary
2 |  | 2 |  | 3 |  | 2 | Floor outlets |  |  | 2.2.3.2 | 4 | 0 | UF – Floor outlets | 7 – Plumbing and Sanitary
2 |  | 3 | Roof | 1 | Roof structure | 1 | Roof structure – pitched |  |  | 2.3.1.1 | 4 | 0 | Roof structure – pitched | 1 – Building Structure
2 |  | 3 |  | 1 |  | 1 |  | 1 | Roof decks and slabs | 2.3.1.1.1 | 5 | 0 | Roof – Decks and slabs | 1 – Building Structure
2 |  | 3 |  | 1 |  | 1 |  | 2 | Pitched roof structure | 2.3.1.1.2 | 5 | 0 | Roof – Pitched structure | 1 – Building Structure
2 |  | 3 |  | 1 |  | 1 |  | 18 | Thermal insulation (laid in roof space) | 2.3.1.1.18 | 5 | 0 | Roof – Thermal insulation (laid in roof space) | 1 – Building Structure
2 |  | 3 |  | 1 |  | 4 | Roof structure – flat |  |  | 2.3.1.4 | 4 | 0 | Roof structure – flat | 1 – Building Structure
2 |  | 3 |  | 2 | Roof coverings | 1 | Roof coverings (pitched/flat) – state type | 1 | Roof cladding/coverings system | 2.3.2.1.1 | 5 | 0 | Roof cladding/coverings system | 2 – Roofing
2 |  | 3 |  | 2 |  | 1 |  | 2 | Mastic asphalt – including underlay, flashings, etc. applicable to the roof covering system | 2.3.2.1.2 | 5 | 0 | Mastic asphalt – including underlay, flashings, etc. applicable to the roof covering system | 2 – Roofing
2 |  | 3 |  | 2 |  | 2 | Extra over roof coverings | 3 | Photovoltaic device | 2.3.2.2.3 | 5 | 0 | Roof – Photovoltaic device | 2 – Roofing
2 |  | 3 |  | 2 |  | 2 |  | 6 | Thermal insulation | 2.3.2.2.6 | 5 | 0 | Roof – Thermal insulation | 2 – Roofing
2 |  | 3 |  | 2 |  | 2 |  | 7 | Surface treatment (state type) | 2.3.2.2.7 | 5 | 0 | Roof – Surface treatment | 2 – Roofing
2 |  | 3 |  | 2 |  | 2 |  | 8 | Roof paving | 2.3.2.2.8 | 5 | 0 | Roof – Paving | 2 – Roofing
2 |  | 3 |  | 2 |  | 2 |  | 9 | Green roofs and roof gardens | 2.3.2.2.9 | 5 | 0 | Roof – Green and roof gardens | 2 – Roofing
2 |  | 3 |  | 2 |  | 2 |  | 10 | Planting to green roofs/roof garden | 2.3.2.2.10 | 5 | 0 | Roof – Planting to green roofs/roof garden | 2 – Roofing
2 |  | 3 |  | 2 |  | 3 | Eaves and verge treatment to pitched rooves | 1 | Fascia and soffit | 2.3.2.3.1 | 5 | 0 | Roof – Eaves and verge treatment | 2 – Roofing
2 |  | 3 |  | 2 |  | 4 | Edge treatment to flat roofs |  |  | 2.3.2.4 | 4 | 0 | Roof – Edge treatment to flat roofs | 2 – Roofing
2 |  | 3 |  | 2 |  | 5 | Flashings |  |  | 2.3.2.5 | 4 | 0 | Roof – Flashings | 2 – Roofing
2 |  | 3 |  | 3 | Specialist roof systems | 1 | Specialist roof systems | 1 | Patent glazing | 2.3.3.1.1 | 5 | 0 | Roof – Patent glazing | 13 – Specialist
2 |  | 3 |  | 3 |  | 1 |  | 2 | Glazed roofing system | 2.3.3.1.2 | 5 | 0 | Roof – Glazed roofing system | 13 – Specialist
2 |  | 3 |  | 3 |  | 1 |  | 3 | Perspex roofing system | 2.3.3.1.3 | 5 | 0 | Roof – Perspex roofing system | 13 – Specialist
2 |  | 3 |  | 3 |  | 1 |  | 4 | Roof components flashings, etc. | 2.3.3.1.4 | 5 | 0 | Roof – Components flashings | 13 – Specialist
2 |  | 3 |  | 4 | Roof drainage | 1 | Gutters | 1 | Gutters | 2.3.4.1.1 | 5 | 0 | Roof – Gutters | 2 – Roofing
2 |  | 3 |  | 4 |  | 1 |  | 3 | Symphonic roof drainage | 2.3.4.1.3 | 5 | 0 | Roof – Symphonic roof drainage | 2 – Roofing
2 |  | 3 |  | 4 |  | 1 |  | 4 | Rainwater heads | 2.3.4.1.4 | 5 | 0 | Roof – Rainwater heads | 2 – Roofing
2 |  | 3 |  | 4 |  | 1 |  | 5 | Painting and anti-corrosion treatments | 2.3.4.1.5 | 5 | 0 | Roof – Painting and anti-corrosion treatments | 7 – Plumbing and Sanitary
2 |  | 3 |  | 4 |  | 2 | Rainwater pipes | 2 | Rainwater downpipes | 2.3.4.2.2 | 5 | 0 | Roof – Rainwater downpipes | 7 – Plumbing and Sanitary
2 |  | 3 |  | 5 | Roof lights, skylights and openings | 1 | Roof lights skylights and openings | 1 | Roof lights skylights and openings | 2.3.5.1.1 | 5 | 0 | Roof lights skylights and openings | 7 – Plumbing and Sanitary
2 |  | 3 |  | 5 |  | 1 |  | 2 | Opening gear and frames, kerbs and glazing | 2.3.5.1.2 | 5 | 0 | Roof – Opening gear and frames, kerbs and glazing | 2 – Roofing
2 |  | 3 |  | 5 |  | 1 |  | 3 | Sun pipes and tubes | 2.3.5.1.3 | 5 | 0 | Roof – Sun pipes and tubes | 2 – Roofing
2 |  | 3 |  | 5 |  | 1 |  | 4 | Pavement lights | 2.3.5.1.4 | 5 | 0 | Roof – Pavement lights | 2 – Roofing
2 |  | 3 |  | 5 |  | 1 |  | 5 | Roof hatches | 2.3.5.1.5 | 5 | 0 | Roof – Hatches | 2 – Roofing
2 |  | 3 |  | 5 |  | 1 |  | 6 | Access hatches | 2.3.5.1.6 | 5 | 0 | Roof – Access hatches | 2 – Roofing
2 |  | 3 |  | 5 |  | 1 |  | 7 | Smoke vents | 2.3.5.1.7 | 5 | 0 | Roof – Smoke vents | 2 – Roofing
2 |  | 3 |  | 5 |  | 1 |  | 8 | Roof vents and roof cowls | 2.3.5.1.8 | 5 | 0 | Roof – Vents and roof cowls | 2 – Roofing
2 |  | 3 |  | 6 | Roof features | 1 | Roof features | 1 | Turrets | 2.3.6.1.1 | 5 | 0 | Roof – Turrets | 2 – Roofing
2 |  | 3 |  | 6 |  | 1 |  | 2 | Wind vanes | 2.3.6.1.2 | 5 | 0 | Roof – Wind vanes | 2 – Roofing
2 |  | 3 |  | 6 |  | 1 |  | 3 | Spires | 2.3.6.1.3 | 5 | 0 | Roof – Spires | 2 – Roofing
2 |  | 3 |  | 6 |  | 1 |  | 4 | False chimneys | 2.3.6.1.4 | 5 | 0 | Roof – False chimneys | 2 – Roofing
2 |  | 3 |  | 6 |  | 1 |  | 5 | Roof enclosure | 2.3.6.1.5 | 5 | 0 | Roof – Enclosure | 2 – Roofing
2 |  | 3 |  | 6 |  | 1 |  | 6 | Fall arrest systems | 2.3.6.1.6 | 5 | 0 | Roof – Fall arrest systems | 2 – Roofing
2 |  | 3 |  | 6 |  | 1 |  | 7 | Access systems for cleaning roof | 2.3.6.1.7 | 5 | 0 | Roof – Access systems for cleaning roof | 2 – Roofing
2 |  | 3 |  | 6 |  | 1 |  | 8 | Roof edge protection | 2.3.6.1.8 | 5 | 0 | Roof – Edge protection | 2 – Roofing
2 |  | 3 |  | 6 |  | 1 |  | 9 | Balustrades, handrails to roof edges | 2.3.6.1.9 | 5 | 0 | Roof – Balustrades, handrails to roof edges | 2 – Roofing
2 |  | 3 |  | 6 |  | 1 |  | 10 | Service walkways within roof voids | 2.3.6.1.10 | 5 | 0 | Roof – Service walkways within roof voids | 2 – Roofing
2 |  | 4 | Stairs and ramps | 1 | Stair/ramp structure | 1 | Stairs structures | 1 | Staircases | 2.4.1.1.1 | 5 | 0 | Stairs – Structures | 1 – Building Structure
2 |  | 4 |  | 1 |  | 2 | Ramp structures | 2 | Access ramps | 2.4.1.2.2 | 5 | 0 | Ramps – Access ramps | 1 – Building Structure
2 |  | 4 |  | 2 | Stair/ramp finishes | 1 | Stair finishes |  |  | 2.4.2.1 | 4 | 0 | Stairs – Finishes – (state type e.g. timber, stone) | 1 – Building Structure
2 |  | 4 |  | 2 |  | 2 | Ramp finishes |  |  | 2.4.2.2 | 4 | 0 | Ramps – Finishes – state type (e.g. timber, stone) | 1 – Building Structure
2 |  | 4 |  | 3 | Stair/ramp balustrade and handrails | 1 | Wall handrails | 1 | Balustrades and handrails to stairs | 2.4.3.1.1 | 5 | 0 | Stairs – Balustrades and handrails | 1 – Building Structure
2 |  | 4 |  | 3 |  | 1 |  | 2 | Balustrades and handrails to landings | 2.4.3.1.2 | 5 | 0 | Stairs – Balustrades and handrails to landings | 1 – Building Structure
2 |  | 4 |  | 3 |  | 1 |  | 3 | Balustrades /handrails to landings between floors | 2.4.3.1.3 | 5 | 0 | Stairs – Balustrades/handrails to landings | 1 – Building Structure
2 |  | 4 |  | 3 |  | 1 |  | 4 | Applied coating and painting systems | 2.4.3.1.4 | 5 | 0 | Stairs – Applied coating and painting systems | 1 – Building Structure
2 |  | 4 |  | 4 | Ladders/chutes/slides | 1 | Ladders | 1 | Fire escape ladders | 2.4.4.1.1 | 5 | 0 | Ladders – Fire escape | 1 – Building Structure
2 |  | 4 |  | 4 |  | 1 |  | 2 | Access ladders | 2.4.4.1.2 | 5 | 0 | Ladders – Access | 1 – Building Structure
2 |  | 4 |  | 4 |  | 1 |  | 3 | Loft ladders | 2.4.4.1.3 | 5 | 0 | Ladders – Loft | 1 – Building Structure
2 |  | 4 |  | 4 |  | 1 |  | 4 | Applied coating and painting systems | 2.4.4.1.4 | 5 | 0 | Ladders – Applied coating and painting systems | 1 – Building Structure
2 |  | 4 |  | 4 |  | 2 | Chutes | 7 | Fire escape chutes | 2.4.4.2.7 | 5 | 0 | Chutes – Fire escape | 1 – Building Structure
2 |  | 4 |  | 4 |  | 3 | Slides | 7 | Fire escape slides | 2.4.4.3.7 | 5 | 0 | Slides – Fire escape | 1 – Building Structure
2 |  | 5 | External walls (EW) | 1 | External enclosing walls above ground floor level | 1 | External walls | 1 | External enclosing walls | 2.5.1.1.1 | 5 | 0 | EW – External enclosing walls (state type) | 1 – Building Structure
2 |  | 5 |  | 1 |  | 1 |  | 3 | Parapet walls | 2.5.1.1.3 | 5 | 0 | EW – Parapet walls | 1 – Building Structure
2 |  | 5 |  | 1 |  | 1 |  | 5 | Chimneys | 2.5.1.1.5 | 5 | 0 | EW – Chimneys | 1 – Building Structure
2 |  | 5 |  | 1 |  | 1 |  | 7 | Curtain walling | 2.5.1.1.7 | 5 | 0 | EW – Curtain walling | 1 – Building Structure
2 |  | 5 |  | 1 |  | 1 |  | 8 | Structural glazing | 2.5.1.1.8 | 5 | 0 | EW – Structural glazing | 1 – Building Structure
2 |  | 5 |  | 1 |  | 1 |  | 9 | Profiled sheet cladding systems | 2.5.1.1.9 | 5 | 0 | EW – Profiled sheet cladding systems | 1 – Building Structure
2 |  | 5 |  | 1 |  | 1 |  | 11 | Opening vents | 2.5.1.1.11 | 5 | 0 | EW – Opening vents | 1 – Building Structure
2 |  | 5 |  | 1 |  | 1 |  | 12 | Integral blind | 2.5.1.1.12 | 5 | 0 | EW – Integral blind | 1 – Building Structure
2 |  | 5 |  | 1 |  | 1 |  | 25 | External decorations | 2.5.1.1.25 | 5 | 0 | EW – External decorations | 1 – Building Structure
2 |  | 5 |  | 1 |  | 1 |  | 27 | Planted 'green' walls | 2.5.1.1.27 | 5 | 0 | EW – Planted 'green' walls | 1 – Building Structure
2 |  | 5 |  | 1 |  | 6 | Extra over for integral photovoltaic panels | 10 | Photovoltaic part of curtain walling | 2.5.2.6.10 | 5 | 0 | EW – Photovoltaic part of curtain walling | 1 – Building Structure
2 |  | 5 |  | 2 | External enclosing walls below ground floor level | 1 | External walls (EW) |  |  | 2.5.2.1 | 5 | 0 | External walls – state type (e.g. brickwork; cladding) | 1 – Building Structure
2 |  | 5 |  | 2 |  | 1 |  | 4 | Parapet walls | 2.5.2.1.4 | 5 | 0 | EW – Parapet walls | 1 – Building Structure
2 |  | 5 |  | 2 |  | 1 |  | 6 | Chimneys | 2.5.2.1.6 | 5 | 0 | EW – Chimneys | 1 – Building Structure
2 |  | 5 |  | 2 |  | 1 |  | 8 | Curtain walling | 2.5.2.1.8 | 5 | 0 | EW – Curtain walling | 1 – Building Structure
2 |  | 5 |  | 2 |  | 1 |  | 9 | Structural glazing | 2.5.2.1.9 | 5 | 0 | EW – Structural glazing | 1 – Building Structure
2 |  | 5 |  | 2 |  | 6 | Finishes to external walls | 22 | External decorations | 2.5.2.6.22 | 5 | 0 | EW – External decorations | 1 – Building Structure
2 |  | 5 |  | 3 | Solar/rain screen cladding | 1 | Vertical solar/rain screening |  |  | 2.5.3.1 | 4 | 0 | EW – Vertical solar/rain screening | 1 – Building Structure
2 |  | 5 |  | 3 |  | 2 | Horizontal solar/rain screening | 4 | Brise soleil system | 2.5.3.2.4 | 5 | 0 | EW – Brise soleil system | 1 – Building Structure
2 |  | 5 |  | 4 | External soffits | 1 | External soffits |  |  | 2.5.4.1 | 4 | 0 | EW – External soffits | 1 – Building Structure
2 |  | 5 |  | 4 |  | 2 | Cornices, covings, etc. | 6 | Cornices, etc. | 2.5.4.2.6 | 5 | 0 | EW – Cornices | 1 – Building Structure
2 |  | 5 |  | 4 |  | 3 | Shadow gaps | 7 | Shadow gaps | 2.5.4.3.7 | 5 | 0 | EW – Shadow gaps | 1 – Building Structure
2 |  | 5 |  | 4 |  | 4 | Access hatches | 8 | Access hatches | 2.5.4.4.8 | 5 | 0 | EW – Access hatches | 1 – Building Structure
2 |  | 5 |  | 4 |  | 5 | Painting and decorating to false ceilings | 5 | External decorations | 2.5.4.5.5 | 5 | 0 | EW – Decorations | 1 – Building Structure
2 |  | 5 |  | 5 | Subsidiary walls, balustrades, handrails, railings and proprietary balconies | 1 | Walls | 1 | Low level or dwarf walls, balustrades, handrails and railing to external walkways | 2.5.5.1.1 | 5 | 0 | Walls – Low level or dwarf walls, balustrades, handrails and railing to external walkways | 1 – Building Structure
2 |  | 5 |  | 5 |  | 2 | Walls forming planters | 2 | Wall forming planters | 2.5.5.2.2 | 5 | 0 | Walls – Forming planters | 1 – Building Structure
2 |  | 5 |  | 5 |  | 3 | Combined balustrades and handrails | 3 | Combined balustrades and handrails | 2.5.5.3.3 | 5 | 0 | Walls – Combined balustrades and handrails | 1 – Building Structure
2 |  | 5 |  | 5 |  | 4 | Wall mounted handrails | 4 | Wall handrails | 2.5.5.4.4 | 5 | 0 | Walls – Handrails | 1 – Building Structure
2 |  | 5 |  | 5 |  | 5 | Parapet railings | 5 | Railings and barriers | 2.5.5.5.5 | 5 | 0 | Walls – Railings and barriers | 1 – Building Structure
2 |  | 5 |  | 5 |  | 6 | Proprietary bolt on balconies (e.g. Juliet balconies) | 6 | Juliet balconies | 2.5.5.6.6 | 5 | 0 | Walls – Juliet balconies | 1 – Building Structure
2 |  | 5 |  | 5 |  | 7 | Rainwater Downpipes | 7 | Surface water drainage | 2.5.5.7.7 | 5 | 0 | Walls – Rainwater downpipes | 1 – Building Structure
2 |  | 5 |  | 5 |  | 8 | Floor outlets | 7 | Surface water drainage | 2.5.5.8.7 | 5 | 0 | Walls – Floor outlets | 1 – Building Structure
2 |  | 5 |  | 6 | Facade access/cleaning systems | 1 | Facade cleaning systems | 1 | Window/facade cleaning cradles | 2.5.6.1.1 | 5 | 0 | Walls – Window/facade cleaning cradles | 13 – Specialist
2 |  | 5 |  | 6 |  | 1 |  | 2 | Combined facade/roof cleaning system | 2.5.6.1.2 | 5 | 0 | Walls – Combined facade/roof cleaning system | 13 – Specialist
2 |  | 5 |  | 6 |  | 1 |  | 3 | Building maintenance units | 2.5.6.1.3 | 5 | 0 | Walls – Building maintenance units | 13 – Specialist
2 |  | 5 |  | 6 |  | 1 |  | 4 | Other facade access systems | 2.5.6.1.4 | 5 | 0 | Walls – Other facade access systems | 13 – Specialist
2 |  | 6 | Windows and external doors | 1 | External windows | 1 | External windows | 1 | External windows | 2.6.1.1.1 | 5 | 0 | External windows | 3 – Exterior and External Works
2 |  | 6 |  | 1 |  | 1 |  | 2 | Ironmongery | 2.6.1.1.2 | 5 | 0 | Windows – Ironmongery | 3 – Exterior and External Works
2 |  | 6 |  | 1 |  | 1 |  | 8 | Solar/rain screening over cladding system to windows | 2.6.1.1.8 | 5 | 0 | Windows – Solar/rain screening over cladding system | 3 – Exterior and External Works
2 |  | 6 |  | 1 |  | 1 |  | 9 | Photovoltaic glazing (integral to window system) | 2.6.1.1.9 | 5 | 0 | Photovoltaic glazing (integral to window system) | 3 – Exterior and External Works
2 |  | 6 |  | 1 |  | 1 |  | 10 | Canopies | 2.6.1.1.10 | 5 | 0 | Canopies | 3 – Exterior and External Works
2 |  | 6 |  | 1 |  | 1 |  | 11 | Protective film applied to windows | 2.6.1.1.11 | 5 | 0 | Windows – Protective film applied | 3 – Exterior and External Works
2 |  | 6 |  | 1 |  | 1 |  | 14 | Painting and decorating | 2.6.1.1.14 | 5 | 0 | Windows (external) – Painting and decorating | 3 – Exterior and External Works
2 |  | 6 |  | 1 |  | 2 | Louvres | 3 | Louvered windows and panels | 2.6.1.2.3 | 5 | 0 | Windows – Louvres and panels | 3 – Exterior and External Works
2 |  | 6 |  | 1 |  | 3 | Shop fronts | 4 | External shop front | 2.6.1.3.4 | 5 | 0 | Shop fronts | 3 – Exterior and External Works
2 |  | 6 |  | 1 |  | 4 | Roller shutters (RS) | 5 | Roller shutters, sliding shutters, grilles | 2.6.1.4.5 | 5 | 0 | RS – Roller shutters, sliding shutters, grilles | 3 – Exterior and External Works
2 |  | 6 |  | 1 |  | 4 |  | 6 | Fly screens and storm windows | 2.6.1.4.6 | 5 | 0 | RS – Fly screens and storm windows | 3 – Exterior and External Works
2 |  | 6 |  | 1 |  | 4 |  | 7 | Integral blinds to windows | 2.6.1.4.7 | 5 | 0 | RS – Integral blinds to windows | 3 – Exterior and External Works
2 |  | 6 |  | 1 |  | 4 |  | 12 | External blinds, shutters, etc. | 2.6.1.4.12 | 5 | 0 | RS – External blinds, shutters, etc. | 3 – Exterior and External Works
2 |  | 6 |  | 2 | External doors (ED) | 1 | External doors | 1 | Entrance doors, frames, linings, doorsets | 2.6.2.1.1 | 5 | 0 | ED – Entrance doors, frames, linings, doorsets | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 1 |  | 2 | Entrance screens and doors, inc frames | 2.6.2.1.2 | 5 | 0 | ED – Entrance screens and doors, inc frames | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 1 |  | 4 | Patio doors | 2.6.2.1.4 | 5 | 0 | ED – Patio doors | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 1 |  | 8 | Manual and automatic doors | 2.6.2.1.8 | 5 | 0 | ED – Manual and automatic doors | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 1 |  | 11 | Fanlights and side panels integral to doors | 2.6.2.1.11 | 5 | 0 | ED – Fanlights and side panels integral to doors | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 1 |  | 13 | Ironmongery | 2.6.2.1.13 | 5 | 0 | ED – Ironmongery | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 1 |  | 14 | Glazed vision panels | 2.6.2.1.14 | 5 | 0 | ED – Glazed vision panels | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 1 |  | 15 | Painting and decorating | 2.6.2.1.15 | 5 | 0 | Ed – Painting and decorating | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 1 |  | 16 | Fly screens and storm windows | 2.6.2.1.16 | 5 | 0 | ED – Fly screens and storm windows | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 1 |  | 17 | Integral blinds to doors | 2.6.2.1.17 | 5 | 0 | ED – Integral blinds to doors | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 1 |  | 18 | Solar / rain screen over cladding to doors | 2.6.2.1.18 | 5 | 0 | ED – Solar / rain screen over cladding to doors | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 2 | Revolving doors | 3 | Revolving doors | 2.6.2.2.3 | 5 | 0 | ED – Revolving doors | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 3 | Shop front doors | 7 | External shop front doors | 2.6.2.3.7 | 5 | 0 | ED – External shop front doors | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 4 | Roller shutters | 6 | Roller shutters, sliding shutters in doors | 2.6.2.4.6 | 5 | 0 | ED – Roller shutters, sliding shutters in doors | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 5 | Garage doors | 5 | Garage doors | 2.6.2.5.5 | 5 | 0 | ED – Garage doors | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 6 | Canopies | 9 | Canopies, etc. providing protection | 2.6.2.6.9 | 5 | 0 | ED – Canopies, etc. providing protection | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 7 | Grilles | 10 | Grilles (fixed and folding) | 2.6.2.7.10 | 5 | 0 | ED – Grilles (fixed and folding) | 3 – Exterior and External Works
2 |  | 6 |  | 2 |  | 8 | Architraves | 12 | Architraves | 2.6.2.8.12 | 5 | 0 | ED – Architraves | 3 – Exterior and External Works
2 |  | 7 | Internal walls and partitions (IW) | 1 | Walls and partitions | 1 | Walls and partitions |  |  | 2.7.1.1 | 4 | 0 | IW – Walls and partitions – state type (block; timber) | 1 – Building Structure
2 |  | 7 |  | 1 |  | 1 |  | 3 | Internal shop fronts | 2.7.1.1.3 | 5 | 0 | IW – Internal shop fronts | 1 – Building Structure
2 |  | 7 |  | 1 |  | 1 |  | 9 | Borrowed lights/screens, etc. | 2.7.1.1.9 | 5 | 0 | IW – Borrowed lights/screens, etc. | 1 – Building Structure
2 |  | 7 |  | 1 |  | 1 |  | 17 | Integral blinds in partitions | 2.7.1.1.17 | 5 | 0 | IW – Integral blinds in partitions | 1 – Building Structure
2 |  | 7 |  | 1 |  | 3 | Fixed partitions | 22 | Fixed partitions | 2.7.1.3.22 | 5 | 0 | IW – Fixed partitions | 1 – Building Structure
2 |  | 7 |  | 2 | Balustrades and handrails | 1 | Combined Balustrades and handrails | 1 | Balustrades and handrails | 2.7.2.1.1 | 5 | 0 | IW – Balustrades and handrails | 4 – Interior Finishes and FF&E
2 |  | 7 |  | 3 | Movable room dividers | 1 | Moveable room dividers | 1 | Moveable room dividers | 2.7.3.1.1 | 5 | 0 | IW – Moveable room dividers | 4 – Interior Finishes and FF&E
2 |  | 7 |  | 4 | Cubicles | 1 | Cubicles | 1 | Proprietary pre finished panel cubicles | 2.7.4.1.1 | 5 | 0 | IW – Proprietary pre finished panel cubicles | 4 – Interior Finishes and FF&E
2 |  | 8 | Internal doors (ID) | 1 | Internal doors (ID) | 1 | Internal doors – standard or purpose made | 1 | Doors (including standard doors or purpose made doors | 2.8.1.1.1 | 5 | 0 | ID – Doors, inc. standard doors or purpose made doors | 4 – Interior Finishes and FF&E
2 |  | 8 |  | 1 |  | 1 |  | 5 | Glazed vision panels, etc. | 2.8.1.1.5 | 5 | 0 | ID – Glazed vision panels | 4 – Interior Finishes and FF&E
2 |  | 8 |  | 1 |  | 1 |  | 6 | Sliding and folding doors in fixed partitions | 2.8.1.1.6 | 5 | 0 | ID – Sliding and folding doors in fixed partitions | 4 – Interior Finishes and FF&E
2 |  | 8 |  | 1 |  | 1 |  | 7 | Hatches | 2.8.1.1.7 | 5 | 0 | ID – Hatches | 4 – Interior Finishes and FF&E
2 |  | 8 |  | 1 |  | 1 |  | 8 | Ironmongery | 2.8.1.1.8 | 5 | 0 | ID – Ironmongery | 4 – Interior Finishes and FF&E
2 |  | 8 |  | 1 |  | 1 |  | 10 | Painting and decorating | 2.8.1.1.10 | 5 | 0 | ID – Painting and decorating | 4 – Interior Finishes and FF&E
2 |  | 8 |  | 1 |  | 2 | Fire resisting doors | 1.A | Fire resisting doors | 2.8.1.2.1.A | 5 | 0 | ID – Fire resisting doors | 4 – Interior Finishes and FF&E
2 |  | 8 |  | 1 |  | 3 | Door sets | 3 | Door sets | 2.8.1.3.3 | 5 | 0 | ID – Door sets | 4 – Interior Finishes and FF&E
2 |  | 8 |  | 1 |  | 4 | Composite door and sidelights/over panels | 4 | Composite door and fanlight | 2.8.1.4.4 | 5 | 0 | ID – Composite door and fanlight | 4 – Interior Finishes and FF&E
2 |  | 8 |  | 1 |  | 5 | Roller /sliding shutters, etc. | 8 | Roller/sliding door | 2.8.1.5.8 | 5 | 0 | ID – Roller/sliding door | 4 – Interior Finishes and FF&E
2 |  | 8 |  | 1 |  | 6 | Architraves | 9 | Architraves | 2.8.1.6.9 | 5 | 0 | ID – Architraves | 4 – Interior Finishes and FF&E
3 | Internal finishes | 1 | Wall finishes (WF) | 1 | Finishes to walls | 1 | Wall finishes | 1 | In-situ coatings applied to walls | 3.1.1.1.1 | 5 | 0 | WF – Wall finishes (state type e.g. plaster; timber etc) | 4 – Interior Finishes and FF&E
3 |  | 1 |  | 1 |  | 1 |  | 3 | Plasterboard or other sheet linings | 3.1.1.1.3 | 5 | 0 | WF – Plasterboard or other sheet linings | 4 – Interior Finishes and FF&E
3 |  | 1 |  | 1 |  | 1 |  | 4 | Ceramic wall tiling | 3.1.1.1.4 | 5 | 1 | WF – Specialist wall finishes | 4 – Interior Finishes and FF&E
3 |  | 1 |  | 1 |  | 1 |  | 12 | Specialist wall finishes | 3.1.1.1.12 | 5 | 0 | WF – Acoustic Insulation | 4 – Interior Finishes and FF&E
3 |  | 1 |  | 1 |  | 2 | Picture /dado rails | 7 | Picture and dado rail | 3.1.1.2.7 | 5 | 0 | WF – Picture and dado rail | 4 – Interior Finishes and FF&E
3 |  | 1 |  | 1 |  | 3 | Proprietary impact and bumper guards | 8 | Wall protection | 3.1.1.3.8 | 5 | 0 | WF – Wall protection | 4 – Interior Finishes and FF&E
3 |  | 2 | Floor finishes (FF) | 1 | Finishes to floors | 1 | Floor finishes – state type | 1 | Non structural screeds | 3.2.1.1.1 | 5 | 1 | FF – Non structural screeds | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 1 |  | 2 | Latex screeds | 3.2.1.1.2 | 5 | 0 | FF – Latex screeds | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 1 |  | 3 | Chemical surface hardeners | 3.2.1.1.3 | 5 | 0 | FF – Chemical surface hardeners | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 1 |  | 4 | Floating floors | 3.2.1.1.4 | 5 | 0 | FF – Floating floors | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 1 |  | 5 | Resin boned resilient layers | 3.2.1.1.5 | 5 | 0 | FF – Resin boned resilient layers | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 1 |  | 6 | Insitu floor finishes | 3.2.1.1.6 | 5 | 0 | FF – Insitu floor finishes | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 1 |  | 7 | Hard tiled floor finishes | 3.2.1.1.7 | 5 | 0 | FF – Hard tiled floor finishes | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 1 |  | 8 | Wood block | 3.2.1.1.8 | 5 | 0 | FF – Wood block | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 1 |  | 9 | Proprietary thin tiled and strip flooring | 3.2.1.1.9 | 5 | 0 | FF – Proprietary thin tiled and strip flooring | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 1 |  | 10 | Floor painting and sealing | 3.2.1.1.10 | 5 | 0 | FF – Floor painting and sealing | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 1 |  | 11 | Carpets (edge fixed including underlay) | 3.2.1.1.11 | 5 | 0 | FF – Carpets (edge fixed including underlay) | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 1 |  | 12 | Tile/sheet floors | 3.2.1.1.12 | 5 | 0 | FF – Tile/sheet floors | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 2 | Specialist flooring systems | 13 | Timber sprung floor | 3.2.1.2.13 | 5 | 0 | FF – Timber sprung floor | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 3 | Skirtings | 17 | Skirtings | 3.2.1.3.17 | 5 | 0 | FF – Skirtings | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 4 | Mat wells | 18 | Matwells | 3.2.1.4.18 | 5 | 0 | FF – Matwells | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 5 | Finishes to swimming pools tanks | 15 | Finishes to swimming pools | 3.2.1.5.15 | 5 | 0 | FF – Finishes to swimming pools | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 6 | Line markings | 19 | Line markings | 3.2.1.6.19 | 5 | 0 | FF – Line markings | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 1 |  | 7 | Numeral and symbols | 19 | Numerals and symbols | 3.2.1.7.19 | 5 | 0 | FF – Numerals and symbols | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 2 | Raised access floors | 1 | Raised access floor systems | 1 | Proprietary access floor system | 3.2.2.1.1 | 5 | 0 | FF – Proprietary access floor system | 4 – Interior Finishes and FF&E
3 |  | 2 |  | 2 |  | 2 | Skirtings |  |  | 3.2.2.2 | 4 | 0 | FF – Skirtings | 4 – Interior Finishes and FF&E
3 |  | 3 | Ceiling finishes (CF) | 1 | Finishes to ceilings | 1 | Ceiling finishes | 1 | Linings to ceilings | 3.3.1.1.1 | 5 | 0 | CF – Ceiling finishes | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 1 |  | 1 |  | 3 | In-situ coatings applied to ceilings | 3.3.1.1.3 | 5 | 0 | CF – In-situ coatings applied to ceilings | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 1 |  | 1 |  | 4 | Sprayed monolithic coatings | 3.3.1.1.4 | 5 | 0 | CF – Sprayed monolithic coatings | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 1 |  | 1 |  | 5 | Painting and decorating to ceilings | 3.3.1.1.5 | 5 | 0 | CF – Painting and decorating to ceilings | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 1 |  | 1 |  | 7 | Specialist ceiling finishes | 3.3.1.1.7 | 5 | 0 | CF – Specialist ceiling finishes | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 1 |  | 2 | Cornices, covings, etc. | 6 | Cornices and covings | 3.3.1.2.6 | 5 | 0 | CF – Cornices and covings | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 2 | False ceilings | 1 | False ceilings – state type | 1 | Proprietary suspended ceiling systems, including suspension systems | 3.3.2.1.1 | 5 | 0 | CF – Proprietary suspended ceiling systems, including suspension systems | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 2 |  | 1 |  | 3 | Insitu coatings | 3.3.2.1.3 | 5 | 0 | CF – Insitu coatings | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 2 |  | 1 |  | 4 | Painting and decorating to false ceilings | 3.3.2.1.4 | 5 | 0 | CF – Painting and decorating to false ceilings | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 2 |  | 2 | Cornices and covings | 5 | Cornices and covings | 3.3.2.2.5 | 5 | 0 | CF – Cornices and covings | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 2 |  | 3 | Access hatches | 7 | Access hatches | 3.3.2.3.7 | 5 | 0 | CF – Access hatches | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 3 | Demountable suspended ceilings | 1 | Demountable suspended ceilings |  |  | 3.3.3.1 | 4 | 0 | CF – Demountable suspended ceilings | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 3 |  | 2 | Shadow gaps, etc. | 6 | Shadow gaps | 3.3.3.2.6 | 5 | 0 | CF – Shadow gaps | 4 – Interior Finishes and FF&E
3 |  | 3 |  | 3 |  | 3 | Access hatches | 7 | Access hatches | 3.3.3.3.7 | 5 | 0 | CF – Access hatches | 4 – Interior Finishes and FF&E
4 | Fittings, furnishings and equipment | 1 | Fittings, furnishings and equipment (FFE) | 1 | General fittings, furnishings and equipment | 1 | Fittings |  |  | 4.1.1.1 | 4 | 0 | FFE – Fittings (state type) | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 1 |  | 1 | Counters, desks & benches and worktops | 4.1.1.1.1 | 5 | 0 | FFE – Counters, desks & benches and worktops | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 1 |  | 2 | Mirrors | 4.1.1.1.2 | 5 | 0 | FFE – Mirrors | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 1 |  | 3 | Curtains, tracks, etc. | 4.1.1.1.3 | 5 | 0 | FFE – Curtains, tracks, etc. | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 1 |  | 5 | Fireplace surrounds and hearths | 4.1.1.1.5 | 5 | 0 | FFE – Fireplace surrounds and hearths | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 1 |  | 8 | Storage racks, shelving, etc. | 4.1.1.1.8 | 5 | 0 | FFE – Storage racks, shelving, etc. | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 1 |  | 10 | Fitted seating upholstery | 4.1.1.1.10 | 5 | 0 | FFE – Fitted seating upholstery | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 2 | Furnishings |  |  | 4.1.1.2 | 4 | 0 | FFE – Furnishings (state type) | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 2 |  | 4 | Blinds | 4.1.1.2.4 | 5 | 0 | FFE – Blinds | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 2 |  | 6 | Wall hangings | 4.1.1.2.6 | 5 | 0 | FFE – Wall hangings | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 2 |  | 7 | Loose carpets | 4.1.1.2.7 | 5 | 0 | FFE – Loose carpets | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 2 |  | 9 | Tables and chairs | 4.1.1.2.9 | 5 | 0 | FFE – Tables and chairs | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 2 |  | 11 | Bedroom furniture | 4.1.1.2.11 | 5 | 0 | FFE – Bedroom furniture | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 2 |  | 13 | Lockers, hat and coat rails | 4.1.1.2.13 | 5 | 0 | FFE – Lockers, hat and coal rails | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 3 | Equipment – state type | 14 | Hand held firefighting equipment | 4.1.1.3.14 | 5 | 0 | FFE – Hand held firefighting equipment – Water, Co2 etc | 10 – Safety Systems
4 |  | 1 |  | 1 |  | 3 |  | 15 | Bins, etc. | 4.1.1.3.15 | 5 | 0 | FFE – Bins | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 3 |  | 16 | Safes | 4.1.1.3.16 | 5 | 0 | FFE – Safes | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 3 |  | 17 | Vacuum cleaners and cleaning equipment | 4.1.1.3.17 | 5 | 0 | FFE – Vacuum cleaners and cleaning equipment | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 3 |  | 18 | Televisions, hi-fi and computers | 4.1.1.3.18 | 5 | 0 | FFE – Televisions, hi-fi and computers | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 3 |  | 19 | Vending machines | 4.1.1.3.19 | 5 | 0 | FFE – Vending machines | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 1 |  | 3 |  | 20 | Telephone booths and enclosure | 4.1.1.3.20 | 5 | 0 | FFE – Telephone booths and enclosure | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 2 | Domestic kitchen fittings and equipment | 1 | Kitchen units | 1 | Domestic kitchen units | 4.1.2.1.1 | 5 | 0 | FFE – Domestic kitchen units | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 2 |  | 1 |  | 2 | Sinks and taps etc, part of kitchen units | 4.1.2.1.2 | 5 | 0 | FFE – Sinks and taps etc, part of kitchen units | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 2 |  | 1 |  | 8 | Kitchen equipment (taken in 4.1.2.3 to 7) | 4.1.2.1.8 | 5 | 0 | FFE – Kitchen equipment (taken in 4.1.2.3 to 7) | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 2 |  | 1 |  | 9 | Other kitchen fittings and equipment | 4.1.2.1.9 | 5 | 0 | FFE – Other kitchen fittings and equipment | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 2 |  | 2 | Kitchen appliances | 3 | Catering equipment (ovens, hobs, etc.) | 4.1.2.2.3 | 5 | 0 | FFE – Catering equipment (ovens, hobs, etc.) | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 2 |  | 2 |  | 4 | Refrigerators/ freezers | 4.1.2.2.4 | 5 | 0 | FFE – Refrigerators/freezers | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 2 |  | 2 |  | 5 | Dishwashers | 4.1.2.2.5 | 5 | 0 | FFE – Dishwashers | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 2 |  | 2 |  | 6 | White goods (washing machine, dryers) | 4.1.2.2.6 | 5 | 0 | FFE – White goods (e.g. washing machine, dryers) | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 2 |  | 3 | Waste bins, towel ranks, etc. (Not maintained) | 7 | Waste bins, towel racks | 4.1.2.3.7 | 5 | 0 | FFE – Waste bins, towel racks | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 3 | Special-purpose fittings, furnishings & equipment | 1 | Fittings | 1 | Special purpose fittings (type for particular buildings such as educational; hospitals, factories, defence, farming, fishing etc) | 4.1.3.1.1 | 5 | 0 | FFE – Special purpose fittings (type for particular buildings such as educational; hospitals, factories, defence, farming, fishing, etc.) | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 3 |  | 2 | Furnishings | 1 | Special purpose furnishings(type for particular buildings such as educational; hospitals and other by function usage) | 4.1.3.2.1 | 5 | 0 | FFE – Special purpose furnishings (type for particular buildings such as educational; hospitals and other by function usage) | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 3 |  | 3 | Equipment | 1 | Special purpose equipment (type for particular buildings such as educational; hospitals and others by function usage) | 4.1.3.3.1 | 5 | 0 | FFE – Special purpose equipment (type for particular buildings such as educational; hospitals and others by function usage) | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 3 |  | 3 |  | 2 | Other special purpose fittings, furnishings and equipment (state type) | 4.1.3.3.2 | 5 | 0 | FFE – Other special purpose fittings, furnishings and equipment (state type) | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 4 | Signs/notices | 1 | Components | 1 | Directional signboards | 4.1.4.1.1 | 5 | 0 | FFE – Directional signboards | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 4 |  | 1 |  | 2 | Notice boards, white boards, etc. | 4.1.4.1.2 | 5 | 0 | FFE – Notice boards, white boards, etc. | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 4 |  | 1 |  | 3 | Sign writing | 4.1.4.1.3 | 5 | 0 | FFE – Sign writing | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 4 |  | 1 |  | 4 | Shop front lettering, emblems and symbols | 4.1.4.1.4 | 5 | 0 | FFE – Shop front lettering, emblems and symbols | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 4 |  | 1 |  | 5 | Door or floor numbering or lettering | 4.1.4.1.5 | 5 | 0 | FFE – Door or floor numbering or lettering | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 4 |  | 1 |  | 6 | Nameplates, plaques and ID symbols | 4.1.4.1.6 | 5 | 0 | FFE – Nameplates, plaques and ID symbols | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 4 |  | 1 |  | 7 | Lettering emblems and directional symbols | 4.1.4.1.7 | 5 | 0 | FFE – Lettering emblems and directional symbols | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 5 | Works of art | 1 | Not covered by NRM 3 |  |  | 4.1.5.1 | 4 | 0 | FFE – Works of art | NOT APPLICABLE
4 |  | 1 |  | 5 |  | 2 | Decorative features and panels | 2 | Decorative features – including panels | 4.1.5.2.2 | 5 | 0 | FFE – Decorative features – including panels | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 6 | Non mechanical and non electrical equipment | 1 | Equipment | 1 | Disabled access equipment | 4.1.6.1.1 | 5 | 0 | FFE – Disabled access equipment | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 6 |  | 1 |  | 2 | Other non-mechanical/electrical equipment | 4.1.6.1.2 | 5 | 0 | FFE – Other non-mechanical/electrical equipment | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 6 |  | 2 | Removable ladders | 2 | Ladders | 4.1.6.2.2 | 5 | 0 | FFE – Removable Ladders | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 7 | Internal planting | 1 | Plants and shrub beds | 2 | Planting container grown plants | 4.1.7.1.2 | 5 | 0 | FFE – Planting container grown plants | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 7 |  | 1 |  | 3 | Planting shrubs | 4.1.7.1.3 | 5 | 0 | FFE – Planting shrubs | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 7 |  | 1 |  | 5 | Planting to containers | 4.1.7.1.5 | 5 | 0 | FFE – Planting to containers | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 7 |  | 1 |  | 7 | Watering feeding and maintenance | 4.1.7.1.7 | 5 | 0 | FFE – Watering feeding and maintenance | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 7 |  | 4 |  | 8 | Replacement plants | 4.1.7.4.8 | 5 | 0 | FFE – Replacement plants | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 7 |  | 4 |  | 9 | Artificial plants | 4.1.7.4.9 | 5 | 0 | FFE – Artificial plants | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 7 |  | 2 | Plant containers | 1 | Internal prefabricated plant containers | 4.1.7.2.1 | 5 | 0 | FFE – Internal prefabricated plant containers | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 7 |  | 3 | Trees | 4 | Planting trees | 4.1.7.3.4 | 5 | 0 | FFE – Planting trees | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 7 |  | 4 | Tree planters | 6 | Planting containers | 4.1.7.4.6 | 5 | 0 | FFE – Planting containers | 4 – Interior Finishes and FF&E
4 |  | 1 |  | 8 | Bird and vermin control | 1 | Wires, nets, traps, etc. |  |  | 4.1.8.1 | 4 | 0 | FFE – Wires, nets and traps | 13 – Specialist
4 |  | 1 |  | 8 |  | 2 | Electronic and sonic systems | 2 | Electronic and sonic systems | 4.1.8.2.2 | 5 | 0 | FFE – Electronic and sonic systems | 13 – Specialist
4 |  | 1 |  | 8 |  | 3 | Bird repellent coatings | 3 | Bird repellent coatings | 4.1.8.3.3 | 5 | 0 | FFE – Bird repellent coatings | 13 – Specialist
5 | Services | 1 | Sanitary appliances (SA) | 1 | Sanitary appliances | 1 | Sanitary appliances | 1 | WC, slop hoppers, urinals/cisterns | 5.1.1.1.1 | 5 | 0 | SA – WC, slop hoppers, urinals/cisterns | 7 – Plumbing and Sanitary
5 |  | 1 |  | 1 |  | 1 |  | 2 | Sinks | 5.1.1.1.2 | 5 | 0 | SA – Sinks | 7 – Plumbing and Sanitary
5 |  | 1 |  | 1 |  | 1 |  | 3 | Wash basins | 5.1.1.1.3 | 5 | 0 | SA – Wash basins | 7 – Plumbing and Sanitary
5 |  | 1 |  | 1 |  | 1 |  | 4 | Bidets | 5.1.1.1.4 | 5 | 0 | SA – Bidets | 7 – Plumbing and Sanitary
5 |  | 1 |  | 1 |  | 1 |  | 5 | Baths | 5.1.1.1.5 | 5 | 0 | SA – Baths | 7 – Plumbing and Sanitary
5 |  | 1 |  | 1 |  | 1 |  | 6 | Shower trays | 5.1.1.1.6 | 5 | 0 | SA – Shower trays | 7 – Plumbing and Sanitary
5 |  | 1 |  | 1 |  | 1 |  | 7 | Shower unit including head/hose | 5.1.1.1.7 | 5 | 0 | SA – Shower unit including head/hose | 7 – Plumbing and Sanitary
5 |  | 1 |  | 1 |  | 1 |  | 8 | Supplementary list (pumps) | 5.1.1.1.8 | 5 | 0 | SA – Shower booster pumps | 7 – Plumbing and Sanitary
5 |  | 1 |  | 1 |  | 1 |  | 9 | Supplementary list (valves) | 5.1.1.1.9 | 5 | 0 | SA – Shower valves | 7 – Plumbing and Sanitary
5 |  | 1 |  | 1 |  | 1 |  | 10 | Drinking fountains | 5.1.1.1.10 | 5 | 0 | SA – Drinking fountains | 7 – Plumbing and Sanitary
5 |  | 1 |  | 1 |  | 1 |  | 11 | Taps and waste fittings | 5.1.1.1.11 | 5 | 0 | SA – Taps and waste fittings | 7 – Plumbing and Sanitary
5 |  | 1 |  | 1 |  | 1 |  | 12 | Water saving devices | 5.1.1.1.12 | 5 | 0 | SA – Water saving devices | 7 – Plumbing and Sanitary
5 |  | 1 |  | 1 |  | 1 |  | 13 | Automated controls and sensors | 5.1.1.1.13 | 5 | 0 | SA – Automated controls and sensors | 7 – Plumbing and Sanitary
5 |  | 1 |  | 2 | Sanitary ancillaries | 1 | Fittings | 1 | Shower cubicles | 5.1.2.1.1 | 5 | 0 | SA – Shower cubicles | 7 – Plumbing and Sanitary
5 |  | 1 |  | 2 |  | 1 |  | 2 | Bath/shower curtain and rails | 5.1.2.1.2 | 5 | 0 | SA – Bath/shower curtain and rails | 7 – Plumbing and Sanitary
5 |  | 1 |  | 2 |  | 1 |  | 3 | Grab/support rail | 5.1.2.1.3 | 5 | 0 | SA – Grab/support rail | 7 – Plumbing and Sanitary
5 |  | 1 |  | 2 |  | 1 |  | 4 | Towel rails and holders | 5.1.2.1.4 | 5 | 0 | SA – Towel rails and holders | 7 – Plumbing and Sanitary
5 |  | 1 |  | 2 |  | 1 |  | 5 | Hand dryers | 5.1.2.1.5 | 5 | 0 | SA – Hand dryers | 7 – Plumbing and Sanitary
5 |  | 1 |  | 2 |  | 1 |  | 6 | Paper towel dispensers | 5.1.2.1.6 | 5 | 0 | SA – Paper towel dispensers | 7 – Plumbing and Sanitary
5 |  | 1 |  | 2 |  | 1 |  | 7 | Sanitary incinerators (towel disposal) | 5.1.2.1.7 | 5 | 0 | SA – Sanitary incinerators (towel disposal) | 7 – Plumbing and Sanitary
5 |  | 1 |  | 2 |  | 1 |  | 8 | Macerators | 5.1.2.1.8 | 5 | 0 | SA – Macerators | 7 – Plumbing and Sanitary
5 |  | 1 |  | 2 |  | 1 |  | 9 | Other sanitary fittings (state type) | 5.1.2.1.9 | 5 | 0 | SA – Other sanitary fittings (state type) | 7 – Plumbing and Sanitary
5 |  | 2 | Services equipment (SE) | 1 | Services equipment | 1 | Services equipment | 1 | Catering equipment – state type | 5.2.1.1.1 | 5 | 0 | SE – Catering equipment – state type | 8 – Service Equipment
5 |  | 2 |  | 1 |  | 1 |  | 2 | Sinks – supplied with catering equipment | 5.2.1.1.2 | 5 | 0 | SE – Sinks – supplied with catering equipment | 8 – Service Equipment
5 |  | 2 |  | 1 |  | 1 |  | 3 | Food storage equipment | 5.2.1.1.3 | 5 | 0 | SE – Food storage equipment | 8 – Service Equipment
5 |  | 2 |  | 1 |  | 1 |  | 4 | Other free standing/fixed equipment | 5.2.1.1.4 | 5 | 0 | SE – Other free standing/fixed equipment | 8 – Service Equipment
5 |  | 3 | Disposal installations (DI) | 1 | Foul drainage above ground | 1 | Drainage to sanitary appliances | 1 | Waste pipes and fittings | 5.3.1.1.1 | 5 | 0 | DI – Waste pipes and fittings | 7 – Plumbing and Sanitary
5 |  | 3 |  | 1 |  | 2 | Drainage to services equipment | 2 | Discharge stacks and waste pipes | 5.3.1.2.2 | 5 | 0 | DI – Discharge stacks and waste pipes | 7 – Plumbing and Sanitary
5 |  | 3 |  | 1 |  | 2 |  | 3 | Ventilation stacks and pipes | 5.3.1.2.3 | 5 | 0 | DI – Ventilation stacks and pipes | 7 – Plumbing and Sanitary
5 |  | 3 |  | 1 |  | 2 |  | 4 | Traps access points and rodding eyes | 5.3.1.2.4 | 5 | 0 | DI – Traps access points and rodding eyes | 7 – Plumbing and Sanitary
5 |  | 3 |  | 1 |  | 2 |  | 5 | Pipeline assemblies | 5.3.1.2.5 | 5 | 0 | DI – Pipeline assemblies | 7 – Plumbing and Sanitary
5 |  | 3 |  | 1 |  | 2 |  | 6 | Floor channels and gratings | 5.3.1.2.6 | 5 | 0 | DI – Floor channels and gratings | 7 – Plumbing and Sanitary
5 |  | 3 |  | 1 |  | 2 |  | 7 | Sump pumps | 5.3.1.2.7 | 5 | 0 | DI – Sump pumps | 7 – Plumbing and Sanitary
5 |  | 3 |  | 2 | Chemical, toxic and industrial liquid waste drainage | 1 | Drainage to appliance or equipment | 1 | Pipe work systems | 5.3.2.1.1 | 5 | 0 | DI – Pipe work systems | 13 – Specialist
5 |  | 3 |  | 2 |  | 1 |  | 2 | Traps access points and rodding eyes | 5.3.2.1.2 | 5 | 0 | DI – Traps access points and rodding eyes | 13 – Specialist
5 |  | 3 |  | 2 |  | 1 |  | 3 | Gullies | 5.3.2.1.3 | 5 | 0 | DI – Gullies | 13 – Specialist
5 |  | 3 |  | 2 |  | 1 |  | 5 | Storage tanks and vessels | 5.3.2.1.5 | 5 | 0 | DI – Storage tanks and vessels | 13 – Specialist
5 |  | 3 |  | 2 |  | 1 |  | 6 | Settlement tanks | 5.3.2.1.6 | 5 | 0 | DI – Settlement tanks | 13 – Specialist
5 |  | 3 |  | 2 |  | 1 |  | 7 | Effluent treatment plant | 5.3.2.1.7 | 5 | 0 | DI – Effluent treatment plant | 13 – Specialist
5 |  | 3 |  | 2 |  | 1 |  | 8 | Dosing equipment | 5.3.2.1.8 | 5 | 0 | DI – Dosing equipment | 13 – Specialist
5 |  | 3 |  | 2 |  | 1 |  | 9 | Sterilisation equipment | 5.3.2.1.9 | 5 | 0 | DI – Sterilisation equipment | 13 – Specialist
5 |  | 3 |  | 2 |  | 1 |  | 11 | Thermal insulation | 5.3.2.1.11 | 5 | 0 | DI – Thermal insulation | 13 – Specialist
5 |  | 3 |  | 2 |  | 1 |  | 13 | Control components | 5.3.2.1.13 | 5 | 0 | DI – Control components | 13 – Specialist
5 |  | 3 |  | 2 |  | 1 |  | 14 | Monitoring equipment | 5.3.2.1.14 | 5 | 0 | DI – Monitoring equipment | 13 – Specialist
5 |  | 3 |  | 2 |  | 1 |  | 15 | Painting anti-corrosion treatments | 5.3.2.1.15 | 5 | 0 | DI – Painting anti-corrosion treatments | 13 – Specialist
5 |  | 3 |  | 3 | Refuse disposal | 1 | Refuse disposal installations | 1 | Refuse input devices | 5.3.3.1.1 | 5 | 0 | DI – Refuse input devices | 7 – Plumbing and Sanitary
[8 empty] | 2 | Refuse chutes and ducts | 5.3.3.1.2 | 5 | 0 | DI – Refuse chutes and ducts | 7 – Plumbing and Sanitary
[8 empty] | 3 | Plant for compacting/macerating refuse | 5.3.3.1.3 | 5 | 0 | DI – Plant for compacting/macerating refuse | 7 – Plumbing and Sanitary
[8 empty] | 4 | Refuse collection equipment | 5.3.3.1.4 | 5 | 0 | DI – Refuse collection equipment | 7 – Plumbing and Sanitary
5 |  | 3 |  | 3 |  | 1 |  | 5 | Incineration plant | 5.3.3.1.5 | 5 | 0 | DI – Incineration plant | 7 – Plumbing and Sanitary
5 |  | 3 |  | 3 |  | 1 |  | 6 | Paper shredders | 5.3.3.1.6 | 5 | 0 | DI – Paper shredders | 7 – Plumbing and Sanitary
5 |  | 3 |  | 3 |  | 1 |  | 7 | Safety devices | 5.3.3.1.7 | 5 | 0 | DI – Safety devices | 7 – Plumbing and Sanitary
5 |  | 4 | Water installations (WI) | 1 | Mains water supply | 1 | Mains water supply | 1 | Pipe work systems | 5.4.1.1.1 | 5 | 0 | WI – Pipe work systems | 7 – Plumbing and Sanitary
5 |  | 4 |  | 1 |  | 1 |  | 2 | Supplementary list (valves) | 5.4.1.1.2 | 5 | 0 | WI – Valves | 7 – Plumbing and Sanitary
5 |  | 4 |  | 1 |  | 1 |  | 3 | Water meters | 5.4.1.1.3 | 5 | 0 | WI – Water meters | 7 – Plumbing and Sanitary
5 |  | 4 |  | 1 |  | 1 |  | 4 | Rising main to storage tanks | 5.4.1.1.4 | 5 | 0 | WI – Rising main to storage tanks | 7 – Plumbing and Sanitary
5 |  | 4 |  | 1 |  | 1 |  | 5 | Trace heating | 5.4.1.1.5 | 5 | 0 | WI – Trace heating | 7 – Plumbing and Sanitary
5 |  | 4 |  | 1 |  | 1 |  | 7 | Thermal insulation | 5.4.1.1.7 | 5 | 0 | WI – Thermal insulation | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 | Cold water distribution | 1 | Cold water distribution | 1 | CW Pipe work systems | 5.4.2.1.1 | 5 | 0 | WI – CW Pipe work systems | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 1 |  | 2 | Supplementary list (valves) | 5.4.2.1.2 | 5 | 0 | WI – Valves | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 1 |  | 3 | Water saving devices | 5.4.2.1.3 | 5 | 0 | WI – Water saving devices | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 1 |  | 4 | Supplementary list (taps and outlet fittings) | 5.4.2.1.4 | 5 | 0 | WI – Taps | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 1 |  | 5 | Supplementary list (pumps) | 5.4.2.1.5 | 5 | 0 | WI – Pumps | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 1 |  | 6 | Pressurisation units | 5.4.2.1.6 | 5 | 0 | WI – Pressurisation units | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 1 |  | 7 | Pressure booster sets | 5.4.2.1.7 | 5 | 0 | WI – Pressure booster sets | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 1 |  | 8 | Cold water storage tanks and cisterns | 5.4.2.1.8 | 5 | 0 | WI – Cold water storage tanks and cisterns | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 1 |  | 9 | Trace heating | 5.4.2.1.9 | 5 | 0 | WI – Trace heating | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 1 |  | 10 | Instrumentation and controls | 5.4.2.1.10 | 5 | 0 | WI – Instrumentation and controls | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 1 |  | 11 | Thermal insulation | 5.4.2.1.11 | 5 | 0 | WI – Thermal insulation | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 2 | Storage tanks | 2 | Storage tanks | 5.4.2.2.2 | 5 | 0 | WI – Storage tanks | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 3 | Rainwater harvesting | 12 | Rainwater harvesting | 5.4.2.3.12 | 5 | 0 | WI – Rainwater harvesting | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 3A | Grey water collection pipe systems | 13 | Grey water collection pipe systems | 5.4.2.3A.13 | 5 | 0 | WI – Grey water collection pipe systems | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 6 | Sundry items | 1 | Train water points | 5.4.2.6.1 | 5 | 0 | WI – Train water points | 7 – Plumbing and Sanitary
5 |  | 4 |  | 2 |  | 6 |  | 2 | Vehicle washing points | 5.4.2.6.2 | 5 | 0 | WI – Vehicle washing points | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 | Hot water distribution | 1 | Hot water distribution | 1 | Hot water systems (vented or unvented) | 5.4.3.1.1 | 5 | 0 | WI – Hot water systems (vented or unvented) | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 2 | Supplementary list (valves) | 5.4.3.1.2 | 5 | 0 | WI – Valves | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 3 | Water saving devices | 5.4.3.1.3 | 5 | 0 | WI – Water saving devices | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 4 | Supplementary list (taps and outlet fittings) | 5.4.3.1.4 | 5 | 0 | WI – Taps | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 5 | Supplementary list (pumps) | 5.4.3.1.5 | 5 | 0 | WI – Pumps | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 6 | Heat exchangers | 5.4.3.1.6 | 5 | 0 | WI – Heat exchangers | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 7 | Storage cylinders and calorifiers | 5.4.3.1.7 | 5 | 0 | WI – Storage cylinders and calorifiers | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 8 | Trace heating | 5.4.3.1.8 | 5 | 0 | WI – Trace heating | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 9 | Hot water storage tanks | 5.4.3.1.9 | 5 | 0 | WI – Hot water storage tanks | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 10 | Immersion heaters | 5.4.3.1.10 | 5 | 0 | WI – Immersion heaters | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 11 | Insulation combination units | 5.4.3.1.11 | 5 | 0 | WI – Insulation combination units | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 12 | Water softeners | 5.4.3.1.12 | 5 | 0 | WI – Water softeners | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 13 | Instrumentation and controls | 5.4.3.1.13 | 5 | 0 | WI – Instrumentation and controls | 7 – Plumbing and Sanitary
5 |  | 4 |  | 3 |  | 1 |  | 14 | Thermal insulation | 5.4.3.1.14 | 5 | 0 | WI – Thermal insulation | 7 – Plumbing and Sanitary
5 |  | 4 |  | 4 | Local hot water distribution | 1 | Water heaters | 1 | Instant water heaters | 5.4.4.1.1 | 5 | 0 | WI – Instant water heaters | 7 – Plumbing and Sanitary
5 |  | 4 |  | 4 |  | 1 |  | 2 | Under-sink, multipoint and over sink units | 5.4.4.1.2 | 5 | 0 | WI – Under-sink, multipoint and over sink units | 7 – Plumbing and Sanitary
5 |  | 4 |  | 5 | Steam and condensate distribution | 1 | Steam and condensate distribution | 1 | Steam services pipe work systems | 5.4.5.1.1 | 5 | 0 | WI – Steam services pipe work systems | 5 – HVAC and Mechanical
5 |  | 4 |  | 5 |  | 1 |  | 2 | Supplementary list (valves) | 5.4.5.1.2 | 5 | 0 | WI – Valves | 5 – HVAC and Mechanical
5 |  | 4 |  | 5 |  | 1 |  | 3 | Steam reduction stations | 5.4.5.1.3 | 5 | 0 | WI – Steam reduction stations | 5 – HVAC and Mechanical
5 |  | 4 |  | 5 |  | 1 |  | 4 | Condensate receivers | 5.4.5.1.4 | 5 | 0 | WI – Condensate receivers | 5 – HVAC and Mechanical
5 |  | 4 |  | 5 |  | 1 |  | 5 | Condensate pump sets | 5.4.5.1.5 | 5 | 0 | WI – Condensate pump sets | 5 – HVAC and Mechanical
5 |  | 4 |  | 5 |  | 1 |  | 6 | Steam connection units | 5.4.5.1.6 | 5 | 0 | WI – Steam connection units | 5 – HVAC and Mechanical
5 |  | 4 |  | 5 |  | 1 |  | 7 | Supplementary list (taps and outlet fittings) | 5.4.5.1.7 | 5 | 0 | WI – Taps | 5 – HVAC and Mechanical
5 |  | 4 |  | 5 |  | 1 |  | 8 | Heat exchangers | 5.4.5.1.8 | 5 | 0 | WI – Heat exchangers | 5 – HVAC and Mechanical
5 |  | 4 |  | 5 |  | 1 |  | 9 | Storage cylinders and calorifiers | 5.4.5.1.9 | 5 | 0 | WI – Storage cylinders and calorifiers | 5 – HVAC and Mechanical
5 |  | 4 |  | 5 |  | 1 |  | 10 | Instrumentation and controls | 5.4.5.1.10 | 5 | 0 | WI – Instrumentation and controls | 5 – HVAC and Mechanical
5 |  | 4 |  | 5 |  | 1 |  | 11 | Thermal insulation | 5.4.5.1.11 | 5 | 0 | WI – Thermal insulation | 5 – HVAC and Mechanical
5 |  | 5 | Heat source (HS) | 1 | Heat source | 1 | Heat source | 1 | Boilers – biomass | 5.5.1.1.1 | 5 | 0 | HS – Boilers Biomass | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 2 | Boiler – gas/oil | 5.5.1.1.2 | 5 | 0 | HS – Boiler Gas/oil | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 2.A | Boiler – steam | 5.5.1.1.2.A | 5 | 0 | HS – Boiler Steam | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 3 | Coal-fired boiler plant and ancillary items | 5.5.1.1.3 | 5 | 0 | HS – Coal-fired boiler plant and ancillary items | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 4 | Boiler – electric | 5.5.1.1.4 | 5 | 0 | HS – Boiler Electric | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 5 | Packaged steam generators | 5.5.1.1.5 | 5 | 0 | HS – Packaged steam generators | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 6 | Boiler – wood pellet | 5.5.1.1.6 | 5 | 0 | HS – Boiler Wood pellet | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 7 | Central combined heat and power plant | 5.5.1.1.7 | 5 | 0 | HS – Central combined heat and power plant | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 8 | Heat pumps | 5.5.1.1.8 | 5 | 0 | HS – Heat pumps | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 9 | Ground source heating | 5.5.1.1.9 | 5 | 0 | HS – Ground source heating | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 10 | Supplementary list (pumps) | 5.5.1.1.10 | 5 | 0 | HS – Pumps | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 10.A | Supplementary list (valves) | 5.5.1.1.10.A | 5 | 0 | HS – Valves | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 11 | Step down/non storage cylinders | 5.5.1.1.11 | 5 | 0 | HS – Step down/non storage cylinders | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 12 | Solar thermal panels | 5.5.1.1.12 | 5 | 0 | HS – Solar thermal panels | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 13 | Other heat sources (air source heating) | 5.5.1.1.13 | 5 | 0 | HS – Other heat sources (air source heating) | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 14 | Water tanks (header tanks) | 5.5.1.1.14 | 5 | 0 | HS – Water tanks (header tanks) | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 15 | Vibration isolation mountings | 5.5.1.1.15 | 5 | 0 | HS – Vibration isolation mountings | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 16 | Instrumentation and controls | 5.5.1.1.16 | 5 | 0 | HS – Instrumentation and controls | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 17 | Forced draft fans | 5.5.1.1.17 | 5 | 0 | HS – Forced draft fans | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 18 | Gantries | 5.5.1.1.18 | 5 | 0 | HS – Gantries | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 19 | Chimneys and flues | 5.5.1.1.19 | 5 | 0 | HS – Chimneys and flues | 5 – HVAC and Mechanical
5 |  | 5 |  | 1 |  | 1 |  | 20 | Forced draft extract | 5.5.1.1.20 | 5 | 0 | HS – Forced draft extract | 5 – HVAC and Mechanical
5 |  | 6 | Space heating and air conditioning (SHAC) | 1 | Central heating | 1 | Central heating systems | 1 | Central heating system | 5.6.1.1.1 | 5 | 0 | SHAC – Central heating system | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 2 | Heat distribution pipework systems | 5.6.1.1.2 | 5 | 0 | SHAC – Heat distribution pipework systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 3 | Heat emission units (e.g. radiators, etc.) | 5.6.1.1.3 | 5 | 0 | SHAC – Heat emission units (e.g. radiators, etc.) | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 4 | Under floor heating | 5.6.1.1.4 | 5 | 0 | SHAC – Under floor heating | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 5 | Heating ceiling panels | 5.6.1.1.5 | 5 | 0 | SHAC – Heating ceiling panels | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 6 | Warm air heating | 5.6.1.1.6 | 5 | 0 | SHAC – Warm air heating | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 7 | Convection systems | 5.6.1.1.7 | 5 | 0 | SHAC – Convection systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 8 | Fan assisted convection systems | 5.6.1.1.8 | 5 | 0 | SHAC – Fan assisted convection systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 9 | Cable heating systems | 5.6.1.1.9 | 5 | 0 | SHAC – Cable heating systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 10 | Plenum air-heating systems | 5.6.1.1.10 | 5 | 0 | SHAC – Plenum air-heating systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 11 | Off peak heating system | 5.6.1.1.11 | 5 | 0 | SHAC – Off peak heating system | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 12 | Distribution pipelines | 5.6.1.1.12 | 5 | 0 | SHAC – Distribution pipelines | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 13 | Heated towel rails | 5.6.1.1.13 | 5 | 0 | SHAC – Heated towel rails | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 14 | Supplementary list (valves) | 5.6.1.1.14 | 5 | 0 | SHAC – Valves | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 15 | Supplementary list (ductwork) | 5.6.1.1.15 | 5 | 0 | SHAC – Ductwork | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 16 | Air handling equipment | 5.6.1.1.16 | 5 | 0 | SHAC – Air handling equipment | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 17 | Grilles and diffusers | 5.6.1.1.17 | 5 | 0 | SHAC – Grilles and diffusers | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 18 | Plate recuperator | 5.6.1.1.18 | 5 | 0 | SHAC – Plate recuperator | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 19 | Thermal wheel | 5.6.1.1.19 | 5 | 0 | SHAC – Thermal wheel | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 20 | Duct heat recovery – electric | 5.6.1.1.20 | 5 | 0 | SHAC – Duct heat recovery – electric | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 21 | Cables | 5.6.1.1.21 | 5 | 0 | SHAC – Cables | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 22 | Instrumentation and controls | 5.6.1.1.22 | 5 | 0 | SHAC – Instrumentation and controls | 5 – HVAC and Mechanical
5 |  | 6 |  | 1 |  | 1 |  | 23 | Thermal insulation | 5.6.1.1.23 | 5 | 0 | SHAC – Thermal insulation | 5 – HVAC and Mechanical
5 |  | 6 |  | 2 | Local heating | 1 | Heaters | 1 | Heat emitters | 5.6.2.1.1 | 5 | 0 | SHAC – Heat emitters | 5 – HVAC and Mechanical
5 |  | 6 |  | 2 |  | 1 |  | 2 | Chimneys and flues | 5.6.2.1.2 | 5 | 0 | SHAC – Chimneys and flues | 5 – HVAC and Mechanical
5 |  | 6 |  | 2 |  | 1 |  | 3 | Instrumentation and controls | 5.6.2.1.3 | 5 | 0 | SHAC – Instrumentation and controls | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 | Central cooling | 1 | Central cooling systems | 1 | Chilled beams | 5.6.3.1.1 | 5 | 0 | SHAC – Chilled beams | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 2 | Terminal units – fan coils | 5.6.3.1.2 | 5 | 0 | SHAC – Terminal units – fan coils | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 3 | Terminal units – VAV | 5.6.3.1.3 | 5 | 0 | SHAC – Terminal units – VAV | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 4 | Terminal units – VRV | 5.6.3.1.4 | 5 | 0 | SHAC – Terminal units – VRV | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 5 | Chillers | 5.6.3.1.5 | 5 | 0 | SHAC – Chillers | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 6 | Central refrigeration plant | 5.6.3.1.6 | 5 | 0 | SHAC – Central refrigeration plant | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 7 | Cooling towers | 5.6.3.1.7 | 5 | 0 | SHAC – Cooling towers | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 8 | Pipework systems | 5.6.3.1.8 | 5 | 0 | SHAC – Pipework systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 9 | Cold and treated water feeds | 5.6.3.1.9 | 5 | 0 | SHAC – Cold and treated water feeds | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 10 | Supplementary list (valves) | 5.6.3.1.10 | 5 | 0 | SHAC – Valves | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 11 | Supplementary list (pumps) | 5.6.3.1.11 | 5 | 0 | SHAC – Pumps | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 12 | Distribution ductwork and fittings | 5.6.3.1.12 | 5 | 0 | SHAC – Distribution ductwork and fittings | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 13 | Grilles and diffusers | 5.6.3.1.13 | 5 | 0 | SHAC – Grilles and diffusers | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 13.A | Supplementary list (fans) | 5.6.3.1.13.A | 5 | 0 | SHAC – Fans | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 14 | Air handling units | 5.6.3.1.14 | 5 | 0 | SHAC – Air handling units | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 14.A | Supplementary list (filters) | 5.6.3.1.14.A | 5 | 0 | SHAC – Filters | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 15 | Emission units | 5.6.3.1.15 | 5 | 0 | SHAC – Emission units | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 16 | Instrumentation and controls | 5.6.3.1.16 | 5 | 0 | SHAC – Instrumentation and controls | 5 – HVAC and Mechanical
5 |  | 6 |  | 3 |  | 1 |  | 17 | Thermal insulation | 5.6.3.1.17 | 5 | 0 | SHAC – Thermal insulation | 5 – HVAC and Mechanical
5 |  | 6 |  | 4 | Local cooling | 1 | Cooling units | 1 | Air conditioning units | 5.6.4.1.1 | 5 | 0 | SHAC – Air conditioning units | 5 – HVAC and Mechanical
5 |  | 6 |  | 4 |  | 1 |  | 2 | Pipe work systems | 5.6.4.1.2 | 5 | 0 | SHAC – Pipe work systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 4 |  | 1 |  | 3 | Supplementary list (valves) | 5.6.4.1.3 | 5 | 0 | SHAC – Valves | 5 – HVAC and Mechanical
5 |  | 6 |  | 4 |  | 1 |  | 4 | Ductwork system | 5.6.4.1.4 | 5 | 0 | SHAC – Ductwork system | 5 – HVAC and Mechanical
5 |  | 6 |  | 4 |  | 1 |  | 5 | Grilles and diffusers | 5.6.4.1.5 | 5 | 0 | SHAC – Grilles and diffusers | 5 – HVAC and Mechanical
5 |  | 6 |  | 4 |  | 1 |  | 5.A | Supplementary list (fans) | 5.6.4.1.5.A | 5 | 0 | SHAC – Fans | 5 – HVAC and Mechanical
5 |  | 6 |  | 4 |  | 1 |  | 6 | Instrumentation and controls | 5.6.4.1.6 | 5 | 0 | SHAC – Instrumentation and controls | 5 – HVAC and Mechanical
5 |  | 6 |  | 4 |  | 1 |  | 7 | Thermal insulation | 5.6.4.1.7 | 5 | 0 | SHAC – Thermal insulation | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 | Central heating and cooling | 1 | Combined central heating and cooling systems | 1 | Terminal units – fan coils | 5.6.5.1.1 | 5 | 0 | SHAC – Terminal units – fan coils | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 2 | Terminal units – VAV | 5.6.5.1.2 | 5 | 0 | SHAC – Terminal units – VAV | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 3 | Reverse cycle heat pump systems | 5.6.5.1.3 | 5 | 0 | SHAC – Reverse cycle heat pump systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 4 | Chillers | 5.6.5.1.4 | 5 | 0 | SHAC – Chillers | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 5 | Pipe work systems | 5.6.5.1.5 | 5 | 0 | SHAC – Pipe work systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 6 | Supplementary list (valves) | 5.6.5.1.6 | 5 | 0 | SHAC – Valves | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 7 | Supplementary list (pumps) | 5.6.5.1.7 | 5 | 0 | SHAC – Pumps | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 8 | Ductwork systems | 5.6.5.1.8 | 5 | 0 | SHAC – Ductwork systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 9 | Grilles and diffusers | 5.6.5.1.9 | 5 | 0 | SHAC – Grilles and diffusers | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 9.A | Supplementary list (fans) | 5.6.5.1.9.A |  |  | SHAC – Fans | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 10 | Air handling units | 5.6.5.1.10 | 5 | 0 | SHAC – Air handling units | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 10.A | Supplementary list (filters) | 5.6.5.1.10.A | 5 | 0 | SHAC – AHU Filters | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 11 | Emission units | 5.6.5.1.11 | 5 | 0 | SHAC – Emission units | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 12 | Vibration isolation mountings | 5.6.5.1.12 | 5 | 0 | SHAC – Vibration isolation mountings | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 13 | Instrumentation and controls | 5.6.5.1.13 | 5 | 0 | SHAC – Instrumentation and controls | 5 – HVAC and Mechanical
5 |  | 6 |  | 5 |  | 1 |  | 14 | Thermal insulation | 5.6.5.1.14 | 5 | 0 | SHAC – Thermal insulation | 5 – HVAC and Mechanical
5 |  | 6 |  | 6 | Local heating and cooling | 1 | Local heating and cooling units | 1 | Split systems / DX systems | 5.6.6.1.1 | 5 | 0 | SHAC – Split systems / DX systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 6 |  | 1 |  | 2 | Pipework systems | 5.6.6.1.2 | 5 | 0 | SHAC – Pipework systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 6 |  | 1 |  | 3 | Supplementary list (Valves) | 5.6.6.1.3 | 5 | 0 | SHAC – Valves | 5 – HVAC and Mechanical
5 |  | 6 |  | 6 |  | 1 |  | 4 | Supplementary list (Pumps) | 5.6.6.1.4 | 5 | 0 | SHAC – Pumps | 5 – HVAC and Mechanical
5 |  | 6 |  | 6 |  | 1 |  | 5 | Ductwork system | 5.6.6.1.5 | 5 | 0 | SHAC – Ductwork system | 5 – HVAC and Mechanical
5 |  | 6 |  | 6 |  | 1 |  | 6 | Grilles and diffusers | 5.6.6.1.6 | 5 | 0 | SHAC – Grilles and diffusers | 5 – HVAC and Mechanical
5 |  | 6 |  | 6 |  | 1 |  | 6.A | Supplementary list (Fans) | 5.6.6.1.6.A | 5 | 0 | SHAC – Fans | 5 – HVAC and Mechanical
5 |  | 6 |  | 6 |  | 1 |  | 7 | Vibration isolation mountings | 5.6.6.1.7 | 5 | 0 | SHAC – Vibration isolation mountings | 5 – HVAC and Mechanical
5 |  | 6 |  | 6 |  | 1 |  | 8 | Instrumentation and controls | 5.6.6.1.8 | 5 | 0 | SHAC – Instrumentation and controls | 5 – HVAC and Mechanical
5 |  | 6 |  | 6 |  | 1 |  | 9 | Thermal insulation | 5.6.6.1.9 | 5 | 0 | SHAC – Thermal insulation | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 | Central air conditioning | 1 | Central air conditioning systems | 1 | Plenum air – heating systems | 5.6.7.1.1 | 5 | 0 | SHAC – Plenum air – heating systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 2 | Central air conditioning systems – VAV | 5.6.7.1.2 | 5 | 0 | SHAC – Central air conditioning systems – VAV | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 3 | Supplementary list (Humidifiers/dehumidifiers) | 5.6.7.1.3 | 5 | 0 | SHAC – Humidifiers | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 4 | Multi-zone air conditioning systems | 5.6.7.1.4 | 5 | 0 | SHAC – Multi-zone air conditioning systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 5 | Induction air conditioning systems | 5.6.7.1.5 | 5 | 0 | SHAC – Induction air conditioning systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 6 | Hybrid air conditioning systems | 5.6.7.1.6 | 5 | 0 | SHAC – Hybrid air conditioning systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 7 | Chillers | 5.6.7.1.7 | 5 | 0 | SHAC – Chillers | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 8 | Air handling units | 5.6.7.1.8 | 5 | 0 | SHAC – Air handling units | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 8 | Supplementary list (Filters) | 5.6.7.1.8.A | 5 | 1 | SHAVC – AHU Filters | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 9 | Terminal units / emitters | 5.6.7.1.9 | 5 | 0 | SHAC – Terminal units / emitters | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 10 | Distribution pipelines systems | 5.6.7.1.10 | 5 | 0 | SHAC – Distribution pipelines systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 11 | Supplementary list (Valves) | 5.6.7.1.11 | 5 | 0 | SHAC – Valves | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 12 | Supplementary list (Pumps) | 5.6.7.1.12 | 5 | 0 | SHAC – Pumps | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 13 | Ductwork system | 5.6.7.1.13 | 5 | 0 | SHAC – Ductwork system | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 14 | Grilles and diffusers | 5.6.7.1.14 | 5 | 0 | SHAC – Grilles and diffusers | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 14.A | Supplementary list (Fans) | 5.6.7.1.14.A | 5 | 0 | SHAC – Fans | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 15 | Instrumentation and controls | 5.6.7.1.15 | 5 | 0 | SHAC – Instrumentation and controls | 5 – HVAC and Mechanical
5 |  | 6 |  | 7 |  | 1 |  | 16 | Thermal insulation | 5.6.7.1.16 | 5 | 0 | SHAC – Thermal insulation | 5 – HVAC and Mechanical
5 |  | 6 |  | 8 | Local air conditioning | 1 | Self contained air conditioning units | 1 | Room air conditioning units | 5.6.8.1.1 | 5 | 0 | SHAC – Room air conditioning units | 5 – HVAC and Mechanical
5 |  | 6 |  | 8 |  | 1 |  | 2 | Clean room air conditioning units | 5.6.8.1.2 | 5 | 0 | SHAC – Clean room air conditioning units | 5 – HVAC and Mechanical
5 |  | 6 |  | 8 |  | 1 |  | 3 | Pipework systems | 5.6.8.1.3 | 5 | 0 | SHAC – Pipework systems | 5 – HVAC and Mechanical
5 |  | 6 |  | 8 |  | 1 |  | 4 | Supplementary list (valves) | 5.6.8.1.4 | 5 | 0 | SHAC – Valves | 5 – HVAC and Mechanical
5 |  | 6 |  | 8 |  | 1 |  | 5 | Supplementary list (pumps) | 5.6.8.1.5 | 5 | 0 | SHAC – Pumps | 5 – HVAC and Mechanical
5 |  | 6 |  | 8 |  | 1 |  | 6 | Ductwork system | 5.6.8.1.6 | 5 | 0 | SHAC – Ductwork system | 5 – HVAC and Mechanical
5 |  | 6 |  | 8 |  | 1 |  | 7 | Grilles and diffusers | 5.6.8.1.7 | 5 | 0 | SHAC – Grilles and diffusers | 5 – HVAC and Mechanical
5 |  | 6 |  | 8 |  | 1 |  | 7 | Supplementary list (fans) | 5.6.8.1.7A |  |  | SHAC – Fans | 5 – HVAC and Mechanical
5 |  | 6 |  | 8 |  | 1 |  | 8 | Vibration isolation mountings | 5.6.8.1.8 | 5 | 0 | SHAC – Vibration isolation mountings | 5 – HVAC and Mechanical
5 |  | 6 |  | 8 |  | 1 |  | 9 | Instrumentation and controls | 5.6.8.1.9 | 5 | 0 | SHAC – Instrumentation and controls | 5 – HVAC and Mechanical
5 |  | 6 |  | 8 |  | 1 |  | 10 | Thermal insulation | 5.6.8.1.10 | 5 | 0 | SHAC – Thermal insulation | 5 – HVAC and Mechanical
5 |  | 6 |  | 8 |  | 1 |  | 11 | Air curtains | 5.6.8.1.11 | 5 | 0 | SHAC – Air curtains | 5 – HVAC and Mechanical
5 |  | 7 | Ventilation systems (VS) | 1 | Central ventilation | 1 | Central ventilation systems | 1 | Fans | 5.7.1.1.1 | 5 | 0 | VS – Fans | 5 – HVAC and Mechanical
5 |  | 7 |  | 1 |  | 1 |  | 2 | Air supply and extract | 5.7.1.1.2 | 5 | 0 | VS – Air supply and extract | 5 – HVAC and Mechanical
5 |  | 7 |  | 1 |  | 1 |  | 2.A | Supplementary list (fans) | 5.7.1.1.2.A | 5 | 0 | VS – Fans | 5 – HVAC and Mechanical
5 |  | 7 |  | 1 |  | 1 |  | 3 | Extract units/terminal units | 5.7.1.1.3 | 5 | 0 | VS – Extract units/terminal units | 5 – HVAC and Mechanical
5 |  | 7 |  | 1 |  | 1 |  | 4 | Fan units | 5.7.1.1.4 | 5 | 0 | VS – Fan units | 5 – HVAC and Mechanical
5 |  | 7 |  | 1 |  | 1 |  | 5 | Ductwork systems | 5.7.1.1.5 | 5 | 0 | VS – Ductwork systems | 5 – HVAC and Mechanical
5 |  | 7 |  | 1 |  | 1 |  | 6 | Grilles and diffusers | 5.7.1.1.6 | 5 | 0 | VS – Grilles and diffusers | 5 – HVAC and Mechanical
5 |  | 7 |  | 1 |  | 1 |  | 7 | Distribution pipelines system | 5.7.1.1.7 | 5 | 0 | VS – Distribution pipelines system | 5 – HVAC and Mechanical
5 |  | 7 |  | 1 |  | 1 |  | 8 | Supplementary list (valves) | 5.7.1.1.8 | 5 | 0 | VS – Valves | 5 – HVAC and Mechanical
5 |  | 7 |  | 1 |  | 1 |  | 9 | Supplementary list (pumps) | 5.7.1.1.9 | 5 | 0 | VS – Pumps | 5 – HVAC and Mechanical
5 |  | 7 |  | 1 |  | 1 |  | 10 | Vibration isolation mountings | 5.7.1.1.10 | 5 | 0 | VS – Vibration isolation mountings | 5 – HVAC and Mechanical
5 |  | 7 |  | 1 |  | 1 |  | 11 | Instrumentation and controls | 5.7.1.1.11 | 5 | 0 | VS – Instrumentation and controls | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 | Local and special ventilation | 1 | Toilets/bathroom ventilation units | 1 | Toilet extract system | 5.7.2.1.1 | 5 | 0 | VS – Toilet extract system | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 1 |  | 1.A | Supplementary list (fans) | 5.7.2.1.1.A | 5 | 0 | VS – Fans | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 2 | Kitchen ventilation units | 2 | Kitchen ventilation units | 5.7.2.2.2 | 5 | 0 | VS – Kitchen ventilation units | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 3 | Safety cabinet and fume cupboards | 3 | Safety cabinet and fume cupboards | 5.7.2.3.3 | 5 | 0 | VS – Safety cabinet and fume cupboards | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 4 | Fume extracts | 4 | Fume extracts | 5.7.2.4.4 | 5 | 0 | VS – Fume extracts | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 5 | Dust collection units | 5 | Dust collection units | 5.7.2.5.5 | 5 | 0 | VS – Dust collection units | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 6 | Anaesthetic gas extracts | 6 | Anaesthetic gas extracts | 5.7.2.6.6 | 5 | 0 | VS – Anaesthetic gas extracts | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 7 | Cyclone systems | 7 | Cyclone systems | 5.7.2.7.7 | 5 | 0 | VS – Cyclone systems | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 8 | Unit extract fans | 8 | Unit extract fans | 5.7.2.8.8 | 5 | 0 | VS – Unit extract fans | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 9 | Rotating ventilators | 9 | Rotating ventilators | 5.7.2.9.9 | 5 | 0 | VS – Rotating ventilators | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 9 |  | 9.A | Supplementary list (fans) | 5.7.2.9.9.A | 5 | 0 | VS – Fans | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 10 | Roof-mounted ventilation | 10 | Roof-mounted ventilation units | 5.7.2.10.10 | 5 | 0 | VS – Roof-mounted ventilation units | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 11 | Car parking ventilation | 11 | Car parking ventilation | 5.7.2.11.11 | 5 | 0 | VS – Car parking ventilation | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 11 |  | 11.A | Supplementary list (fans) | 5.7.2.11.11.A | 5 | 0 | VS – Fans | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 12 | Other local and special ventilation units | 12 | Ductwork system | 5.7.2.12.12 | 5 | 0 | VS – Ductwork system | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 12 |  | 13 | Grilles and diffusers | 5.7.2.12.13 | 5 | 0 | VS – Grilles and diffusers | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 12 |  | 13.A | Supplementary list (fans) | 5.7.2.12.13.A | 5 | 0 | VS – Fans | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 12 |  | 14 | Vibration isolation mountings | 5.7.2.12.14 | 5 | 0 | VS – Vibration isolation mountings | 5 – HVAC and Mechanical
5 |  | 7 |  | 2 |  | 12 |  | 15 | Instrumentation and controls | 5.7.2.12.15 | 5 | 0 | VS – Instrumentation and controls | 5 – HVAC and Mechanical
5 |  | 7 |  | 3 | Smoke extract/control | 1 | Smoke extract/control systems | 1 | Smoke extract | 5.7.3.1.1 | 5 | 0 | VS – Smoke extract | 10 – Safety Systems
5 |  | 7 |  | 3 |  | 1 |  | 2 | Automatic smoke compartmentalisation | 5.7.3.1.2 | 5 | 0 | VS – Automatic smoke compartmentalisation | 10 – Safety Systems
5 |  | 7 |  | 3 |  | 1 |  | 3 | Supplementary list (fans) | 5.7.3.1.3 | 5 | 0 | VS – Fans | 10 – Safety Systems
5 |  | 7 |  | 3 |  | 1 |  | 4 | Ductwork systems | 5.7.3.1.4 | 5 | 0 | VS – Ductwork systems | 10 – Safety Systems
5 |  | 7 |  | 3 |  | 1 |  | 5 | Grilles and diffusers | 5.7.3.1.5 | 5 | 0 | VS – Grilles and diffusers | 10 – Safety Systems
5 |  | 7 |  | 3 |  | 1 |  | 6 | Vibration isolation mountings | 5.7.3.1.6 | 5 | 0 | VS – Vibration isolation mountings | 10 – Safety Systems
5 |  | 7 |  | 3 |  | 1 |  | 7 | Instrumentation and controls | 5.7.3.1.7 | 5 | 0 | VS – Instrumentation and controls | 10 – Safety Systems
5 |  | 8 | Electrical installations (EI) | 1 | Electrical mains and sub mains distribution | 1 | Electrical mains and sub mains LV distribution | 1 | LV distribution | 5.8.1.1.1 | 5 | 0 | EI – LV distribution | 6 – Electrical
5 |  | 8 |  | 1 |  | 1 |  | 2 | HV switch gear | 5.8.1.1.2 | 5 | 0 | EI – HV switch gear | 6 – Electrical
5 |  | 8 |  | 1 |  | 1 |  | 3 | LV switchgear and distribution boards | 5.8.1.1.3 | 5 | 0 | EI – LV switchgear and distribution boards | 6 – Electrical
5 |  | 8 |  | 1 |  | 1 |  | 4 | HV and LV cables and wiring | 5.8.1.1.4 | 5 | 0 | EI – HV and LV cables and wiring | 6 – Electrical
5 |  | 8 |  | 1 |  | 1 |  | 5 | Conduits and cable trunking | 5.8.1.1.5 | 5 | 0 | EI – Conduits and cable trunking | 6 – Electrical
5 |  | 8 |  | 1 |  | 1 |  | 6 | Busbar trunking | 5.8.1.1.6 | 5 | 0 | EI – Busbar trunking | 6 – Electrical
5 |  | 8 |  | 1 |  | 1 |  | 7 | Earthing and bonding | 5.8.1.1.7 | 5 | 0 | EI – Earthing and bonding | 6 – Electrical
5 |  | 8 |  | 1 |  | 1 |  | 8 | Transformers | 5.8.1.1.8 | 5 | 0 | EI – Transformers | 6 – Electrical
5 |  | 8 |  | 1 |  | 1 |  | 9 | Fuse pillars, base units, etc. | 5.8.1.1.9 | 5 | 0 | EI – Fuse pillars, base units, etc. | 6 – Electrical
5 |  | 8 |  | 1 |  | 1 |  | 10 | Surge protection | 5.8.1.1.10 | 5 | 0 | EI – Surge protection | 6 – Electrical
5 |  | 8 |  | 1 |  | 1 |  | 11 | Electricity monitoring system | 5.8.1.1.11 | 5 | 0 | EI – Electricity monitoring system | 6 – Electrical
5 |  | 8 |  | 2 | Power installations | 1 | Power installations | 1 | General LV power installations | 5.8.2.1.1 | 5 | 0 | EI – General LV power installations | 6 – Electrical
5 |  | 8 |  | 2 |  | 1 |  | 2 | Extra LV supply installations | 5.8.2.1.2 | 5 | 0 | EI – Extra LV supply installations | 6 – Electrical
5 |  | 8 |  | 2 |  | 1 |  | 3 | DC installations | 5.8.2.1.3 | 5 | 0 | EI – DC installations | 6 – Electrical
5 |  | 8 |  | 2 |  | 1 |  | 4 | Distribution boards (PDUs) | 5.8.2.1.4 | 5 | 0 | EI – Distribution boards (PDUs) | 6 – Electrical
5 |  | 8 |  | 2 |  | 1 |  | 5 | UPS system | 5.8.2.1.5 | 5 | 0 | EI – UPS system | 6 – Electrical
5 |  | 8 |  | 2 |  | 1 |  | 6 | Cables and wiring | 5.8.2.1.6 | 5 | 0 | EI – Cables and wiring | 6 – Electrical
5 |  | 8 |  | 2 |  | 1 |  | 7 | Conduits and cable trunking | 5.8.2.1.7 | 5 | 0 | EI – Conduits and cable trunking | 6 – Electrical
5 |  | 8 |  | 2 |  | 1 |  | 8 | Earthing and bonding | 5.8.2.1.8 | 5 | 0 | EI – Earthing and bonding | 6 – Electrical
5 |  | 8 |  | 2 |  | 1 |  | 9 | Socket outlets | 5.8.2.1.9 | 5 | 0 | EI – Socket outlets | 6 – Electrical
5 |  | 8 |  | 2 |  | 1 |  | 11 | Specialist power installations | 5.8.2.1.11 | 5 | 0 | EI – Specialist power installations | 6 – Electrical
5 |  | 8 |  | 2 |  | 2 | Testing of installations | 14.A | Portable Appliance Testing (PAT) | 5.8.2.2.14.A | 5 | 0 | EI – PAT Testing | 6 – Electrical
5 |  | 8 |  | 2 |  | 2 |  | 14.B | Fixed electrical wire testing | 5.8.2.2.14.B | 5 | 0 | EI – Fixed electrical wire testing | 6 – Electrical
5 |  | 8 |  | 3 | Lighting installations | 1 | Lighting installations | 1 | Light fittings – general | 5.8.3.1.1 | 5 | 0 | EI – Light fittings – general | 6 – Electrical
5 |  | 8 |  | 3 |  | 1 |  | 2 | Emergency lighting | 5.8.3.1.2 | 5 | 0 | EI – Emergency lighting | 6 – Electrical
5 |  | 8 |  | 3 |  | 1 |  | 3 | External lighting | 5.8.3.1.3 | 5 | 0 | EI – External lighting | 6 – Electrical
5 |  | 8 |  | 3 |  | 1 |  | 4 | LV switchgear and distribution boards | 5.8.3.1.4 | 5 | 0 | EI – LV switchgear and distribution boards | 6 – Electrical
5 |  | 8 |  | 3 |  | 1 |  | 5 | Cables and wiring | 5.8.3.1.5 | 5 | 0 | EI – Cables and wiring | 6 – Electrical
5 |  | 8 |  | 3 |  | 1 |  | 6 | Conduits and cable trunking | 5.8.3.1.6 | 5 | 0 | EI – Conduits and cable trunking | 6 – Electrical
5 |  | 8 |  | 3 |  | 1 |  | 7 | Earthing and bonding | 5.8.3.1.7 | 5 | 0 | EI – Earthing and bonding | 6 – Electrical
5 |  | 8 |  | 3 |  | 1 |  | 8 | Fittings to lighting points | 5.8.3.1.8 | 5 | 0 | EI – Fittings to lighting points | 6 – Electrical
5 |  | 8 |  | 3 |  | 1 |  | 9 | Lighting switches | 5.8.3.1.9 | 5 | 0 | EI – Lighting switches | 6 – Electrical
5 |  | 8 |  | 3 |  | 1 |  | 10 | Luminaries/lamps | 5.8.3.1.10 | 5 | 0 | EI – Luminaries/lamps | 6 – Electrical
5 |  | 8 |  | 3 |  | 1 |  | 11 | Lighting control equipment | 5.8.3.1.11 | 5 | 0 | EI – Lighting control equipment | 6 – Electrical
5 |  | 8 |  | 4 | Specialist lighting installations | 1 | Specialist lighting installations | 1 | Illuminated display units | 5.8.4.1.1 | 5 | 0 | EI – Illuminated display units | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 2 | Studio lighting | 5.8.4.1.2 | 5 | 0 | EI – Studio lighting | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 3 | Auditorium lighting | 5.8.4.1.3 | 5 | 0 | EI – Auditorium lighting | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 4 | Arena lighting | 5.8.4.1.4 | 5 | 0 | EI – Arena lighting | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 5 | Operating theatre lighting | 5.8.4.1.5 | 5 | 0 | EI – Operating theatre lighting | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 6 | LV switchgear and distribution boards | 5.8.4.1.6 | 5 | 0 | EI – LV switchgear and distribution boards | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 7 | Cables and wiring | 5.8.4.1.7 | 5 | 0 | EI – Cables and wiring | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 8 | Conduits and cable trunking | 5.8.4.1.8 | 5 | 0 | EI – Conduits and cable trunking | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 9 | Earthing and bonding | 5.8.4.1.9 | 5 | 0 | EI – Earthing and bonding | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 10 | Fittings to lighting points | 5.8.4.1.10 | 5 | 0 | EI – Fittings to lighting points | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 11 | Switches | 5.8.4.1.11 | 5 | 0 | EI – Switches | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 12 | Luminaries/lamps | 5.8.4.1.12 | 5 | 0 | EI – Luminaries/lamps | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 13 | Lighting gantries | 5.8.4.1.13 | 5 | 0 | EI – Lighting gantries | 6 – Electrical
5 |  | 8 |  | 4 |  | 1 |  | 14 | Lighting control equipment | 5.8.4.1.14 | 5 | 0 | EI – Lighting control equipment | 6 – Electrical
5 |  | 8 |  | 5 | Local electricity generation systems | 1 | Electricity generation systems | 1 | Standby generator | 5.8.5.1.1 | 5 | 0 | EI – Standby generator | 6 – Electrical
5 |  | 8 |  | 5 |  | 1 |  | 2 | Ancillary cables and wiring | 5.8.5.1.2 | 5 | 0 | EI – Ancillary cables and wiring | 6 – Electrical
5 |  | 8 |  | 5 |  | 4 | Wind turbines | 1 | Wind turbines | 5.8.5.4.1 | 5 | 0 | EI – Wind turbines | 13 – Specialist
5 |  | 8 |  | 5 |  | 5 | Photovoltaic devices | 2 | Photovoltaic devices | 5.8.5.5.2 | 5 | 0 | EI – Photovoltaic devices | 13 – Specialist
5 |  | 8 |  | 5 |  | 5 |  | 3 | Solar collectors | 5.8.5.5.3 | 5 | 0 | EI – Solar collectors | 13 – Specialist
5 |  | 8 |  | 5 |  | 6 | Other transformation devices | 4 | Other transformation devices | 5.8.5.6.4 | 5 | 0 | EI – Other transformation devices | 13 – Specialist
5 |  | 8 |  | 5 |  | 4 |  | 5 | Generators | 5.8.5.4.5 | 5 | 0 | EI – Generators | 13 – Specialist
5 |  | 8 |  | 5 |  | 4 |  | 6 | Ancillary cables and wiring, etc. | 5.8.5.4.6 | 5 | 0 | EI – Ancillary cables and wiring, etc. | 13 – Specialist
5 |  | 8 |  | 6 | Earthling and bonding systems | 1 | Earthling and bonding systems | 1 | Earthing and bonding cables | 5.8.6.1.1 | 5 | 0 | EI – Earthing and bonding cables | 6 – Electrical
5 |  | 8 |  | 6 |  | 1 |  | 2 | Protective conductor earthing | 5.8.6.1.2 | 5 | 0 | EI – Protective conductor earthing | 6 – Electrical
5 |  | 8 |  | 6 |  | 1 |  | 3.A | Hazardous areas (electrics) earthing | 5.8.6.1.3.A | 5 | 0 | EI – Hazardous areas (electrics) earthing | 6 – Electrical
5 |  | 9 | Fuel installations | 1 | Fuel storage | 1 | Fuel storage | 1 | Fuel systems – oil, petrol, diesel and liquified petroleum gas, biomass and others | 5.9.1.1.1 | 5 | 0 | Fuel systems – oil, petrol, diesel and liquified petroleum gas, biomass and others | 12 – Fuel Systems
5 |  | 9 |  | 1 |  | 1 |  | 2 | Storage tanks and vessels | 5.9.1.1.2 | 5 | 0 | Fuel – Storage tanks and vessels | 12 – Fuel Systems
5 |  | 9 |  | 1 |  | 1 |  | 5 | Thermal insulation | 5.9.1.1.5 | 5 | 0 | Fuel – Thermal insulation | 12 – Fuel Systems
5 |  | 9 |  | 2 | Fuel distribution systems | 1 | Piped distribution systems | 1 | Fuel systems – oil, petrol, diesel and liquified petroleum gas, biomass and others | 5.9.2.1.1 | 5 | 0 | Fuel systems – oil, petrol, diesel and liquified petroleum gas, biomass and others | 12 – Fuel Systems
5 |  | 9 |  | 2 |  | 1 |  | 2 | Pipework systems | 5.9.2.1.2 | 5 | 0 | Fuel – Pipework systems | 12 – Fuel Systems
5 |  | 9 |  | 2 |  | 1 |  | 3 | Supplementary list (pumps) | 5.9.2.1.3 | 5 | 0 | Fuel – Pumps | 12 – Fuel Systems
5 |  | 9 |  | 2 |  | 1 |  | 3.A | Supplementary list (valves) | 5.9.2.1.3.A | 5 | 0 | Flue – Valves | 12 – Fuel Systems
5 |  | 9 |  | 2 |  | 1 |  | 4 | Bracketry | 5.9.2.1.4 | 5 | 0 | Flue – Bracketry | 12 – Fuel Systems
5 |  | 9 |  | 2 |  | 1 |  | 5 | Gas distribution components | 5.9.2.1.5 | 5 | 0 | Fuel – Gas distribution components | 12 – Fuel Systems
5 |  | 9 |  | 2 |  | 1 |  | 6 | Terminal control equipment | 5.9.2.1.6 | 5 | 0 | Fuel – Terminal control equipment | 12 – Fuel Systems
5 |  | 9 |  | 2 |  | 1 |  | 7 | Thermal insulation | 5.9.2.1.7 | 5 | 0 | Fuel – Thermal insulation | 12 – Fuel Systems
5 |  | 9 |  | 2 |  | 1 |  | 8 | Monitoring equipment | 5.9.2.1.8 | 5 | 0 | Fuel – Monitoring equipment | 12 – Fuel Systems
5 |  | 10 | Lift and conveyor installations | 1 | Lifts | 1 | Passenger lifts | 1 | Complete lift installations (state type) | 5.10.1.1.1 | 5 | 0 | Lifts – Complete lift installations | 9 – Lifts and Conveyors
5 |  | 10 |  | 1 |  | 1 |  | 2 | Fire fighting lifts | 5.10.1.1.2 | 5 | 0 | Lifts – Fire fighting | 9 – Lifts and Conveyors
5 |  | 10 |  | 1 |  | 2 | Wall climbing lifts | 3 | Wall climbing lifts | 5.10.1.2.3 | 5 | 0 | Lifts – Wall climbing | 9 – Lifts and Conveyors
5 |  | 10 |  | 1 |  | 2 |  | 4 | Gantries, trolley and blocks, etc. | 5.10.1.2.4 | 5 | 0 | Lifts – Gantries, trolley and blocks | 9 – Lifts and Conveyors
5 |  | 10 |  | 1 |  | 2 |  | 5 | Lift controls and electrical works | 5.10.1.2.5 | 5 | 0 | Lifts controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 1 |  | 3 | Goods lift | 1 | Complete lift installations (state type) | 5.10.1.3.1 | 5 | 0 | Lifts – Complete lift installations | 9 – Lifts and Conveyors
5 |  | 10 |  | 1 | Lifts | 6 | Enclosed hoists | 1 | Hoists, kitchen service and dumb waiters | 5.10.1.6.1 | 5 | 0 | Hoists, kitchen service and dumb waiters | 9 – Lifts and Conveyors
5 |  | 10 |  | 1 |  | 6 |  | 2 | Complete hoist installations | 5.10.1.6.2 | 5 | 0 | Complete hoist installations | 9 – Lifts and Conveyors
5 |  | 10 |  | 1 |  | 6 |  | 3 | Supplementary list (controllers and sensors) | 5.10.1.6.3 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 2 | Escalators | 1 | Escalators | 1 | Escalators | 5.10.2.1.1 | 5 | 0 | Escalators | 9 – Lifts and Conveyors
5 |  | 10 |  | 2 |  | 1 |  | 2 | Ancillary components | 5.10.2.1.2 | 5 | 0 | Ancillary components | 9 – Lifts and Conveyors
5 |  | 10 |  | 2 |  | 1 |  | 3 | Supplementary list (controllers and sensors) | 5.10.2.1.3 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 3 | Moving pavements | 1 | Moving pavements | 1 | Moving platforms | 5.10.3.1.1 | 5 | 0 | Moving platforms | 9 – Lifts and Conveyors
5 |  | 10 |  | 3 |  | 1 |  | 2 | Travelators | 5.10.3.1.2 | 5 | 0 | Travelators | 9 – Lifts and Conveyors
5 |  | 10 |  | 3 |  | 1 |  | 3 | Stair lifts | 5.10.3.1.3 | 5 | 0 | Stair lifts | 9 – Lifts and Conveyors
5 |  | 10 |  | 3 |  | 1 |  | 4 | Supplementary list (controllers and sensors) | 5.10.3.1.4 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 4 | Powered stair lifts | 1 | Powered stair lifts | 1 | Complete powered stair life installations | 5.10.4.1.1 | 5 | 0 | Complete powered stair life installations | 9 – Lifts and Conveyors
5 |  | 10 |  | 4 |  | 1 |  | 2 | Supplementary list (controllers and sensors) | 5.10.4.1.2 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 5 | Conveyors | 1 | People conveyors | 1 | Complete conveyor systems | 5.10.5.1.1 | 5 | 0 | Complete conveyor systems | 9 – Lifts and Conveyors
5 |  | 10 |  | 5 |  | 1 |  | 2 | Specialist system (baggage handling) | 5.10.5.1.2 | 5 | 0 | Specialist system (baggage handling) | 9 – Lifts and Conveyors
5 |  | 10 |  | 5 |  | 1 |  | 3 | Supplementary list (controllers and sensors) | 5.10.5.1.3 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 5 |  | 2 | Goods conveyor | 1 | Complete conveyor systems | 5.10.5.2.1 | 5 | 0 | Complete conveyor systems | 9 – Lifts and Conveyors
5 |  | 10 |  | 5 |  | 2 |  | 3 | Supplementary list (controllers and sensors) | 5.10.5.2.3 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 6 | Dock levellers and scissor lifts | 1 | Dock levellers | 1 | Dock levellers, including canopy | 5.10.6.1.1 | 5 | 0 | Dock levellers, including canopy | 9 – Lifts and Conveyors
5 |  | 10 |  | 6 |  | 1 |  | 3 | Supplementary list (controllers and sensors) | 5.10.6.1.3 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 6 |  | 2 | Scissor lifts | 2 | Scissor lifts | 5.10.6.2.2 | 5 | 0 | Scissor lifts | 9 – Lifts and Conveyors
5 |  | 10 |  | 6 |  | 2 |  | 3 | Supplementary list (controllers and sensors) | 5.10.6.2.3 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 7 | Cranes and unenclosed hoists | 1 | Cranes | 1 | Cranes | 5.10.7.1.1 | 5 | 0 | Cranes | 9 – Lifts and Conveyors
5 |  | 10 |  | 7 |  | 1 |  | 4 | Supplementary list (controllers and sensors) | 5.10.7.1.4 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 7 |  | 2 | Travelling cranes | 2 | Travelling cranes | 5.10.7.2.2 | 5 | 0 | Travelling cranes | 9 – Lifts and Conveyors
5 |  | 10 |  | 7 |  | 2 |  | 4 | Supplementary list (controllers and sensors) | 5.10.7.2.4 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 7 |  | 3 | Unenclosed hoists | 3 | Unenclosed hoists and other lifting systems | 5.10.7.3.3 | 5 | 0 | Unenclosed hoists and other lifting systems | 9 – Lifts and Conveyors
5 |  | 10 |  | 7 |  | 3 |  | 4 | Supplementary list (controllers and sensors) | 5.10.7.3.4 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 8 | Car lifts, car stacking systems, turntables, etc. | 1 | Car lifts | 1 | Car lifts | 5.10.8.1.1 | 5 | 0 | Car lifts | 9 – Lifts and Conveyors
5 |  | 10 |  | 8 |  | 1 |  | 3 | Supplementary list (controllers and sensors) | 5.10.8.1.3 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 8 |  | 2 | Car stacking | 2 | Car stacking | 5.10.8.2.2 | 5 | 0 | Car stacking | 9 – Lifts and Conveyors
5 |  | 10 |  | 8 |  | 2 |  | 3 | Supplementary list (controllers and sensors) | 5.10.8.2.3 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 8 |  | 3 | Vehicle turntables | 3 | Vehicle turntables | 5.10.8.3.3 | 5 | 0 | Vehicle turntables | 9 – Lifts and Conveyors
5 |  | 10 |  | 8 |  | 3 |  | 3 | Supplementary list (controllers and sensors) | 5.10.8.3.3B | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 9 | Document handling/delivery systems | 1 | Document handling/delivery systems | 1.A | Document handling/delivery systems | 5.10.9.1.1.A | 5 | 0 | Document handling/delivery systems | 9 – Lifts and Conveyors
5 |  | 10 |  | 9 |  | 1 |  | 2 | Supplementary list (controllers and sensors) | 5.10.9.1.2 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 9 |  | 2 | Warehouse picking systems | 1.B | Warehouse picking systems | 5.10.9.2.1.B | 5 | 0 | Warehouse picking systems | 9 – Lifts and Conveyors
5 |  | 10 |  | 9 |  | 2 |  | 2 | Supplementary list (controllers and sensors) | 5.10.9.2.2 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
[6 empty] | 3 | Other systems (state type) | 1.C | Other systems (state type) | 5.10.9.3.1.C | 5 | 0 | Other systems (state type) | 9 – Lifts and Conveyors
5 |  | 10 |  | 9 |  | 3 |  | 2 | Supplementary list (controllers and sensors) | 5.10.9.3.2 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 10 |  | 10 | Other transport systems | 1 | Other lift and conveyor installations | 1 | Paternoster lifts | 5.10.10.1.1 | 5 | 0 | Lifts – Paternoster | 9 – Lifts and Conveyors
5 |  | 10 |  | 10 |  | 1 |  | 2 | Hoist for moving people with disability | 5.10.10.1.2 | 5 | 0 | Hoist for moving people with disability | 9 – Lifts and Conveyors
5 |  | 10 |  | 10 |  | 1 |  | 3 | Other transport systems | 5.10.10.1.3 | 5 | 0 | Other transport systems | 9 – Lifts and Conveyors
5 |  | 10 |  | 10 |  | 1 |  | 4 | Supplementary list (controllers and sensors) | 5.10.10.1.4 | 5 | 0 | Controls and electrical works | 9 – Lifts and Conveyors
5 |  | 11 | Fire and lightning protection | 1 | Fire fighting systems | 1 | Fire hose reels | 1 | Fire hose reels – inc. pressure booster sets | 5.11.1.1.1 | 5 | 0 | Fire hose reels – inc. pressure booster sets | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 1 |  | 4 | Distribution pipeline systems | 5.11.1.1.4 | 5 | 0 | Distribution pipeline systems | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 1 |  | 5 | Thermal insulation | 5.11.1.1.5 | 5 | 0 | Thermal insulation | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 1 |  | 6 | Control components | 5.11.1.1.6 | 5 | 0 | Control components | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 2 | Dry risers – valves. Pressure vessels, etc. | 2 | Dry risers | 5.11.1.2.2 | 5 | 0 | Dry risers | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 2 |  | 4 | Distribution pipeline systems | 5.11.1.2.4 | 5 | 0 | Distribution pipeline systems | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 2 |  | 5 | Thermal insulation | 5.11.1.2.5 | 5 | 0 | Thermal insulation | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 3 | Wet risers | 3 | Wet risers | 5.11.1.3.3 | 5 | 0 | Wet risers | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 3 |  | 4 | Distribution pipeline systems | 5.11.1.3.4 | 5 | 0 | Distribution pipeline systems | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 3 |  | 5 | Thermal insulation | 5.11.1.3.5 | 5 | 0 | Thermal insulation | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 4 | Fire and oxide protection curtains | 7 | Fire and smoke protection curtains | 5.11.1.4.7 | 5 | 0 | Fire and smoke protection curtains | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 4 |  | 6 | Control components | 5.11.1.4.6 | 5 | 0 | Control components | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 5 | Other fire fighting systems (state type) |  |  | 5.11.1.5 | 4 | 0 | Other fire fighting systems (state type) | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 5 |  | 4 | Distribution pipeline systems | 5.11.1.5.4 | 5 | 0 | Distribution pipeline systems | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 5 |  | 5 | Thermal insulation | 5.11.1.5.5 | 5 | 0 | Thermal insulation | 10 – Safety Systems
5 |  | 11 |  | 1 |  | 5 |  | 6 | Control components | 5.11.1.5.6 | 5 | 0 | Control components | 10 – Safety Systems
5 |  | 11 |  | 2 | Fire suppression systems | 1 | Sprinklers – inc. control devices and sprinkler heads | 1 | Sprinklers – inc. control devices and sprinkler heads | 5.11.2.1.1 | 5 | 0 | Sprinklers – inc. control devices and sprinkler heads | 10 – Safety Systems
5 |  | 11 |  | 2 |  | 2 | Deluge systems | 2 | Deluge systems | 5.11.2.2.2 | 5 | 0 | Deluge systems | 10 – Safety Systems
5 |  | 11 |  | 2 |  | 3 | Gas fire fighting systems | 3 | Gas fire fighting systems | 5.11.2.3.3 | 5 | 0 | Gas fire fighting systems | 10 – Safety Systems
5 |  | 11 |  | 2 |  | 4 | Foam fighting systems | 4 | Foam fighting systems | 5.11.2.4.4 | 5 | 0 | Foam fighting systems | 10 – Safety Systems
5 |  | 11 |  | 2 |  | 5 | Other fire suppression systems | 5 | Distribution pipelines system | 5.11.2.5.5 | 5 | 0 | Distribution pipelines system | 10 – Safety Systems
5 |  | 11 |  | 2 |  | 5 |  | 6 | Water tanks and cisterns for firefighting | 5.11.2.5.6 | 5 | 0 | Water tanks and cisterns for firefighting | 10 – Safety Systems
5 |  | 11 |  | 2 |  | 5 |  | 7 | Thermal insulation | 5.11.2.5.7 | 5 | 0 | Thermal insulation | 10 – Safety Systems
5 |  | 11 |  | 2 |  | 5 |  | 8 | Control components | 5.11.2.5.8 | 5 | 0 | Control components | 10 – Safety Systems
5 |  | 11 |  | 3 | Lightning protection | 1 | Lightning protection | 1 | Bonded steel frame/tape based systems | 5.11.3.1.1 | 5 | 0 | Bonded steel frame/tape based systems | 10 – Safety Systems
5 |  | 11 |  | 3 |  | 1 |  | 2 | Finials | 5.11.3.1.2 | 5 | 0 | Finials | 10 – Safety Systems
5 |  | 11 |  | 3 |  | 1 |  | 3 | Conductor tapes | 5.11.3.1.3 | 5 | 0 | Conductor tapes | 10 – Safety Systems
5 |  | 11 |  | 3 |  | 1 |  | 4 | Grounding/earthing | 5.11.3.1.4 | 5 | 0 | Grounding/earthing | 10 – Safety Systems
5 |  | 12 | Communication, security and control systems | 1 | Communication systems | 1 | Telecommunication | 1 | General communications and PA systems | 5.12.1.1.1 | 5 | 0 | General communications and PA systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 2 | Data transmission | 1 | Computer networking, modems etc. | 5.12.1.2.1 | 5 | 0 | Computer networking, modems, etc. | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 2 |  | 2 | Multiplexes data terminals | 5.12.1.2.2 | 5 | 0 | Multiplexes data terminals | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 3 | Paging and emergency | 1 | Aerials, radio and paging equipment | 5.12.1.3.1 | 5 | 0 | Aerials, radio and paging equipment | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 3 |  | 2 | Emergency call buttons, pull cords, etc. | 5.12.1.3.2 | 5 | 0 | Emergency call buttons, pull cords etc. | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 3 |  | 3 | Paging and emergency call systems | 5.12.1.3.3 | 5 | 0 | Paging and emergency call systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 3 |  | 4 | Hospital patients call points | 5.12.1.3.4 | 5 | 0 | Hospital patients call points | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 3 |  | 5 | Cell call systems | 5.12.1.3.5 | 5 | 0 | Cell call systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 3 |  | 6 | Personal receivers | 5.12.1.3.6 | 5 | 0 | Personal receivers | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 4 | Public address and conference audio | 1 | Public address system | 5.12.1.4.1 | 5 | 0 | Public address system | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 4 |  | 2 | Conference audio facilities | 5.12.1.4.2 | 5 | 0 | Conference audio facilities | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 4 |  | 3 | Induction loop systems | 5.12.1.4.3 | 5 | 0 | Induction loop systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 4 |  | 4 | Hospital radio facilities | 5.12.1.4.4 | 5 | 0 | Hospital radio facilities | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 4 |  | 5 | Background noise systems | 5.12.1.4.5 | 5 | 0 | Background noise systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 4 |  | 6 | Microphones, amplifiers and speakers | 5.12.1.4.6 | 5 | 0 | Microphones, amplifiers and speakers | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 4 |  | 7 | Indicator boards | 5.12.1.4.7 | 5 | 0 | Indicator boards | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 5 | Radio systems | 1 | Cable and satellite systems | 5.12.1.5.1 | 5 | 0 | Cable and satellite systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 5 |  | 2 | Receivers and other ancillaries | 5.12.1.5.2 | 5 | 0 | Receivers and other ancillaries | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 6 | Projection systems | 1 | Cinematographic equipment | 5.12.1.6.1 | 5 | 0 | Cinematographic equipment | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 6 |  | 2 | Fixed and portable projectors | 5.12.1.6.2 | 5 | 0 | Fixed and portable projectors | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 6 |  | 3 | Screens and back projection equipment | 5.12.1.6.3 | 5 | 0 | Screens and back projection equipment | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 6 |  | 4 | Sound equipment | 5.12.1.6.4 | 5 | 0 | Sound equipment | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 7 | Fire detection and alarm systems |  |  | 5.12.1.7 | 4 | 0 | Fire detection and alarm systems | 10 – Safety Systems
5 |  | 12 |  | 1 |  | 7 |  | 1 | Carbon dioxide sensor | 5.12.1.7.1 | 5 | 0 | Carbon dioxide sensor | 10 – Safety Systems
5 |  | 12 |  | 1 |  | 7 |  | 2 | Heat detector | 5.12.1.7.2 | 5 | 0 | Heat detector | 10 – Safety Systems
5 |  | 12 |  | 1 |  | 7 |  | 7 | Call points automatic detection equipment | 5.12.1.7.7 | 5 | 0 | Call points automatic detection equipment | 10 – Safety Systems
5 |  | 12 |  | 1 |  | 8 | Smoke detection and alarm systems | 1 | Smoke detectors | 5.12.1.8.1 | 5 | 0 | Smoke detectors | 10 – Safety Systems
5 |  | 12 |  | 1 |  | 8 |  | 2 | IT smoke detection system | 5.12.1.8.2 | 5 | 0 | IT smoke detection system | 10 – Safety Systems
5 |  | 12 |  | 1 |  | 8 |  | 3 | Gas detector sensors | 5.12.1.8.3 | 5 | 0 | Gas detector sensors | 10 – Safety Systems
5 |  | 12 |  | 1 |  | 8 |  | 4 | Batteries – lead acid – unsealed | 5.12.1.8.4 | 5 | 0 | Batteries – lead acid – unsealed | 10 – Safety Systems
5 |  | 12 |  | 1 |  | 8 |  | 5 | Batteries – sealed | 5.12.1.8.5 | 5 | 0 | Batteries – sealed | 10 – Safety Systems
5 |  | 12 |  | 1 |  | 8 |  | 6 | Battery charging equipment | 5.12.1.8.6 | 5 | 0 | Battery charging equipment | 10 – Safety Systems
5 |  | 12 |  | 1 |  | 9 | Liquid detection systems |  |  | 5.12.1.9 | 4 | 0 | Liquid detection systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 10 | Clocks, card clocks and flexitime installations |  |  | 5.12.1.10 | 4 | 0 | Clocks, card clocks and flexitime installations | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 11 | Door entry systems |  |  | 5.12.1.11 | 4 | 0 | Door entry systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 12 | Radio and televisions |  |  | 5.12.1.12 | 4 | 0 | Radio and televisions | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 13 | Television systems |  |  | 5.12.1.13 | 4 | 0 | Television systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 14 | TV monitors |  |  | 5.12.1.14 | 4 | 0 | TV monitors | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 15 | Pneumatic message systems |  |  | 5.12.1.15 | 4 | 0 | Pneumatic message systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 1 |  | 16 | Other comms systems |  |  | 5.12.1.16 | 4 | 0 | Other comms systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 2 | Security systems | 1 | Surveillance equipment | 1 | Surveillance systems | 5.12.2.1.1 | 5 | 0 | Surveillance systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 2 |  | 2 | Security detection | 2 | Security detection | 5.12.2.2.2 | 5 | 0 | Security detection | 11 – Communication, Controls and Security
5 |  | 12 |  | 2 |  | 3 | Security alarm equipment | 3 | Security alarm equipment | 5.12.2.3.3 | 5 | 0 | Security alarm equipment | 11 – Communication, Controls and Security
5 |  | 12 |  | 2 |  | 4 | Access control systems | 4 | Access control systems | 5.12.2.4.4 | 5 | 0 | Access control systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 2 |  | 5 | Burglar and security alarms | 5 | Burglar and security alarms | 5.12.2.5.5 | 5 | 0 | Burglar and security alarms | 11 – Communication, Controls and Security
5 |  | 12 |  | 2 |  | 6 | Door entry systems | 6 | Door entry systems (audio and visual) | 5.12.2.6.6 | 5 | 0 | Door entry systems (audio and visual) | 11 – Communication, Controls and Security
5 |  | 12 |  | 2 |  | 7 | Security lights and lighting systems | 7 | Security lights and lighting systems | 5.12.2.7.7 | 5 | 0 | Security lights and lighting systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 2 |  | 8 | Other security systems | 8 | Other security systems | 5.12.2.8.8 | 5 | 0 | Other security systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 3 | Central control/building management systems | 1 | Central control/building management systems | 1 | Control panels for mechanical and electrical equipment | 5.12.3.1.1 | 5 | 0 | Control panels for mechanical and electrical equipment | 11 – Communication, Controls and Security
5 |  | 12 |  | 3 |  | 1 |  | 2 | BMS and operating station systems | 5.12.3.1.2 | 5 | 0 | BMS and operating station systems | 11 – Communication, Controls and Security
5 |  | 12 |  | 3 |  | 1 |  | 4 | Controlling terminal units and switches | 5.12.3.1.4 | 5 | 0 | Controlling terminal units and switches | 11 – Communication, Controls and Security
5 |  | 12 |  | 3 |  | 1 |  | 5 | Control cabling and containment | 5.12.3.1.5 | 5 | 0 | Control cabling and containment | 11 – Communication, Controls and Security
5 |  | 12 |  | 3 |  | 1 |  | 6 | Compressed air and vacuum operating controls | 5.12.3.1.6 | 5 | 0 | Compressed air and vacuum operating controls | 11 – Communication, Controls and Security
5 |  | 12 |  | 3 |  | 2 | Computer aided facilities management (CAFM) system | 3 | CAFM systems | 5.12.3.2.3 | 5 | 0 | CAFM systems | 11 – Communication, Controls and Security
5 |  | 13 | Specialist installations | 1 | Specialist piped supply systems | 1 | Medical and laboratory gas supply systems | 1 | Medical and laboratory gas supply systems – including ancillary components (e.g. storage vessels, controls and alarms, etc.) | 5.13.1.1.1 | 5 | 0 | Medical and laboratory gas supply systems – including ancillary components (e.g. storage vessels, controls and alarms, etc.) | 13 – Specialist
5 |  | 13 |  | 1 |  | 2 | Centralised vacuum cleaning systems | 2 | Centralised vacuum cleaning systems – including vacuum pumps, blowers, etc. | 5.13.1.2.2 | 5 | 0 | Centralised vacuum cleaning systems – including vacuum pumps, blowers, etc. | 13 – Specialist
5 |  | 13 |  | 1 |  | 3 | Treated water systems | 3 | Treated water systems – including ancillary components (e.g. raw sewage storage tanks, chemical storage and vessels, etc.) | 5.13.1.3.3 | 5 | 0 | Treated water systems – including ancillary components (e.g. raw sewage storage tanks, chemical storage and vessels) | 13 – Specialist
5 |  | 13 |  | 1 |  | 4 | Swimming pools water treatment systems | 4 | Swimming pools water treatment systems – including ancillary components (e.g. filters vessels, chemical storage vessels, chemical dosing equipment storage vessels, etc.) | 5.13.1.4.4 | 5 | 0 | Swimming pools water treatment systems – including ancillary components (e.g. filters vessels, chemical storage vessels, chemical dosing equipment storage vessels, etc.) | 13 – Specialist
5 |  | 13 |  | 1 |  | 5 | Compressed air systems | 5 | Compressed air systems – including compressors and other ancillary components | 5.13.1.5.5 | 5 | 0 | Compressed air systems – including compressors and other ancillary components | 13 – Specialist
5 |  | 13 |  | 1 |  | 6 | Vacuum installations | 6 | Vacuum installations – including ancillary components | 5.13.1.6.6 | 5 | 0 | Vacuum installations – including ancillary components | 13 – Specialist
5 |  | 13 |  | 1 |  | 7 | Other specialist piped supply systems | 7 | Other specialist piped supply systems | 5.13.1.7.7 | 5 | 0 | Other specialist piped supply systems | 13 – Specialist
5 |  | 13 |  | 1 |  | 7 |  | 8 | Pipework systems | 5.13.1.7.8 | 5 | 0 | Pipework systems | 13 – Specialist
5 |  | 13 |  | 1 |  | 7 |  | 9 | Air duct lines and ancillaries and fittings | 5.13.1.7.9 | 5 | 0 | Air duct lines and ancillaries and fittings | 13 – Specialist
5 |  | 13 |  | 1 |  | 7 |  | 10 | Thermal insulation | 5.13.1.7.10 | 5 | 0 | Thermal insulation | 13 – Specialist
5 |  | 13 |  | 1 |  | 7 |  | 11 | Silencers and acoustic treatment | 5.13.1.7.11 | 5 | 0 | Silencers and acoustic treatment | 13 – Specialist
5 |  | 13 |  | 1 |  | 7 |  | 12 | Control components | 5.13.1.7.12 | 5 | 0 | Control components | 13 – Specialist
5 |  | 13 |  | 2 | Specialist refrigeration systems | 1 | Cold rooms | 1 | Cold rooms | 5.13.2.1.1 | 5 | 0 | Cold rooms | 13 – Specialist
5 |  | 13 |  | 2 |  | 2 | Ice pads | 2 | Ice pads | 5.13.2.2.2 | 5 | 0 | Ice pads | 13 – Specialist
5 |  | 13 |  | 2 |  | 3 | Other specialist refrigeration systems | 3 | Other specialist refrigeration systems | 5.13.2.3.3 | 5 | 0 | Other specialist refrigeration systems | 13 – Specialist
5 |  | 13 |  | 3 | Specialist mechanical installations | 1 | Other specialist installations | 1 | Wave machines | 5.13.3.1.1 | 5 | 0 | Wave machines | 13 – Specialist
5 |  | 13 |  | 3 |  | 1 |  | 2 | Saunas | 5.13.3.1.2 | 5 | 0 | Saunas | 13 – Specialist
5 |  | 13 |  | 3 |  | 1 |  | 3 | Jacuzzis | 5.13.3.1.3 | 5 | 0 | Jacuzzis | 13 – Specialist
5 |  | 13 |  | 3 |  | 1 |  | 4 | Swimming pools | 5.13.3.1.4 | 5 | 0 | Swimming pools | 13 – Specialist
5 |  | 13 |  | 3 |  | 1 |  | 5 | Other specialist installations (state type) | 5.13.3.1.5 | 5 | 0 | Other specialist installations (state type) | 13 – Specialist
5 |  | 13 |  | 4 | Specialist electrical installations | 1 | Specialist electrical and electronic installations | 1 | Radio and television studio equipment | 5.13.4.1.1 | 5 | 0 | Radio and television studio equipment | 13 – Specialist
5 |  | 12 |  | 4 |  | 1 |  | 2 | Recoding studio equipment | 5.12.4.1.2 | 5 | 0 | Recoding studio equipment | 13 – Specialist
5 |  | 13 |  | 4 |  | 1 |  | 3 | Television aerial and satellite systems | 5.13.4.1.3 | 5 | 0 | Television aerial and satellite systems | 13 – Specialist
5 |  | 13 |  | 4 |  | 1 |  | 4 | Home cinemas | 5.13.4.1.4 | 5 | 0 | Home cinemas | 13 – Specialist
5 |  | 13 |  | 4 |  | 1 |  | 5 | Multi-room audio and video | 5.13.4.1.5 | 5 | 0 | Multi-room audio and video | 13 – Specialist
5 |  | 13 |  | 4 |  | 1 |  | 6 | Automated curtains and blinds | 5.13.4.1.6 | 5 | 0 | Automated curtains and blinds | 13 – Specialist
5 |  | 13 |  | 4 |  | 1 |  | 7 | Other specialist electrical/electronic system | 5.13.4.1.7 | 5 | 0 | Other specialist electrical/electronic system | 13 – Specialist
5 |  | 13 |  | 5 | Water features | 1 | Water features | 1 | Water features – inc. ornamental fountains and waterfalls | 5.13.5.1.1 | 5 | 0 | Water features – inc. ornamental fountains and waterfalls | 13 – Specialist
5 |  | 13 |  | 5 |  | 1 |  | 2 | Water filtration equipment | 5.13.5.1.2 | 5 | 0 | Water filtration equipment | 13 – Specialist
5 |  | 13 |  | 5 |  | 1 |  | 3 | Nutrient treatment and equipment | 5.13.5.1.3 | 5 | 0 | Nutrient treatment and equipment | 13 – Specialist
5 |  | 13 |  | 5 |  | 1 |  | 4 | Final electrical components – NA | 5.13.5.1.4 | 5 | 0 | Final electrical components – NA | 13 – Specialist
5 |  | 13 |  | 5 |  | 1 |  | 5 | Control components | 5.13.5.1.5 | 5 | 0 | Control components | 13 – Specialist
5 |  | 14 | Builders' work in connection with services | 1 | Builders' work in connection with services | 1 | Builder's work in general areas | 1 | General builders works with services | 5.14.1.1.1 | 5 | 0 | General builders works with services | 1 – Building Structure
5 |  | 14 |  | 1 |  | 2 | Builder's work in landlord areas | 2 | Builder's work in landlord areas | 5.14.1.2.2 | 5 | 0 | Builder's work in landlord areas | 1 – Building Structure
5 |  | 14 |  | 1 |  | 3 | Builder's work to plant rooms | 3 | Builder's work to plant rooms | 5.14.1.3.3 | 5 | 0 | Builder's work to plant rooms | 1 – Building Structure
5 |  | 14 |  | 1 |  | 4 | Large plant and equipment bases | 4 | Large plant and equipment bases | 5.14.1.4.4 | 5 | 0 | Large plant and equipment bases | 1 – Building Structure
5 |  | 14 |  | 1 |  | 5 | Fuel bunds | 5 | BWIC to fuel bunds | 5.14.1.5.5 | 5 | 0 | BWIC to fuel bunds | 1 – Building Structure
6 | Complete buildings and building units | 1 | Prefabricated buildings | 1 | Complete buildings | N/A | Not covered by NRM 3 |  |  | 6.1.1 | 4 | 0 | Not covered by NRM 3 | NOT APPLICABLE
6 |  | 1 |  | 2 | Building units | N/A | Not covered by NRM 3 |  |  | 6.1.2 | 4 | 0 | Not covered by NRM 3 | NOT APPLICABLE
7 | Works to existing buildings | 1 | Minor demolition works and alteration works | 1 | Minor demolition and alteration works | 1 | Spot items | 1.A | Repair items | 7.1.1.1.1.A | 5 | 0 | Repair items | 1 – Building Structure
7 |  | 1 |  | 1 |  | 2 | Minor demolition works | 2.A | Removal items | 7.1.1.2.2.A | 5 | 0 | Removal items | 1 – Building Structure
7 |  | 1 |  | 1 |  | 3 | Removals | 4 | Kitchen fittings and appliances | 7.1.1.3.4 | 5 | 0 | Kitchen fittings and appliances | 1 – Building Structure
7 |  | 1 |  | 1 |  | 4 | Alteration works | 4.A | Alteration works | 7.1.1.4.4.A | 5 | 0 | Alteration works | 1 – Building Structure
7 |  | 2 | Repairs to existing services | 1 | Existing services | 1 | Equipment/plant repairs | 1.A | Repair items | 7.2.1.1.1.A | 5 | 0 | Repair items | 1 – Building Structure
7 |  | 2 |  | 1 |  | 2 | Overhaul services installations |  |  | 7.2.1.2 | 4 | 0 | Overhaul services installations | 1 – Building Structure
7 |  | 3 | Damp proof courses/fungus and beetle eradication | 1 | Damp proof courses | 1 | Damp-proof courses | 1 | Chemical damp proof course | 7.3.1.1.1 | 5 | 0 | Chemical damp proof course | 1 – Building Structure
7 |  | 3 |  | 1 |  | 1 |  | 2 | Injection of mortar damp proof course | 7.3.1.1.2 | 5 | 0 | Injection of mortar damp proof course | 1 – Building Structure
7 |  | 3 |  | 1 |  | 1 |  | 3 | Inserting mechanical damp proof course | 7.3.1.1.3 | 5 | 0 | Inserting mechanical damp proof course | 1 – Building Structure
7 |  | 3 |  | 1 |  | 1 |  | 4 | Local making good to finishes | 7.3.1.1.4 | 5 | 0 | Local making good to finishes | 1 – Building Structure
7 |  | 3 |  | 2 | Fungus/beetle eradication | 1 | Eradication treatment | 1.A | Fungus/beetle eradication | 7.3.2.1.1.A | 5 | 0 | Fungus/beetle eradication | 1 – Building Structure
7 |  | 4 | Facade retention | 1 | Facade retention | 1 | Support structures |  |  | 7.4.1.1 | 4 | 0 | Support structures | 1 – Building Structure
7 |  | 5 | Cleaning existing surfaces | 1 | Cleaning existing surfaces | 1 | Cleaning existing surfaces | 1 | Remove efflorescence stains, spot graffiti, algae, bird droppings, etc. | 7.5.1.1.1 | 5 | 0 | Remove efflorescence stains, spot graffiti, algae, bird droppings, etc. | 1 – Building Structure
7 |  | 5 |  | 1 |  | 1 |  | 2 | Cleaning surfaces | 7.5.1.1.2 | 5 | 0 | Cleaning surfaces | 1 – Building Structure
7 |  | 5 |  | 1 |  | 1 |  | 3 | Artificial weathering | 7.5.1.1.3 | 5 | 0 | Artificial weathering | 1 – Building Structure
7 |  | 5 |  | 2 | Protective coatings to existing surfaces | 1 | Proactive coatings to existing surfaces | 1.A | Protective coatings | 7.5.2.1.1.A | 5 | 0 | Protective coatings | 1 – Building Structure
7 |  | 6 | Renovation works | 1 | Masonry repairs | 1 | Masonry repairs |  |  | 7.6.1.1 | 5 | 0 | Masonry repairs | 1 – Building Structure
7 |  | 6 |  | 2 | Concrete repairs | 1 | Concrete repairs |  |  | 7.6.2.1 | 5 | 0 | Concrete repairs | 1 – Building Structure
7 |  | 6 |  | 3 | Metal repairs | 1 | Metal repairs |  |  | 7.6.3.1 | 5 | 0 | Metal repairs | 1 – Building Structure
7 |  | 6 |  | 4 | Timber repairs | 1 | Timber repairs |  |  | 7.6.4.1 | 5 | 0 | Timber repairs | 1 – Building Structure
7 |  | 6 |  | 5 | Plastics repairs | 1 | Plastic repairs |  |  | 7.6.5.1 | 5 | 0 | Plastic repairs | 1 – Building Structure
8 | External works | 1 | Site preparation works | 1 | Site clearance | N/A | Not covered by NRM 3 |  |  | 8.1.1 | 4 | 0 | Not covered by NRM 3 | NOT APPLICABLE
8 |  | 1 |  | 2 | Preparatory ground works | N/A | Not covered by NRM 3 |  |  | 8.1.2 | 4 | 0 | Not covered by NRM 3 | NOT APPLICABLE
8 |  | 2 | Roads, paths and paving | 1 | Roads, paths and paving | 1 | Roads | 1.A | Maintenance of roads | 8.2.1.1.1.A | 5 | 0 | Maintenance of roads | 3 – Exterior and External Works
8 |  | 2 |  | 1 |  | 2 | Paths | 1.A | Maintenance of paths | 8.2.1.2.1.A | 5 | 0 | Maintenance of paths | 3 – Exterior and External Works
8 |  | 2 |  | 1 |  | 3 | Paved areas | 12 | Paved areas | 8.2.1.3.12 | 5 | 0 | Paved areas | 3 – Exterior and External Works
8 |  | 2 |  | 1 |  | 4 | Roundabouts | 1.A | Maintenance of roundabouts | 8.2.1.4.1.A | 5 | 0 | Maintenance of roundabouts | 3 – Exterior and External Works
8 |  | 2 |  | 1 |  | 5 | Road crossings | 22 | Road crossings | 8.2.1.5.22 | 5 | 0 | Road crossings | 3 – Exterior and External Works
8 |  | 2 |  | 1 |  | 6 | Steps | 27 | Steps | 8.2.1.6.27 | 5 | 0 | Steps | 3 – Exterior and External Works
8 |  | 2 |  | 1 |  | 7 | Ramps | 28 | Ramps | 8.2.1.7.28 | 5 | 0 | Ramps | 3 – Exterior and External Works
8 |  | 2 |  | 1 |  | 8 | Traffic calming accessories | 25 | Traffic calming accessories | 8.2.1.8.25 | 5 | 0 | Traffic calming accessories | 3 – Exterior and External Works
8 |  | 2 |  | 1 |  | 9 | Tree grilles | 25 | Tree grilles | 8.2.1.9.25 | 5 | 0 | Tree grilles | 3 – Exterior and External Works
8 |  | 2 |  | 1 |  | 10 | Vehicle protection barriers | 23 | Vehicle protection barriers | 8.2.1.10.23 | 5 | 0 | Vehicle protection barriers | 3 – Exterior and External Works
8 |  | 2 |  | 1 |  | 11 | Bumpers | 24 | Bumpers | 8.2.1.11.24 | 5 | 0 | Bumpers | 3 – Exterior and External Works
8 |  | 2 |  | 1 |  | 12 | Pavement markings | 26 | Pavement | 8.2.1.12.26 | 5 | 0 | Pavement | 3 – Exterior and External Works
8 |  | 2 |  | 2 | Special surfaces and paving | 1 | Surfacing and paving |  |  | 8.2.2.1 | 4 | 0 | Surfacing and paving | 3 – Exterior and External Works
8 |  | 3 | Soft landscaping, planting and irrigation systems | 1 | Seeding and turfing | 1 | Grassed areas | 1.A | Seeding and turfing (part of ground maintenance) | 8.3.1.1.1.A | 5 | 0 | Seeding and turfing (part of ground maintenance) | 3 – Exterior and External Works
8 |  | 3 |  | 1 |  | 2 | Reinforced grass proprietary systems | 9 | Reinforced grass proprietary systems | 8.3.1.2.9 | 5 | 0 | Reinforced grass proprietary systems | 3 – Exterior and External Works
8 |  | 3 |  | 1 |  | 3 | Marking out grass sports pitches | 12 | Initial marking out grass sports pitches | 8.3.1.3.12 | 5 | 0 | Initial marking out grass sports pitches | 3 – Exterior and External Works
8 |  | 3 |  | 1 |  | 4 | Work to existing grass areas | 4 | Work to existing grass areas | 8.3.1.4.4 | 5 | 0 | Work to existing grass areas | 3 – Exterior and External Works
8 |  | 3 |  | 1 |  | 5 | Maintenance of grassed areas | 5 | Maintenance of grassed areas | 8.3.1.5.5 | 5 | 0 | Maintenance of grassed areas | 3 – Exterior and External Works
8 |  | 3 |  | 2 | External planting | 1 | Planting |  |  | 8.3.2.1 | 4 | 0 | Planting | 3 – Exterior and External Works
8 |  | 3 |  | 2 |  | 2 | Planting reed beds |  |  | 8.3.2.2 | 4 | 0 | Planting reed beds | 3 – Exterior and External Works
8 |  | 3 |  | 2 |  | 3 | Hedges |  |  | 8.3.2.3 | 4 | 0 | Hedges | 3 – Exterior and External Works
8 |  | 3 |  | 2 |  | 4 | Trees |  |  | 8.3.2.4 | 4 | 0 | Trees | 3 – Exterior and External Works
8 |  | 3 |  | 2 |  | 5 | Woodland planting |  |  | 8.3.2.5 | 4 | 0 | Woodland planting | 3 – Exterior and External Works
8 |  | 3 |  | 2 |  | 6 | Tree surgery |  |  | 8.3.2.6 | 4 | 0 | Tree surgery | 3 – Exterior and External Works
8 |  | 3 |  | 2 |  | 7 | Maintenance works to plants |  |  | 8.3.2.7 | 4 | 0 | Maintenance works to plants | 3 – Exterior and External Works
8 |  | 3 |  | 2 |  | 8 | Maintenance works to trees |  |  | 8.3.2.8 | 4 | 0 | Maintenance works to trees | 3 – Exterior and External Works
8 |  | 3 |  | 2 |  | 9 | Maintenance works to hedges |  |  | 8.3.2.9 | 4 | 0 | Maintenance works to hedges | 3 – Exterior and External Works
8 |  | 3 |  | 3 | Irrigation systems | 1 | Irrigation systems | 1 | Irrigation pipework system | 8.3.3.1.1 | 5 | 0 | Irrigation pipework system | 7 – Plumbing and Sanitary
8 |  | 3 |  | 3 |  | 1 |  | 2 | Storage tanks and vessels | 8.3.3.1.2 | 5 | 0 | Storage tanks and vessels | 7 – Plumbing and Sanitary
8 |  | 3 |  | 3 |  | 1 |  | 3 | Chemical storage vessels | 8.3.3.1.3 | 5 | 0 | Chemical storage vessels | 7 – Plumbing and Sanitary
8 |  | 3 |  | 3 |  | 1 |  | 4 | Chemical dosing equipment | 8.3.3.1.4 | 5 | 0 | Chemical dosing equipment | 7 – Plumbing and Sanitary
8 |  | 3 |  | 3 |  | 1 |  | 5 | Nutrient treatment and equipment | 8.3.3.1.5 | 5 | 0 | Nutrient treatment and equipment | 7 – Plumbing and Sanitary
8 |  | 3 |  | 3 |  | 1 |  | 6 | Outlet pipes and nozzles | 8.3.3.1.6 | 5 | 0 | Outlet pipes and nozzles | 7 – Plumbing and Sanitary
8 |  | 3 |  | 3 |  | 1 |  | 7 | Painting anti-corrosion treatments | 8.3.3.1.7 | 5 | 0 | Painting anti-corrosion treatments | 7 – Plumbing and Sanitary
8 |  | 4 | Fencing, railing and walls | 1 | Fencing and railings | 1 | Fencing | 1 | Fencing systems (types) | 8.4.1.1.1 | 5 | 0 | Fencing systems (types) | 3 – Exterior and External Works
8 |  | 4 |  | 1 |  | 1 |  | 3 | Noise/light screening applied to fencing | 8.4.1.1.3 | 5 | 0 | Noise/light screening applied to fencing | 3 – Exterior and External Works
8 |  | 4 |  | 1 |  | 1 |  | 9 | Fixing railings to concrete and masonry | 8.4.1.1.9 | 5 | 0 | Fixing railings to concrete and masonry | 3 – Exterior and External Works
8 |  | 4 |  | 1 |  | 1 |  | 10 | Painting coating and preservative treatments | 8.4.1.1.10 | 5 | 0 | Painting coating and preservative treatments | 3 – Exterior and External Works
8 |  | 4 |  | 1 |  | 2 | Railings | 2 | Railings | 8.4.1.2.2 | 5 | 0 | Railings | 3 – Exterior and External Works
8 |  | 4 |  | 1 |  | 3 | Gates | 4 | Gates and posts | 8.4.1.3.4 | 5 | 0 | Gates and posts | 3 – Exterior and External Works
8 |  | 4 |  | 1 |  | 3 |  | 5 | Security gates and posts | 8.4.1.3.5 | 5 | 0 | Security gates and posts | 3 – Exterior and External Works
8 |  | 4 |  | 1 |  | 3 |  | 6 | Ironmongery | 8.4.1.3.6 | 5 | 0 | Ironmongery | 3 – Exterior and External Works
8 |  | 4 |  | 2 | Walls and screens | 1 | Walls | 1 | Masonry walls and screens | 8.4.2.1.1 | 5 | 0 | Masonry walls and screens | 3 – Exterior and External Works
8 |  | 4 |  | 2 |  | 1 |  | 9 | Pier caps | 8.4.2.1.9 | 5 | 0 | Pier caps | 3 – Exterior and External Works
8 |  | 4 |  | 2 |  | 1 |  | 10 | Copings, etc. | 8.4.2.1.10 | 5 | 0 | Copings, etc. | 3 – Exterior and External Works
8 |  | 4 |  | 2 |  | 2 | Screens | 2 | Masonry walls with timber infill panels | 8.4.2.2.2 | 5 | 0 | Masonry walls with timber infill panels | 3 – Exterior and External Works
8 |  | 4 |  | 2 |  | 3 | Gates |  |  | 8.4.2.3 | 4 | 0 | Gates | 3 – Exterior and External Works
8 |  | 4 |  | 3 | Retaining walls | 1 | Retaining walls |  |  | 8.4.3.1 | 4 | 0 | Retaining walls | 3 – Exterior and External Works
8 |  | 4 |  | 4 | Barriers and guardrails | 1 | Vehicle restraint systems | 1.A | Fixing barriers and guardrails Redecorations | 8.4.4.1.1.A | 5 | 0 | Fixing barriers and guardrails Redecorations | 3 – Exterior and External Works
8 |  | 4 |  | 4 |  | 1 |  | 1.B | Redecorations | 8.4.4.1.1.B | 5 | 0 | Redecorations | 3 – Exterior and External Works
8 |  | 4 |  | 4 |  | 2 | Pedestrian restraint systems | 2 | Pedestrian restraint systems | 8.4.4.2.2 | 5 | 0 | Pedestrian restraint systems | 3 – Exterior and External Works
8 |  | 4 |  | 4 |  | 3 | Vehicle and pedestrian control barriers and gates | 3 | Vehicle and pedestrian control barriers and gates | 8.4.4.3.3 | 5 | 0 | Vehicle and pedestrian control barriers and gates | 3 – Exterior and External Works
8 |  | 5 | Site/street furniture and equipment | 1 | Site/street furniture and equipment | 1 | Components | 1 | Gates | 8.5.1.1.1 | 5 | 0 | Gates | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 2 | Turnstiles | 8.5.1.1.2 | 5 | 0 | Turnstiles | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 3 | Bollards | 8.5.1.1.3 | 5 | 0 | Bollards | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 4 | Seats, benches and tables | 8.5.1.1.4 | 5 | 0 | Seats, benches and tables | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 5 | Litter bins, grit bins and dustbins | 8.5.1.1.5 | 5 | 0 | Litter bins, grit bins and dustbins | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 6 | Poster display units and notice boards | 8.5.1.1.6 | 5 | 0 | Poster display units and notice boards | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 7 | Cycle stands | 8.5.1.1.7 | 5 | 0 | Cycle stands | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 8 | Directional signs | 8.5.1.1.8 | 5 | 0 | Directional signs | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 9 | Flagpoles | 8.5.1.1.9 | 5 | 0 | Flagpoles | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 10 | Sports and playground equipment | 8.5.1.1.10 | 5 | 0 | Sports and playground equipment | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 11 | Other furniture and equipment | 8.5.1.1.11 | 5 | 0 | Other furniture and equipment | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 12 | Minor footbridges | 8.5.1.1.12 | 5 | 0 | Minor footbridges | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 13 | Clothes drying fittings | 8.5.1.1.13 | 5 | 0 | Clothes drying fittings | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 14 | Bus stops, bus shelters, telephone boxes | 8.5.1.1.14 | 5 | 0 | Bus stops, bus shelters, telephone boxes | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 15 | Sculptures | 8.5.1.1.15 | 5 | 0 | Sculptures | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 16 | Site/street furniture and equipment | 8.5.1.1.16 | 5 | 0 | Site/street furniture and equipment | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 17 | Other site and street furniture and equipment | 8.5.1.1.17 | 5 | 0 | Other site and street furniture and equipment | 3 – Exterior and External Works
8 |  | 5 |  | 1 |  | 1 |  | 19 | Painting and preservation treatments | 8.5.1.1.19 | 5 | 0 | Painting and preservation treatments | 3 – Exterior and External Works
8 |  | 5 |  | 2 | Ornamental features | 1 | Ornamental features | 1 | Water features | 8.5.2.1.1 | 5 | 0 | Water features | 3 – Exterior and External Works
8 |  | 5 |  | 2 |  | 2 |  | 2 | Other features | 8.5.2.2.2 | 5 | 0 | Other features | 3 – Exterior and External Works
8 |  | 6 | External drainage | 1 | Surface water and foul drainage | 1 | Connection to statutory undertakings sewers | 1 | Gullies and gratings | 8.6.1.1.1 | 5 | 0 | Gullies and gratings | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 2 | Drainage runs below ground | 2 | Drainage runs below ground | 8.6.1.2.2 | 5 | 0 | Drainage runs below ground | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 3 | Drainage runs above ground | 3 | Drainage runs above ground | 8.6.1.3.3 | 5 | 0 | Drainage runs above ground | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 4 | Prefabricated channels | 11 | Prefabricated channels | 8.6.1.4.11 | 5 | 0 | Prefabricated channels | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 5 | Manholes | 12 | Interceptor traps | 8.6.1.5.12 | 5 | 0 | Interceptor traps | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 5 |  | 13 | Inspection chambers | 8.6.1.5.13 | 5 | 0 | Inspection chambers | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 5 |  | 14 | Soakaways | 8.6.1.5.14 | 5 | 0 | Soakaways | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 5 |  | 15 | Retention/storage tanks and vessels | 8.6.1.5.15 | 5 | 0 | Retention/storage tanks and vessels | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 5 |  | 16 | Cesspools and septic tanks | 8.6.1.5.16 | 5 | 0 | Cesspools and septic tanks | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 5 |  | 17 | Petrol interceptor units | 8.6.1.5.17 | 5 | 0 | Petrol interceptor units | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 6 | Alterations to existing external drainage systems | 24 | Alterations to existing external drainage systems | 8.6.1.6.24 | 5 | 0 | Alterations to existing external drainage systems | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 7 | Works to existing manholes | 25 | Works to existing manholes | 8.6.1.7.25 | 5 | 0 | Works to existing manholes | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 8 | Cleaning existing drains | 26 | Cleaning existing drains | 8.6.1.8.26 | 5 | 0 | Cleaning existing drains | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 9 | Sealing redundant drains | 27 | Sealing redundant drains | 8.6.1.9.27 | 5 | 0 | Sealing redundant drains | 7 – Plumbing and Sanitary
8 |  | 6 |  | 1 |  | 10 | Filling disused manholes | 28 | Filling disused manholes | 8.6.1.10.28 | 5 | 0 | Filling disused manholes | 7 – Plumbing and Sanitary
8 |  | 6 |  | 2 | Ancillary drainage systems | 1 | Pumping stations | 1 | Pipework systems | 8.6.2.1.1 | 5 | 0 | Pipework systems | 7 – Plumbing and Sanitary
8 |  | 6 |  | 2 |  | 1 |  | 7 | Controls components | 8.6.2.1.7 | 5 | 0 | Controls components | 7 – Plumbing and Sanitary
8 |  | 6 |  | 2 |  | 1 |  | 8 | Monitoring equipment located externally | 8.6.2.1.8 | 5 | 0 | Monitoring equipment located externally | 7 – Plumbing and Sanitary
8 |  | 6 |  | 2 |  | 1 |  | 9 | Painting anti-corrosion treatments | 8.6.2.1.9 | 5 | 0 | Painting anti-corrosion treatments | 7 – Plumbing and Sanitary
8 |  | 6 |  | 2 |  | 2 | Ejector stations |  |  | 8.6.2.2 | 5 | 0 | Ejector stations | 7 – Plumbing and Sanitary
8 |  | 6 |  | 2 |  | 3 | Storage/retention tanks and vessels |  |  | 8.6.2.3 | 5 | 0 | Storage/retention tanks and vessels | 7 – Plumbing and Sanitary
8 |  | 6 |  | 2 |  | 4 | Sewage treatment |  |  | 8.6.2.4 | 5 | 0 | Sewage treatment | 7 – Plumbing and Sanitary
8 |  | 6 |  | 2 |  | 5 | Enzyme systems |  |  | 8.6.2.5 | 5 | 0 | Enzyme systems | 7 – Plumbing and Sanitary
8 |  | 6 |  | 2 |  | 6 | Sustainable urban drainage systems |  |  | 8.6.2.6 | 5 | 0 | Sustainable urban drainage systems | 7 – Plumbing and Sanitary
8 |  | 6 |  | 3 | External laboratory and industrial liquid waste drainage | 1 | Drainage runs below ground | 1 | External chemical toxic and industrial liquid waste drainage | 8.6.3.1.1 | 5 | 0 | External chemical toxic and industrial liquid waste drainage | 13 – Specialist
8 |  | 6 |  | 3 |  | 2 | Drainage runs above ground | 4 | Drainage runs above ground | 8.6.3.2.4 | 5 | 0 | Drainage runs above ground | 13 – Specialist
8 |  | 6 |  | 3 |  | 3 | Equipment and plant | 6 | Storage tanks and vessels | 8.6.3.3.6 | 5 | 0 | Storage tanks and vessels | 13 – Specialist
8 |  | 6 |  | 3 |  | 3 |  | 7 | Settlement tanks | 8.6.3.3.7 | 5 | 0 | Settlement tanks | 13 – Specialist
8 |  | 6 |  | 3 |  | 3 |  | 8 | Effluent treatment plant | 8.6.3.3.8 | 5 | 0 | Effluent treatment plant | 13 – Specialist
8 |  | 6 |  | 3 |  | 3 |  | 9 | Dosing equipment | 8.6.3.3.9 | 5 | 0 | Dosing equipment | 13 – Specialist
8 |  | 6 |  | 3 |  | 3 |  | 10 | Sterilisation equipment | 8.6.3.3.10 | 5 | 0 | Sterilisation equipment | 13 – Specialist
8 |  | 6 |  | 3 |  | 3 |  | 12 | Controls components | 8.6.3.3.12 | 5 | 0 | Controls components | 13 – Specialist
8 |  | 6 |  | 3 |  | 3 |  | 13 | Monitoring equipment | 8.6.3.3.13 | 5 | 0 | Monitoring equipment | 13 – Specialist
8 |  | 6 |  | 4 | Land drainage | 1 | Drainage runs below ground |  |  | 8.6.4.1 | 4 | 0 | Drainage runs below ground | 7 – Plumbing and Sanitary
8 |  | 6 |  | 4 |  | 2 | Manholes | 12 | Soakaways | 8.6.4.2.12 | 5 | 0 | Soakaways | 7 – Plumbing and Sanitary
8 |  | 6 |  | 4 |  | 2 |  | 13 | Storage tanks and vessels | 8.6.4.2.13 | 5 | 0 | Storage tanks and vessels | 7 – Plumbing and Sanitary
8 |  | 6 |  | 4 |  | 3 | Drainage blankets | 6 | Drainage blankets | 8.6.4.3.6 | 5 | 0 | Drainage blankets | 7 – Plumbing and Sanitary
8 |  | 6 |  | 4 |  | 4 | Land drainage to parkland |  |  | 8.6.4.4 | 4 | 0 | Land drainage to parkland | 7 – Plumbing and Sanitary
8 |  | 7 | External services | 1 | Water mains supply | 1 | Connections | 1 | Water mains supply connection | 8.7.1.1.1 | 5 | 0 | Water mains supply connection | 7 – Plumbing and Sanitary
8 |  | 7 |  | 1 |  | 1 |  | 5 | Water meters | 8.7.1.1.5 | 5 | 0 | Water meters | 7 – Plumbing and Sanitary
8 |  | 7 |  | 1 |  | 1 |  | 6 | Fire hydrants | 8.7.1.1.6 | 5 | 0 | Fire hydrants | 7 – Plumbing and Sanitary
8 |  | 7 |  | 1 |  | 1 |  | 7 | Trace heating – pipework | 8.7.1.1.7 | 5 | 0 | Trace heating – pipework | 7 – Plumbing and Sanitary
8 |  | 7 |  | 1 |  | 1 |  | 8 | Thermal insulation | 8.7.1.1.8 | 5 | 0 | Thermal insulation | 7 – Plumbing and Sanitary
8 |  | 7 |  | 1 |  | 2 | Connections to external plant | 2 | Connections to external plant | 8.7.1.2.2 | 5 | 0 | Connections to external plant | 7 – Plumbing and Sanitary
8 |  | 7 |  | 1 |  | 3 | Service runs | 2 | Service runs | 8.7.1.3.2 | 5 | 0 | Service runs | 7 – Plumbing and Sanitary
8 |  | 7 |  | 1 |  | 3 |  | 4 | Mains supply and distribution | 8.7.1.3.4 | 5 | 0 | Mains supply and distribution | 7 – Plumbing and Sanitary
8 |  | 7 |  | 1 |  | 4 | Rainwater harvesting systems | 10 | Rainwater harvesting systems | 8.7.1.4.10 | 5 | 0 | Rainwater harvesting systems | 7 – Plumbing and Sanitary
8 |  | 7 |  | 1 |  | 5 | Grey water systems | 11 | Grey water systems | 8.7.1.5.11 | 5 | 0 | Grey water systems | 7 – Plumbing and Sanitary
8 |  | 7 |  | 2 | Electricity mains supply | 1 | Connection to statutory undertakings | 1 | Electrical mains supply | 8.7.2.1.1 | 5 | 0 | Electrical mains supply | 6 – Electrical
8 |  | 7 |  | 2 |  | 2 | Service runs |  |  | 8.7.2.2 | 4 | 0 | Service runs | 6 – Electrical
8 |  | 7 |  | 2 |  | 3 | Transformer substations | 3 | Transformer substations | 8.7.2.3.3 | 5 | 0 | Transformer substations | 6 – Electrical
8 |  | 7 |  | 2 |  | 4 | External electricity generation installation/plant | 7 | External electricity generation installation/plant | 8.7.2.4.7 | 5 | 0 | External electricity generation installation/plant | 6 – Electrical
8 |  | 7 |  | 3 | External mains transformation devices | 1 | Wind turbines | 1 | Wind turbines (external transformation devices) | 8.7.3.1.1 | 5 | 0 | Wind turbines (external transformation devices) | 13 – Specialist
8 |  | 7 |  | 3 |  | 1 |  | 2 | Distribution of LV electricity to main switch gear panel within buildings | 8.7.3.1.2 | 5 | 0 | Distribution of LV electricity to main switch gear panel within buildings | 13 – Specialist
8 |  | 7 |  | 3 |  | 2 | Photovoltaic devices | 2 | Photovoltaic devices | 8.7.3.2.2 | 5 | 0 | Photovoltaic devices | 13 – Specialist
8 |  | 7 |  | 3 |  | 3 | Other transformation devices | 3 | Other transformation devices | 8.7.3.3.3 | 5 | 0 | Other transformation devices | 13 – Specialist
8 |  | 7 |  | 4 | Electricity distribution to external plant and equipment | 1 | Connections to external plant or equipment | 1 | Electrical distribution systems | 8.7.4.1.1 | 5 | 0 | Electrical distribution systems | 6 – Electrical
8 |  | 7 |  | 4 |  | 1 |  | 2 | LV switchgear and distribution boards | 8.7.4.1.2 | 5 | 0 | LV switchgear and distribution boards | 6 – Electrical
8 |  | 7 |  | 4 |  | 1 |  | 3 | UPS | 8.7.4.1.3 | 5 | 0 | UPS | 6 – Electrical
8 |  | 7 |  | 4 |  | 1 |  | 4 | Cables and wiring | 8.7.4.1.4 | 5 | 0 | Cables and wiring | 6 – Electrical
8 |  | 7 |  | 4 |  | 1 |  | 5 | Conduits and cable trunking | 8.7.4.1.5 | 5 | 0 | Conduits and cable trunking | 6 – Electrical
8 |  | 7 |  | 4 |  | 1 |  | 6 | Earthing and bonding | 8.7.4.1.6 | 5 | 0 | Earthing and bonding | 6 – Electrical
8 |  | 7 |  | 5 | Gas mains supply | 1 | Connections to statutory undertakings | 1 | Gas mains supply | 8.7.5.1.1 | 5 | 0 | Gas mains supply | 12 – Fuel Systems
8 |  | 7 |  | 5 |  | 2 | Service runs | 2 | Gas mains | 8.7.5.2.2 | 5 | 0 | Gas mains | 12 – Fuel Systems
8 |  | 7 |  | 5 |  | 3 |  | 4 | Distribution pipelines | 8.7.5.3.4 | 5 | 0 | Distribution pipelines | 12 – Fuel Systems
8 |  | 7 |  | 5 |  | 3 | Governing stations | 5 | Governing stations | 8.7.5.3.5 | 5 | 0 | Governing stations | 12 – Fuel Systems
8 |  | 7 |  | 5 |  | 3 |  | 6 | LPG installations | 8.7.5.3.6 | 5 | 0 | LPG installations | 12 – Fuel Systems
8 |  | 7 |  | 6 | Telecommunications and other communication system connections | 1 | Telecommunications systems | 1 | Telecommunications systems | 8.7.6.1.1 | 5 | 0 | Telecommunications systems | 11 – Communication, Controls and Security
8 |  | 7 |  | 6 |  | 1 |  | 2 | Telecomm distribution systems | 8.7.6.1.2 | 5 | 0 | Telecomm distribution systems | 11 – Communication, Controls and Security
8 |  | 7 |  | 6 |  | 2 | Cables television connections | 7 | Cables television connections | 8.7.6.2.7 | 5 | 0 | Cables television connections | 11 – Communication, Controls and Security
8 |  | 7 |  | 6 |  | 3 | Other communication systems | 8 | Other communication systems | 8.7.6.3.8 | 5 | 0 | Other communication systems | 11 – Communication, Controls and Security
8 |  | 7 |  | 6 |  | 4 | Service runs | 9 | Service runs | 8.7.6.4.9 | 5 | 0 | Service runs | 11 – Communication, Controls and Security
8 |  | 7 |  | 7 | External fuel storage and piped distribution systems | 1 | Fuel storage and piped distribution systems | 1 | Oil, petrol and diesel | 8.7.7.1.1 | 5 | 0 | Oil, petrol and diesel | 12 – Fuel Systems
8 |  | 7 |  | 7 |  | 1 |  | 2 | Storage tanks and vessels | 8.7.7.1.2 | 5 | 0 | Storage tanks and vessels | 12 – Fuel Systems
8 |  | 7 |  | 7 |  | 1 |  | 3 | Proprietary supports | 8.7.7.1.3 | 5 | 0 | Proprietary supports | 12 – Fuel Systems
8 |  | 7 |  | 7 |  | 1 |  | 6 | Distribution pipelines | 8.7.7.1.6 | 5 | 0 | Distribution pipelines | 12 – Fuel Systems
8 |  | 7 |  | 7 |  | 1 |  | 7 | Pipeline ancillaries | 8.7.7.1.7 | 5 | 0 | Pipeline ancillaries | 12 – Fuel Systems
8 |  | 7 |  | 7 |  | 1 |  | 8 | Thermal insulation | 8.7.7.1.8 | 5 | 0 | Thermal insulation | 12 – Fuel Systems
8 |  | 7 |  | 7 |  | 1 |  | 10 | Meters | 8.7.7.1.10 | 5 | 0 | Meters | 12 – Fuel Systems
8 |  | 7 |  | 7 |  | 1 |  | 11 | Monitoring equipment | 8.7.7.1.11 | 5 | 0 | Monitoring equipment | 12 – Fuel Systems
8 |  | 7 |  | 7 |  | 2 | Service runs |  |  | 8.7.7.2 | 4 | 0 | Service runs | 12 – Fuel Systems
8 |  | 7 |  | 8 | External security systems | 1 | Surveillance equipment | 1 | Surveillance equipment (e.g. CCTV) | 8.7.8.1.1 | 5 | 0 | Surveillance equipment (e.g. CCTV) | 11 – Communication, Controls and Security
8 |  | 7 |  | 8 |  | 1 |  | 9 | Camera poles, etc. | 8.7.8.1.9 | 5 | 0 | Camera poles, etc. | 11 – Communication, Controls and Security
8 |  | 7 |  | 8 |  | 1 |  | 10 | General power installations | 8.7.8.1.10 | 5 | 0 | General power installations | 11 – Communication, Controls and Security
8 |  | 7 |  | 8 |  | 2 | Security detection equipment | 2 | Security detection equipment | 8.7.8.2.2 | 5 | 0 | Security detection equipment | 11 – Communication, Controls and Security
8 |  | 7 |  | 8 |  | 3 | Security alarm equipment | 3 | Security alarm equipment | 8.7.8.3.3 | 5 | 0 | Security alarm equipment | 11 – Communication, Controls and Security
8 |  | 7 |  | 8 |  | 4 | Gate access control systems | 4 | Gate access control systems | 8.7.8.4.4 | 5 | 0 | Gate access control systems | 11 – Communication, Controls and Security
8 |  | 7 |  | 8 |  | 5 | Gate entry systems | 5 | Gate entry systems | 8.7.8.5.5 | 5 | 0 | Gate entry systems | 11 – Communication, Controls and Security
8 |  | 7 |  | 8 |  | 6 | Security lights and lighting systems | 6 | Security lights and lighting systems | 8.7.8.6.6 | 5 | 0 | Security lights and lighting systems | 11 – Communication, Controls and Security
8 |  | 7 |  | 8 |  | 7 | Other security systems | 7 | Other security systems | 8.7.8.7.7 | 5 | 0 | Other security systems | 11 – Communication, Controls and Security
8 |  | 7 |  | 8 |  | 8 | Service runs | 8 | Cables and wiring | 8.7.8.8.8 | 5 | 0 | Cables and wiring | 11 – Communication, Controls and Security
8 |  | 7 |  | 9 | Site/street lighting systems | 1 | External lighting to pedestrian areas | 1 | External lighting columns and poles, bollards and masts | 8.7.9.1.1 | 5 | 0 | External lighting columns and poles, bollards and masts | 6 – Electrical
8 |  | 7 |  | 9 |  | 1 |  | 2 | Luminaries/lamps | 8.7.9.1.2 | 5 | 0 | Luminaries/lamps | 6 – Electrical
8 |  | 7 |  | 9 |  | 1 |  | 4 | General power installations | 8.7.9.1.4 | 5 | 0 | General power installations | 6 – Electrical
8 |  | 7 |  | 9 |  | 1 |  | 7 | Luminaries/lamps | 8.7.9.1.7 | 5 | 0 | Luminaries/lamps | 6 – Electrical
8 |  | 7 |  | 9 |  | 1 |  | 8 | Lighting control points | 8.7.9.1.8 | 5 | 0 | Lighting control points | 6 – Electrical
8 |  | 7 |  | 9 |  | 1 |  | 9 | Painting and anti-corrosion treatments | 8.7.9.1.9 | 5 | 0 | Painting and anti-corrosion treatments | 6 – Electrical
8 |  | 7 |  | 9 |  | 2 | External lighting to paths |  |  | 8.7.9.2 | 4 | 0 | External lighting to paths | 6 – Electrical
8 |  | 7 |  | 9 |  | 3 | External lighting to roads |  |  | 8.7.9.3 | 4 | 0 | External lighting to roads | 6 – Electrical
8 |  | 7 |  | 9 |  | 4 | Illuminated traffic signs | 3 | Illuminated traffic signs | 8.7.9.4.3 | 5 | 0 | Illuminated traffic signs | 6 – Electrical
8 |  | 7 |  | 10 | Local/district heating installations | 1 | Heat source | 1 | External located heat source (e.g. boiler plant) | 8.7.10.1.1 | 5 | 0 | External located heat source (e.g. boiler plant) | 5 – HVAC and Mechanical
8 |  | 7 |  | 10 |  | 1 |  | 2 | Instrumentation and controls (heat source) | 8.7.10.1.2 | 5 | 0 | Instrumentation and controls to heat source | 5 – HVAC and Mechanical
8 |  | 7 |  | 10 |  | 1 |  | 5 | Instrumentation and controls (heating) | 8.7.10.1.5 | 5 | 0 | Instrumentation and controls to heating systems | 5 – HVAC and Mechanical
8 |  | 7 |  | 10 |  | 1 |  | 6 | Thermal insulation | 8.7.10.1.6 | 5 | 0 | Thermal insulation | 5 – HVAC and Mechanical
8 |  | 7 |  | 10 |  | 2 | Service runs | 3 | Service runs | 8.7.10.2.3 | 5 | 0 | Service runs | 5 – HVAC and Mechanical
8 |  | 7 |  | 10 |  | 3 | External heating, ducts and duct access covers | 4 | External heating, ducts and duct access covers | 8.7.10.3.4 | 5 | 0 | External heating, ducts and duct access covers | 5 – HVAC and Mechanical
8 |  | 7 |  | 11 | Builders work in connection with external services | 1 | Ducts, etc. | 1 | Ducts | 8.7.11.1.1 | 5 | 0 | Ducts | 1 – Building Structure
8 |  | 7 |  | 11 |  | 2 | Supports to external storage tanks etc | 2 | Supports to external storage tanks etc | 8.7.11.2.2 | 5 | 0 | Supports to external storage tanks etc | 1 – Building Structure
8 |  | 7 |  | 11 |  | 3 | Fuel bunds, etc. | 3 | Fuel bunds, etc. | 8.7.11.3.3 | 5 | 0 | Fuel bunds, etc. | 1 – Building Structure
8 |  | 7 |  | 11 |  | 4 | Protective compounds, fencing etc for LPG installations, etc. | 4 | Protective compounds, fencing etc for LPG installations, etc. | 8.7.11.4.4 | 5 | 0 | Protective compounds, fencing etc for LPG installations, etc. | 1 – Building Structure
8 |  | 7 |  | 11 |  | 5 | Protective compounds connected with transformer substations, etc. | 5 | Protective compounds connected with transformer substations, etc. | 8.7.11.5.5 | 5 | 0 | Protective compounds connected with transformer substations, etc. | 1 – Building Structure
8 |  | 7 |  | 11 |  | 6 | Bases for service equipment | 6 | Bases for service equipment | 8.7.11.6.6 | 5 | 0 | Bases for service equipment | 1 – Building Structure
8 |  | 7 |  | 11 |  | 7 | Other builder's work in connection with external services | 7 | Other builder's work in connection with external services | 8.7.11.7.7 | 5 | 0 | Other builder's work in connection with external services | 1 – Building Structure
8 |  | 8 | Minor building works and ancillary buildings | 1 | Minor building works | 1 | Refurbishment of existing ancillary buildings | N/A |  | 8.8.1.1 | 4 | 0 | N/A | NOT APPLICABLE
8 |  | 8 |  | 1 |  | 2 | Overhaul existing mechanical and electrical plant ad equipment | 2 | Overhaul existing mechanical and electrical plant ad equipment | 8.8.1.2.2 | 5 | 0 | Overhaul existing mechanical and electrical plant ad equipment | 1 – Building Structure
8 |  | 8 |  | 1 |  | 3 | Repairs to existing fences, railings, walls and screen walls | 3 | Repairs to existing fences, railings, walls and screen walls | 8.8.1.3.3 | 5 | 0 | Repairs to existing fences, railings, walls and screen walls | 1 – Building Structure
8 |  | 8 |  | 2 | Ancillary buildings and structures | 1 | Minor ancillary buildings |  |  | 8.8.2.1 | 4 | 0 | N/A | NOT APPLICABLE
8 |  | 8 |  | 3 | Underpinning to external site boundary walls | 1 | Underpinning to external site boundary walls, etc. | 1 | Underpinning | 8.8.3.1.1 | 5 | 0 | Underpinning | 13 – Specialist
9 | Maintenance contractor's management and administration costs | 1 | Employer's requirements | 1 | Site accommodation | 1 | Site accommodation |  |  | 9.1.1.1 | 4 | 0 | N/A | NOT APPLICABLE
9 |  | 1 |  | 1 |  | 2 | Furniture and equipment |  |  | 9.1.1.2 | 4 | 0 | Furniture and equipment | 14 – Management & Operations
9 |  | 1 |  | 1 |  | 3 | Telecommunications and IT systems |  |  | 9.1.1.3 | 4 | 0 | Telecommunications and IT systems | 14 – Management & Operations
9 |  | 1 |  | 2 | Site records | 1 | Site records | 3 | Web based facilities management systems – including updating data as well as implementation and training on BMS | 9.1.2.1.1 | 5 | 0 | Web based facilities management systems – including updating data as well as implementation and training on BMS | 14 – Management & Operations
9 |  | 1 |  | 3 | Completion and post-completion requirements | 1 | Handover requirements | 2 | Provision of spare parts for maintenance | 9.1.3.1.2 | 5 | 0 | Provision of spare parts for maintenance | 14 – Management & Operations
9 |  | 1 |  | 3 |  | 1 |  | 3 | Provision of tools and potable instruments | 9.1.3.1.3 | 5 | 0 | Provision of tools and portable instruments | 14 – Management & Operations
9 |  | 1 |  | 3 |  | 2 | Operation and maintenance services |  |  | 9.1.3.2 | 4 | 0 | Operation and maintenance services | 14 – Management & Operations
9 |  | 1 |  | 4 | Management tasks – specific types | 1 | Air conditioning inspections |  |  | 9.1.4.1 |  |  | Air conditioning inspections | 14 – Management & Operations | 83-01 & 83-02
[15 empty] | 83--03 | Asbestos | not assigned in 2020
9 |  | 1 |  | 4 |  | 2 | Building logbooks and O&M Manuals |  |  | 9.1.4.2 |  |  | Building logbooks and O&M Manuals | 14 – Management & Operations | 83-04
9 |  | 1 |  | 4 |  | 3 | Display energy certificates (DEC) |  |  | 9.1.4.3 |  |  | Display energy certificates (DEC) | 14 – Management & Operations | 83-05
9 |  | 1 |  | 4 |  | 4 | Electrical installations – management audits |  |  | 9.1.4.4 |  |  | Electrical installations – management audits | 14 – Management & Operations | 83-06
9 |  | 1 |  | 4 |  | 5 | Electrical lighting certificates logbook |  |  | 9.1.4.5 |  |  | Electrical lighting certificates logbook | 14 – Management & Operations | 83-07
9 |  | 1 |  | 4 |  | 6 | Energy performance certificates (EPC) |  |  | 9.1.4.6 |  |  | Energy performance certificates (EPC) | 14 – Management & Operations | 83-08
9 |  | 1 |  | 4 |  | 7 | Evaporating cooling systems – management audit |  |  | 9.1.4.7 |  |  | Evaporating cooling systems – management audit | 14 – Management & Operations | 83-09
9 |  | 1 |  | 4 |  | 8 | Fire risk assessments |  |  | 9.1.4.8 |  |  | Fire risk assessments | 14 – Management & Operations | 83-10
9 |  | 1 |  | 4 |  | 9 | Fire safety logbook |  |  | 9.1.4.9 |  |  | Fire safety logbook | 14 – Management & Operations | 83-11
9 |  | 1 |  | 4 |  | 10 | Inventory of Greenhouses Gases (F-Gases) |  |  | 9.1.4.10 |  |  | Inventory of Greenhouses Gases (F-Gases) | 14 – Management & Operations | 83-12
9 |  | 1 |  | 4 |  | 11 | Lifting equipment – management audit |  |  | 9.1.4.11 |  |  | Lifting equipment – management audit | 14 – Management & Operations | 83-13
9 |  | 1 |  | 4 |  | 12 | Lifts and escalators – management audit |  |  | 9.1.4.12 |  |  | Lifts and escalators – management audit | 14 – Management & Operations | 83-14
9 |  | 1 |  | 4 |  | 13 | Local extract ventilation – management audit |  |  | 9.1.4.13 |  |  | Local extract ventilation – management audit | 14 – Management & Operations | 83-15
9 |  | 1 |  | 4 |  | 14 | Noise assessment and records |  |  | 9.1.4.14 |  |  | Noise assessment and records | 14 – Management & Operations | 83-16
9 |  | 1 |  | 4 |  | 15 | Pressure systems – management audits |  |  | 9.1.4.15 |  |  | Pressure systems – management audits | 14 – Management & Operations | 83-17
9 |  | 1 |  | 4 |  | 16 | Smoke control and pressurisation – management audits |  |  | 9.1.4.16 |  |  | Smoke control and pressurisation – management audits | 14 – Management & Operations | 83-18
9 |  | 1 |  | 4 |  | 17 | Tree reports |  |  | 9.1.4.17 |  |  | Tree reports | 14 – Management & Operations | 88-68
9 |  | 1 |  | 4 |  | 18 | Waste disposal |  |  | 9.1.4.18 |  |  | Waste disposal | 14 – Management & Operations | 83-19
9 |  | 1 |  | 4 |  | 19 | Waste electrical and electronic equipment (WEEE) – management audit |  |  | 9.1.4.19 |  |  | Waste electrical and electronic equipment (WEEE) – management audit | 14 – Management & Operations | 83-20
9 |  | 1 |  | 4 |  | 20 | Water systems – management audit |  |  | 9.1.4.20 |  |  | Water systems – management audit | 14 – Management & Operations | 83-21
9 |  | 1 |  | 4 |  | 21 | Other management tasks – state type |  |  | 9.1.4.21 |  |  | Other management tasks – state type | 14 – Management & Operations
[15 empty] | 83-22 | Water Safety Plan (WSP) | not assigned in 2020
[15 empty] | 83-24 | Polychlorinated Biphenyls (PCBs) - Identification, Registration, Labelling and Disposal | not assigned in 2020
[15 empty] | 83-26 | Checklist for Renting Out Accommodation | not assigned in 2020
[15 empty] | 83-27 | Condition Appraisal and Inventory Check | not assigned in 2020
[15 empty] | 83-28 | Landlord Electrical Safety Checks - England | not assigned in 2020
[15 empty] | 83-29 | Landlord Electrical Safety Checks - Northern Ireland | not assigned in 2020
[15 empty] | 83-30 | Landlord Electrical Safety Checks - Scotland | not assigned in 2020
[15 empty] | 83-31 | Landlord Electrical Safety Checks - Wales | not assigned in 2020
[15 empty] | 83-32 | Landlord Gas Safety Checks | not assigned in 2020
[15 empty] | 83-33 | Fire Alarms and Associated Equipment - Premises Management | not assigned in 2020
9 |  | 2 | Maintenance contractor's cost items | 1 | Management and staff | 1 | Contract specific management and staff |  |  | 9.2.1.1 | 4 | 0 | Contract specific management and staff | 14 – Management & Operations
9 |  | 2 |  | 1 |  | 2 | Visiting management and staff |  |  | 9.2.1.2 | 4 | 0 | Visiting management and staff | 14 – Management & Operations
9 |  | 2 |  | 1 |  | 3 | Extraordinary support costs |  |  | 9.2.1.3 | 4 | 0 | Extraordinary support costs | 14 – Management & Operations
9 |  | 2 |  | 1 |  | 4 | Staff travel (not part of labour rates) |  |  | 9.2.1.4 | 4 | 0 | Staff travel (not part of labour rates) | 14 – Management & Operations
9 |  | 2 |  | 2 | Site establishment | 1 | Site accommodation |  |  | 9.2.2.1 | 4 | 0 | Site accommodation | 14 – Management & Operations
9 |  | 2 |  | 2 |  | 2 | Temporary works |  |  | 9.2.2.2 | 4 | 0 | Temporary works | 14 – Management & Operations
9 |  | 2 |  | 2 |  | 3 | Furniture and equipment |  |  | 9.2.2.3 | 4 | 0 | Furniture and equipment | 14 – Management & Operations
9 |  | 2 |  | 2 |  | 4 | IT systems |  |  | 9.2.2.4 | 4 | 0 | IT systems | 14 – Management & Operations
9 |  | 2 |  | 2 |  | 5 | Consumables and services |  |  | 9.2.2.5 | 4 | 0 | Consumables and services | 14 – Management & Operations
9 |  | 2 |  | 2 |  | 6 | Brought on services |  |  | 9.2.2.6 | 4 | 0 | Brought on services | 14 – Management & Operations
9 |  | 2 |  | 3 | Temporary services | T/E |  |  |  | 9.2.3 | 3 | 0 | Taken elsewhere with work items | NOT APPLICABLE
9 |  | 2 |  | 4 | Security | 1 | Security staff |  |  | 9.2.4.1 | 4 | 0 | N/A | NOT APPLICABLE
9 |  | 2 |  | 4 |  | 2 | Security equipment |  |  | 9.2.4.2 | 4 | 0 | Security equipment | 14 – Management & Operations
9 |  | 2 |  | 4 |  | 3 | Hoardings fences and gates |  |  | 9.2.4.3 | 4 | 0 | Hoardings fences and gates | 14 – Management & Operations
9 |  | 2 |  | 5 | Safety and environmental protection | 1 | Safety performance |  |  | 9.2.5.1 | 4 | 0 | Safety performance | 14 – Management & Operations
9 |  | 2 |  | 5 |  | 2 | Barriers and safety scaffolding |  |  | 9.2.5.2 | 4 | 0 | Barriers and safety scaffolding | 14 – Management & Operations
9 |  | 2 |  | 5 |  | 3 | Environmental protection measures |  |  | 9.2.5.3 | 4 | 0 | Environmental protection measures | 14 – Management & Operations
9 |  | 2 |  | 6 | Control and protection | 1 | Surveys inspections and monitoring |  |  | 9.2.6.1 | 4 | 0 | Surveys inspections and monitoring | 14 – Management & Operations
9 |  | 2 |  | 6 |  | 2 | Setting out |  |  | 9.2.6.2 | 4 | 0 | Setting out | 14 – Management & Operations
9 |  | 2 |  | 6 |  | 3 | Protection of works |  |  | 9.2.6.3 | 4 | 0 | Protection of works | 14 – Management & Operations
9 |  | 2 |  | 6 |  | 4 | Samples |  |  | 9.2.6.4 | 4 | 0 | Samples | 14 – Management & Operations
9 |  | 2 |  | 6 |  | 5 | Environmental control of building |  |  | 9.2.6.5 | 4 | 0 | Environmental control of building | 14 – Management & Operations
9 |  | 2 |  | 7 | Mechanical plant | 1 | Generally |  |  | 9.2.7.1 | 4 | 0 | Generally | 14 – Management & Operations
9 |  | 2 |  | 7 |  | 2 | Tower cranes |  |  | 9.2.7.2 | 4 | 0 | Tower cranes | 14 – Management & Operations
9 |  | 2 |  | 7 |  | 3 | Mobile cranes |  |  | 9.2.7.3 | 4 | 0 | Mobile cranes | 14 – Management & Operations
9 |  | 2 |  | 7 |  | 4 | Hoists |  |  | 9.2.7.4 | 4 | 0 | Hoists | 14 – Management & Operations
9 |  | 2 |  | 7 |  | 5 | Access plant |  |  | 9.2.7.5 | 4 | 0 | Access plant | 14 – Management & Operations
9 |  | 2 |  | 7 |  | 6 | Concrete plant |  |  | 9.2.7.6 | 4 | 0 | Concrete plant | 14 – Management & Operations
9 |  | 2 |  | 7 |  | 7 | Other plant |  |  | 9.2.7.7 | 4 | 0 | Other plant | 14 – Management & Operations
9 |  | 2 |  | 8 | Temporary works – INCLUDED WITH WORK ITEMS | 1 | Access scaffolding | T/E |  | 9.2.8.1 | 4 | 0 | Taken elsewhere with work item | NOT APPLICABLE
9 |  | 2 |  | 8 |  | 2 | Temporary works |  |  | 9.2.8.2 | 4 | 0 | Temporary works | 14 – Management & Operations
9 |  | 2 |  | 9 | Site records | 1 | Maintenance works |  |  | 9.2.9.1 | 4 | 0 | Maintenance works | 14 – Management & Operations
9 |  | 2 |  | 9 |  | 22 | Web based facilities management systems |  |  | 9.2.9.22 | 4 | 0 | Web based facilities management systems | 14 – Management & Operations
9 |  | 2 |  | 10 | Transition and exit requirements | 1 | Testing and commissioning plan |  |  | 9.2.10.1 | 4 | 0 | Testing and commissioning plan | 14 – Management & Operations
9 |  | 2 |  | 10 |  | 2 | Handover |  |  | 9.2.10.2 | 4 | 0 | Handover | 14 – Management & Operations
9 |  | 2 |  | 10 |  | 3 | Post completion services (hand back) |  |  | 9.2.10.3 | 4 | 0 | Post completion services (hand back) | 14 – Management & Operations
9 |  | 2 |  | 11 | Cleaning | 1 | Site tidy |  |  | 9.2.11.1 | 4 | 0 | Site tidy | 14 – Management & Operations
9 |  | 2 |  | 11 |  | 2 | Maintenance of roads, paths and paving |  |  | 9.2.11.2 | 4 | 0 | Maintenance of roads, paths and paving | 14 – Management & Operations
9 |  | 2 |  | 12 | Fees and charges | 1 | Fees |  |  | 9.2.12.1 | 4 | 0 | Fees | 14 – Management & Operations
9 |  | 2 |  | 12 |  | 2 | Charges |  |  | 9.2.12.2 | 4 | 0 | Charges | 14 – Management & Operations
9 |  | 2 |  | 13 | Site services | 1 | Temporary works |  |  | 9.2.13.1 | 4 | 0 | Temporary works | 14 – Management & Operations
9 |  | 2 |  | 13 |  | 2 | Multi service gang |  |  | 9.2.13.2 | 4 | 0 | Multi service gang | 14 – Management & Operations
9 |  | 2 |  | 14 | Insurance, bonds, guarantees and warranties | 1 | Works insurances | 1 | Contractor’s all risks (CAR) insurance | 9.2.14.1.1 | 4 | 0 | Contractor’s all risks (CAR) insurance | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 1 |  | 2 | Contractor’s plant and equipment insurance | 9.2.14.1.2 | 4 | 0 | Contractor’s plant and equipment insurance | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 1 |  | 3 | Temporary buildings insurance | 9.2.14.1.3 | 4 | 0 | Temporary buildings insurance | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 1 |  | 4 | Terrorism insurance | 9.2.14.1.4 | 4 | 0 | Terrorism insurance | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 1 |  | 5 | Other insurances in connection with the works | 9.2.14.1.5 | 4 | 0 | Other insurances in connection with the works | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 1 |  | 6 | Insurance premium tax (IPT) | 9.2.14.1.6 |  |  | Insurance premium tax (IPT) | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 1 |  | 7 | Allowance for recovery of all or part of insurance premium excess | 9.2.14.1.7 |  |  | Allowance for recovery of all or part of insurance premium excess | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 2 | Public liability insurances | 1 | Non-negligence insurance | 9.2.14.2.1 |  |  | Non-negligence insurance | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 2 |  | 2 | Professional indemnity insurance | 9.2.14.2.2 |  |  | Professional indemnity insurance | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 2 |  | 3 | Insurance premium tax (IPT) | 9.2.14.2.3 |  |  | Insurance premium tax (IPT) | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 2 |  | 4 | Allowance for recovery of all or part of insurance premium excess | 9.2.14.2.4 |  |  | Allowance for recovery of all or part of insurance premium excess | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 3 | Inspections | 1 | Statutory compliance inspections | 9.2.14.3.1 |  |  | Refer to section 9.2.15 for specific operational tasks which require inspections | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 3 |  | 2 | Air conditioning inspections (COVID-19) | 9.2.14.3.2 |  |  |  | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 3 |  | 3 | Other forms of inspections (state types) | 9.2.14.3.3 |  |  |  | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 4 | Client’s (main contractor’s) liability insurances | 1 | Management and staff, including administrative staff | 9.2.14.4.1 |  |  | Management and staff, including administrative staff | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 4 |  | 2 | Works operatives | 9.2.14.4.2 |  |  | Works operatives | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 4 |  | 3 | Insurance premium tax (IPT) | 9.2.14.4.3 |  |  | Insurance premium tax (IPT) | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 4 |  | 4 | Allowance for recovery of all or part of insurance premium excess | 9.2.14.4.4 |  |  | Allowance for recovery of all or part of insurance premium excess | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 5 | Other insurances | 1 | Client’s loss of liquidated damages | 9.2.14.5.1 |  |  | Client’s loss of liquidated damages | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 5 |  | 2 | Latent defects cover | 9.2.14.5.2 |  |  | Latent defects cover | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 5 |  | 3 | Motor vehicles | 9.2.14.5.3 |  |  | Motor vehicles | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 5 |  | 4 | Other insurances | 9.2.14.5.4 |  |  | Other insurances | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 5 |  | 5 | Insurance premium tax (IPT) | 9.2.14.5.5 |  |  | Insurance premium tax (IPT) | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 5 |  | 6 | Allowance for recovery of all or part of insurance premium excess | 9.2.14.5.6 |  |  | Allowance for recovery of all or part of insurance premium excess | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 6 | Bonds | 1 | May be included in group element 12 | 9.2.14.6.1 |  |  | Bonds are not part of NRM 3 | NOT APPLICABLE
9 |  | 2 |  | 14 |  | 7 | Guarantees | 1 | Parent company guarantees | 9.2.14.7.1 |  |  | Parent company guarantees | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 7 |  | 2 | Product guarantees (insurance backed) | 9.2.14.7.2 |  |  | Product guarantees (insurance backed) | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 8 | Warranties | 1 | Collateral warranties | 9.2.14.8.1 |  |  | Collateral warranties | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 8 |  | 2 | Funder’s warranties | 9.2.14.8.2 |  |  | Funder’s warranties | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 8 |  | 3 | Purchaser’s and tenant’s warranties | 9.2.14.8.3 |  |  | Purchaser’s and tenant’s warranties | 14 – Management & Operations
9 |  | 2 |  | 14 |  | 8 |  | 4 | Other warranties | 9.2.14.8.4 |  |  | Other warranties | 14 – Management & Operations
9 |  | 2 |  | 15 | Operational Tasks | 1 | Operational tasks specific to maintenance | 1 | Asbestos register | 9.2.15.1.1 |  |  | Asbestos register | 14 – Management & Operations | 87-01
9 |  | 2 |  | 15 |  | 1 |  | 2 | Emergency and panic escape doors and fire exits | 9.2.15.1.2 |  |  | Emergency and panic escape doors and fire exits | 14 – Management & Operations | 87-02
9 |  | 2 |  | 15 |  | 1 |  | 3 | Emergency lighting – power supply and maintained fittings inspections | 9.2.15.1.3 |  |  | Emergency lighting – power supply and maintained fittings inspections | 14 – Management & Operations | 87-03 & 87-04
9 |  | 2 |  | 15 |  | 1 |  | 4 | Fire alarm system – daily /weekly inspections | 9.2.15.1.4 |  |  | Fire alarm system – daily /weekly inspections | 14 – Management & Operations
[15 empty] | 87-06 | Fire Blankets | not assigned in 2020
9 |  | 2 |  | 15 |  | 1 |  | 5 | Automatic doors release mechanisms – electronic secure escape doors and fire exits | 9.2.15.1.5 |  |  | Automatic doors release mechanisms – electronic secure escape doors and fire exits | 14 – Management & Operations | 87-07
[15 empty] | 87-35 | Automatic Door Release Mechanisms - Electrically Held Open Fire Doors | not assigned in 2020
9 |  | 2 |  | 15 |  | 1 |  | 6 | Fire evacuation drill | 9.2.15.1.6 |  |  | Fire evacuation drill | 14 – Management & Operations | 87-08
9 |  | 2 |  | 15 |  | 1 |  | 7 | Fire exit signage | 9.2.15.1.7 |  |  | Fire exit signage | 14 – Management & Operations | 87-09
9 |  | 2 |  | 15 |  | 1 |  | 8 | Fire hydrant – weekly checks | 9.2.15.1.8 |  |  | Fire hydrant – weekly checks | 14 – Management & Operations | NO | Fire Hydrants is not an Operational schedule | Incorrect
9 |  | 2 |  | 15 |  | 1 |  | 9 | Hose reels – daily, monthly and annual checks | 9.2.15.1.9 |  |  | Hose reels – daily, monthly and annual checks | 14 – Management & Operations | 87-12
9 |  | 2 |  | 15 |  | 1 |  | 10 | Insurance periodic inspections | 9.2.15.1.10 |  |  | Insurance periodic inspections | 14 – Management & Operations | 87-13
9 |  | 2 |  | 15 |  | 1 |  | 11 | Independent water risk assessment (legionella) | 9.2.15.1.11 |  |  | Independent water risk assessment (legionella) | 14 – Management & Operations | 87-28
9 |  | 2 |  | 15 |  | 1 |  | 12 | Meter reading (electric, gas, oil and water) | 9.2.15.1.12 |  |  | Meter reading (electric, gas, oil and water) | 14 – Management & Operations | 87-14, 87-15, 87-16, 87-17 & 87-37 | Addition of 87-37 Meter Reading - Heat | 87-37 not assigned in 2020
9 |  | 2 |  | 15 |  | 1 |  | 13 | Oil storage tanks – above ground | 9.2.15.1.13 |  |  | Oil storage tanks – above ground | 14 – Management & Operations | 87-18
9 |  | 2 |  | 15 |  | 1 |  | 14 | Plant room checks | 9.2.15.1.14 |  |  | Plant room checks | 14 – Management & Operations | 87-19
9 |  | 2 |  | 15 |  | 1 |  | 15 | Portable appliance testing . PAT user checks | 9.2.15.1.15 |  |  | Portable appliance testing . PAT user checks | 14 – Management & Operations | 87-20 | In-Service Inspection and Testing of Electrical Equipment - User Checks | PAT Testing is now known as In-Service Inspection and Testing
9 |  | 2 |  | 15 |  | 1 |  | 16 | Portable fire extinguishers – weekly checks | 9.2.15.1.16 |  |  | Portable fire extinguishers – weekly checks | 14 – Management & Operations | 87-21
9 |  | 2 |  | 15 |  | 1 |  | 17 | Smoke control systems – daily 3 monthly and annual checks | 9.2.15.1.17 |  |  | Smoke control systems – daily 3 monthly and annual checks | 14 – Management & Operations | 87-22
9 |  | 2 |  | 15 |  | 1 |  | 18 | Sprinkler systems – inspections | 9.2.15.1.18 |  |  | Sprinkler systems – inspections | 14 – Management & Operations | 87-23
[15 empty] | 87-24 | Steam Boilers - Daily and Weekly Checks and Tests | not assigned in 2020
9 |  | 2 |  | 15 |  | 1 |  | 19 | Visual inspections of voids, cavities & the like | 9.2.15.1.19 |  |  | Visual inspections of voids, cavities & the like | 14 – Management & Operations | 87-25
9 |  | 2 |  | 15 |  | 1 |  | 20 | Water risk assessment (legionella) | 9.2.15.1.20 |  |  | Water risk assessment (legionella) | 14 – Management & Operations | 87-26
9 |  | 2 |  | 15 |  | 1 |  | 21 | Water sampling and testing – closed systems | 9.2.15.1.21 |  |  | Water sampling and testing – closed systems | 14 – Management & Operations | 87-27
9 |  | 2 |  | 15 |  | 1 |  | 22 | Other operational tasks (type to be stated) | 9.2.15.1.22 |  |  | Other operational tasks (type to be stated) | 14 – Management & Operations
[15 empty] | 87-29 | Air Conditioning Inspection (ACI) also known as TM44 Inspection - England, Wales and NI | not assigned in 2020
[15 empty] | 87-30 | Air Conditioning Inspection (ACI) also known as TM44 Inspection - Scotland | not assigned in 2020
[15 empty] | 87-31 | Display Energy Certificates (DEC's) - England and Wales | not assigned in 2020
[15 empty] | 87-32 | Energy Performance Certificates (EPC's) | not assigned in 2020
[15 empty] | 87-33 | Bird Excrement and Associated Material Removal | not assigned in 2020
[15 empty] | 87-34 | Compressed Gas Cylinders (External Storage) | not assigned in 2020
[15 empty] | 87-36 | Air Compressors and Receivers - Operational Checks | not assigned in 2020
9 |  | 2 |  | 16 | Periodic maintenance | 1 | Periodic maintenance tasks | 1 | Ducting – volume control dampers (5 yearly) | 9.2.16.1.1 |  |  | Ducting – volume control dampers (5 yearly) | 14 – Management & Operations
9 |  | 2 |  | 16 |  | 1 |  | 2 | Electrical Fixed wiring testing (2 to 5 yearly) | 9.2.16.1.2 |  |  | Electrical Fixed wiring testing (2 to 5 yearly) | 14 – Management & Operations
9 |  | 2 |  | 16 |  | 1 |  | 3 | Hose reels – static and swinging (5 yearly) | 9.2.16.1.3 |  |  | Hose reels – static and swinging (5 yearly) | 14 – Management & Operations
9 |  | 2 |  | 16 |  | 1 |  | 4 | Main switch panel at supply intake (2 yearly) | 9.2.16.1.4 |  |  | Main switch panel at supply intake (2 yearly) | 14 – Management & Operations
9 |  | 2 |  | 16 |  | 1 |  | 5 | Portable appliance testing – (2 yearly) | 9.2.16.1.5 |  |  | Portable appliance testing – (2 yearly) | 14 – Management & Operations
9 |  | 2 |  | 16 |  | 1 |  | 6 | Sprinkler systems (3 yearly, 5 yearly etc) | 9.2.16.1.6 |  |  | Sprinkler systems (3 yearly, 5 yearly etc) | 14 – Management & Operations
9 |  | 2 |  | 16 |  | 1 |  | 7 | Suspended façade access equipment (10 yearly) | 9.2.16.1.7 |  |  | Suspended façade access equipment (10 yearly) | 14 – Management & Operations
9 |  | 2 |  | 16 |  | 1 |  | 8 | Insurance periodic inspections (2 yearly) | 9.2.16.1.8 |  |  | Insurance periodic inspections (2 yearly) | 14 – Management & Operations
9 |  | 2 |  | 16 |  | 1 |  | 9 | Vertical platform lifts (2 yearly) | 9.2.16.1.9 |  |  | Vertical platform lifts (2 yearly) | 14 – Management & Operations
9 |  | 2 |  | 16 |  | 1 |  | 10 | Other periodic maintenance tasks (to be stated) | 9.2.16.1.10 |  |  | Other periodic maintenance tasks (to be stated) | 14 – Management & Operations
9 |  | 2 |  | 16 |  | 2 | Redecorations programme | 1 | External walls – depending on finishes type | 9.2.16.2.1 |  |  | External walls – depending on finishes type | 15 – Redecorations
9 |  | 2 |  | 16 |  | 2 |  | 2 | External windows and doors – timber or like | 9.2.16.2.2 |  |  | External windows and doors – timber or like | 15 – Redecorations
9 |  | 2 |  | 16 |  | 2 |  | 3 | Internal walls, including skirtings | 9.2.16.2.3 |  |  | Internal walls, including skirtings | 15 – Redecorations
9 |  | 2 |  | 16 |  | 2 |  | 4 | Internal ceilings | 9.2.16.2.4 |  |  | Internal ceilings | 15 – Redecorations
9 |  | 2 |  | 16 |  | 2 |  | 5 | Internal windows and doors | 9.2.16.2.5 |  |  | Internal windows and doors | 15 – Redecorations
10 | Maintenance contractor's overhead and profit | 1 | Maintenance contractor's overhead | 1 | Maintenance contractor's overhead | 1 | Maintenance contractor's overhead |  |  | 10.1.1.1 | 4 | 0 | Maintenance contractors overhead | 16 – Overheads, Fees and Other Contract Costs
10 |  | 2 | Maintenance contractor's profit | 2 | Maintenance contractor's profit | 1 | Maintenance contractor's profit |  |  | 10.2.2.1 | 4 | 0 | Project team and design team consultants and other specialist fees | 16 – Overheads, Fees and Other Contract Costs
11 | Consultant and specialist fees | 1 | Consultant's and specialist fees | 1 | Consultant's and specialist fees | 1 | Consultant's and specialist fees |  |  | 11.1.1.1 | 4 | 0 | Consultant's and specialist fees | 16 – Overheads, Fees and Other Contract Costs
11 |  | 1 |  | 2 | Other consultant's fees | 1 | Other consultant's fees |  |  | 11.1.2.1 | 4 | 0 | Other consultant's fees | 16 – Overheads, Fees and Other Contract Costs
11 |  | 1 |  | 3 | Site investigation fees | 1 | Site investigation fees |  |  | 11.1.3.1 | 4 | 0 | Site investigation fees | 16 – Overheads, Fees and Other Contract Costs
11 |  | 1 |  | 4 | Specialist support consultant's fees | 1 | Specialist support consultants fees |  |  | 11.1.4.1 | 4 | 0 | Specialist support consultants fees | 16 – Overheads, Fees and Other Contract Costs
11 |  | 2 | Maintenance contractor's tender / pre-contract fees | 1 | Management and staff | 1 | Management and staff |  |  | 11.2.1.1 | 4 | 0 | Management and staff | 16 – Overheads, Fees and Other Contract Costs
11 |  | 2 |  | 2 | Specialist support services fees | 1 | Specialist support services fees |  |  | 11.2.2.1 | 4 | 0 | Specialist support services fees | 16 – Overheads, Fees and Other Contract Costs
11 |  | 2 |  | 3 | Temporary accommodation, services and facilities charges | 1 | Temporary accommodation, services and facilities charges |  |  | 11.2.3.1 | 4 | 0 | Temporary accommodation, services and facilities charges | 16 – Overheads, Fees and Other Contract Costs
11 |  | 2 |  | 4 | Main contractor's overhead and profit | 1 | Maintenance contractors overhead and profit |  |  | 11.2.4.1 | 4 | 0 | Maintenance contractors overhead and profit | 16 – Overheads, Fees and Other Contract Costs
11 |  | 3 | Maintenance contractor's design fees | 1 | Main contractor's design consultant's fees | 1 | Maintenance contractors design consultant's fees |  |  | 11.3.1.1 | 4 | 0 | Maintenance contractors design consultant's fees | 16 – Overheads, Fees and Other Contract Costs
12 | Employer definable maintenance related costs | 1 | Employer definable maintenance related costs | 1 | Land acquisition costs | 1 | Land acquisition costs |  |  | 12.1.1.1 | 4 | 0 | Land acquisition costs | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 2 | Employer finance costs | 1 | Employer finance costs |  |  | 12.1.2.1 | 4 | 0 | Employer finance costs | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 3 | Fees | 1 | Fees |  |  | 12.1.3.1 | 4 | 0 | Fees | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 4 | Charges | 1 | Charges |  |  | 12.1.4.1 | 4 | 0 | Charges | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 5 | Planning contributions | N/A | Not covered by NRM 3 |  |  | 12.1.5 | 3 | 0 | Not covered by NRM 3 | NOT APPLICABLE
12 |  | 1 |  | 6 | Insurances | 1 | Insurances |  |  | 12.1.6.1 | 4 | 0 | Insurances | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 7 | Archaeological field work | 1 | Archaeological field work |  |  | 12.1.7.1 | 4 | 0 | Archaeological field work | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 8 | Other specialist fieldwork | 1 | Other specialist fieldwork |  |  | 12.1.8.1 | 4 | 0 | Other specialist fieldwork | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 9 | Decanting and relocation costs | 1 | Decanting and relocation costs |  |  | 12.1.9.1 | 4 | 0 | Decanting and relocation costs | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 10 | Fittings, furnishings and equipment | 1 | Fittings, furnishings and equipment |  |  | 12.1.10.1 | 4 | 0 | Fittings, furnishings and equipment | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 11 | Tenant's costs/contributions | 1 | Tenant's costs/ contributions |  |  | 12.1.11.1 | 4 | 0 | Tenant's costs/ contributions | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 12 | Marketing costs | 1 | Marketing costs |  |  | 12.1.12.1 | 4 | 0 | Marketing costs | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 13 | Other employer costs | 1 | Other employer costs |  |  | 12.1.13.1 | 4 | 0 | Other employer costs | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 14 | Allowances | 1 | Allowances |  |  | 12.1.14.1 | 4 | 0 | Allowances | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 15 | Energy efficiency | 1 | Energy efficiency |  |  | 12.1.15.1 | 4 | 0 | Energy efficiency | 16 – Overheads, Fees and Other Contract Costs
12 |  | 1 |  | 16 | Office churn | N/A | Not covered by NRM 3 |  |  | 12.1.16 | 3 | 0 | Not covered by NRM 3 | NOT APPLICABLE
12 |  | 1 |  | 17 | Soft services – operations | N/A | Not covered by NRM 3 |  |  | 12.1.17 | 3 | 0 | Not covered by NRM 3 | NOT APPLICABLE
12 |  | 1 |  | 18 | End of life | N/A | Taken elsewhere |  |  | 12.1.18 | 3 | 0 | Taken elsewhere | NOT APPLICABLE
12 |  | 1 |  | 19 | Third party income | N/A | Not covered by NRM 3 |  |  | 12.1.19 | 3 | 0 | Not covered by NRM 3 | NOT APPLICABLE
12 |  | 1 |  | 20 | Loss of income | N/A | Not covered by NRM 3 |  |  | 12.1.20 | 3 | 0 | Not covered by NRM 3 | NOT APPLICABLE
13 | Risks | 1 | Design and installation risks | 1 |  | 1 | Design development and standards |  |  | 13.1.1.1 | 4 | 0 | Design development and standards | 17 – Risks and Inflation
13 |  | 1 |  | 1 |  | 2 | Construction installation legacy risks |  |  | 13.1.1.2 | 4 | 0 | Construction installation legacy risks | 17 – Risks and Inflation
13 |  | 1 |  | 1 |  | 3 | Handover |  |  | 13.1.1.3 | 4 | 0 | Handover | 17 – Risks and Inflation
13 |  | 1 |  | 1 |  | 4 | Legislation and changing future regulations, e.g. Health & Safety at work |  |  | 13.1.1.4 | 4 | 0 | Legislation and changing future regulations, e.g. Health & Safety at work | 17 – Risks and Inflation
13 |  | 2 | Maintenance risks | 2 |  | 1 | Procurement |  |  | 13.2.2.1 | 4 | 0 | Procurement | 17 – Risks and Inflation
13 |  | 2 |  | 2 |  | 2 | Maintenance delivery |  |  | 13.2.2.2 | 4 | 0 | Maintenance delivery | 17 – Risks and Inflation
13 |  | 2 |  | 2 |  | 3 | Life cycle replacement works |  |  | 13.2.2.3 | 4 | 0 | Life cycle replacement works | 17 – Risks and Inflation
13 |  | 3 | Employer change risks | 3 |  | 1 | Project brief |  |  | 13.3.3.1 | 4 | 0 | Project brief | 17 – Risks and Inflation
13 |  | 3 |  | 3 |  | 2 | Scope creep |  |  | 13.3.3.2 | 4 | 0 | Scope creep | 17 – Risks and Inflation
13 |  | 3 |  | 3 |  | 3 | System redundancy |  |  | 13.3.3.3 | 4 | 0 | System redundancy | 17 – Risks and Inflation
13 |  | 3 |  | 3 |  | 4 | Timescales |  |  | 13.3.3.4 | 4 | 0 | Timescales | 17 – Risks and Inflation
13 |  | 4 | Employer other risks | 4 |  | 1 | Maintenance brief |  |  | 13.4.4.1 | 4 | 0 | Maintenance brief | 17 – Risks and Inflation
13 |  | 4 |  | 4 |  | 2 | Timescales |  |  | 13.4.4.2 | 4 | 0 | Timescales | 17 – Risks and Inflation
13 |  | 4 |  | 4 |  | 3 | Third party |  |  | 13.4.4.3 | 4 | 0 | Third party | 17 – Risks and Inflation
13 |  | 4 |  | 4 |  | 4 | Management |  |  | 13.4.4.4 | 4 | 0 | Management | 17 – Risks and Inflation
14 | Inflation | 1 | Tender inflation | [6 empty] | 14.1 | 2 | 0 | Tender inflation | 17 – Risks and Inflation
14 |  | 2 | Construction inflation | [6 empty] | 14.2 | 2 | 0 | Construction inflation | 17 – Risks and Inflation
14 |  | 3 | Life cycle renewal inflation | [6 empty] | 14.3 | 2 | 0 | Life cycle renewal inflation | 17 – Risks and Inflation
14 |  | 4 | Life cycle discount rate | [6 empty] | 14.4 | 2 | 0 | Life cycle discount rate | 17 – Risks and Inflation

## 4. NRM3 Logic&Levels Table 2026
| RICS NRM 3 Logic and Level Table (Released January 2026) | [7 empty] | No responsibility for loss or damage caused to any person through the use of this template can be accepted by the authors or RICS.
NRM 3 Aligned Data Standards Version (Frozen date End December 2025)
| 1 |  | 2 |  | 3 |  | 4 |  | 5 | 6 | 7 |  | 8 | 9
| NRM3 Code | L1 | Group Element | L2 | Element (or Systems) | L3 | Sub Element or (System or Sub Systems) | M | Maintainable Asset Description | UoM Renewal | UoM Maintenance | P | Product or Material Type | Work Package (Examples)
1 | 0 | 0 | Facilitating works
2 | 0.1 |  |  | 1 | Toxic/Hazardous/Contaminated Material Treatment
3 | 0.1.1 |  |  |  |  | 1 | Toxic or hazardous material removal |  |  | Item | N/A |  |  | T16 – Specialist
3 | 0.1.2 |  |  |  |  | 2 | Contaminated land |  |  | N/A | N/A
3 | 0.1.3 |  |  |  |  | 3 | Eradication of plant growth |  |  | m²/m3 | N/A |  |  | T16 – Specialist
2 | 0.2 |  |  | 2 | Major demolition works
3 | 0.2.1 |  |  |  |  | 1 | Demolition works |  |  | Excluded | Excluded
3 | 0.2.2 |  |  |  |  | 2 | Soft strip works |  |  | Excluded | Excluded
2 | 0.3 |  |  | 3 | Temporary support to adjacent structures
3 | 0.3.1 |  |  |  |  | 1 | Temporary support to adjacent structures |  |  | Excluded | Excluded
2 | 0.4 |  |  | 4 | Specialist groundworks
3 | 0.4.1 |  |  |  |  | 1 | Site dewatering and pumping
4 | 0.4.1.1 | [6 empty] | 1 | Pumps
5 | 0.4.1.1.X | [8 empty] | Excluded | Excluded | X | See SUP - Pumps | T16 – Specialist
3 | 0.4.2 |  |  |  |  | 2 | Soil stabilisation measures |  |  | Excluded | Excluded
3 | 0.4.3 |  |  |  |  | 3 | Ground gas venting measures
4 | 0.4.3.1 | [6 empty] | 1 | Ground gas venting measures | m² | m² |  |  | T16 – Specialist
2 | 0.5 |  |  | 5 | Temporary diversion works
3 | 0.5.1 |  |  |  |  | 1 | Temporary diversion to drains |  |  | N/A | N/A
3 | 0.5.2 |  |  |  |  | 2 | Temporary diversion to services |  |  | N/A | N/A
3 | 0.5.3 |  |  |  |  | 3 | Temporary diversion of waterways |  |  | N/A | N/A
2 | 0.6 |  |  | 6 | Extraordinary site investigation works
3 | 0.6.1 |  |  |  |  | 1 | Archaeological investigation |  |  | Excluded | Excluded
3 | 0.6.2 |  |  |  |  | 2 | Reptile/wildlife mitigation measures |  |  | Excluded | Excluded
3 | 0.6.3 |  |  |  |  | 3 | Other extraordinary site investigation works |  |  | Excluded | Excluded
1 | 1 | 1 | Substructure
2 | 1.1 |  |  | 1 | Substructure
3 | 1.1.1 |  |  |  |  | 1 | Standard foundations
4 | 1.1.1.1 | [6 empty] | 1 | Damp proofing courses | m | m² |  |  | T16 – Specialist
3 | 1.1.2 |  |  |  |  | 2 | Specialist foundations |  |  | N/A | N/A
3 | 1.1.3 |  |  |  |  | 3 | Lowest floor construction
4 | 1.1.3.1 | [6 empty] | 1 | Gullies, Floor outlets | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 1.1.3.2 | [6 empty] | 2 | Prefabricated floor channels | m | m |  |  | T7 – Sanitary and Plumbing Services
4 | 1.1.3.3 | [6 empty] | 3 | Internal manholes | nr | nr |  |  | T7 – Sanitary and Plumbing Services
3 | 1.1.4 |  |  |  |  | 4 | Basement excavation |  |  | N/A | N/A
3 | 1.1.5 |  |  |  |  | 5 | Basement retaining walls |  |  | N/A | N/A
1 | 2 | 2 | Superstructure
2 | 2.1 |  |  | 1 | Frame
3 | 2.1.1 |  |  |  |  | 1 | Steel frames
4 | 2.1.1.1 | [6 empty] | 1 | Fire protective coating | m² | m² |  |  | T16 – Specialist
3 | 2.1.2 |  |  |  |  | 2 | Space frames / decks
4 | 2.1.2.1 | [6 empty] | 1 | Fire protective coating | m²/nr | m² |  |  | T16 – Specialist
3 | 2.1.3 |  |  |  |  | 3 | Concrete casings to steel frames |  |  | N/A | N/A
3 | 2.1.4 |  |  |  |  | 4 | Concrete frames |  |  | N/A | N/A
3 | 2.1.5 |  |  |  |  | 5 | Timber frames
4 | 2.1.5.1 | [6 empty] | 1 | Timber treatment | m²/nr | m² |  |  | T16 – Specialist
4 | 2.1.5.2 | [6 empty] | 2 | Fire protective coating | m²/nr | m² |  |  | T16 – Specialist
3 | 2.1.6 |  |  |  |  | 6 | Specialist frames |  |  | N/A | N/A
2 | 2.2 |  |  | 2 | Upper floors
3 | 2.2.1 |  |  |  |  | 1 | Floors |  |  | N/A | N/A
3 | 2.2.2 |  |  |  |  | 2 | Balconies |  |  | N/A | N/A
3 | 2.2.3 |  |  |  |  | 3 | Drainage to balconies
4 | 2.2.3.1 | [6 empty] | 1 | Rainwater drainage | m/nr | m/nr |  |  | T7 – Sanitary and Plumbing Services
2 | 2.3 |  |  | 3 | Roof
3 | 2.3.1 |  |  |  |  | 1 | Roof structure
4 | 2.3.1.1 | [6 empty] | 1 | Timber pitched roof structure | m²/nr | m² |  |  | T1 - Building Structure
4 | 2.3.1.2 | [6 empty] | 2 | Steel pitched roof structure | m²/nr | m² |  |  | T1 - Building Structure
4 | 2.3.1.3 | [6 empty] | 3 | Concrete flat roof structure | m²/nr | m² |  |  | T1 - Building Structure
4 | 2.3.1.4 | [6 empty] | 4 | Timber flat roof structure | m²/nr | m² |  |  | T1 - Building Structure
4 | 2.3.1.5 | [6 empty] | 5 | Steel flat roof structure | m²/nr | m² |  |  | T1 - Building Structure
3 | 2.3.2 |  |  |  |  | 2 | Roof coverings
4 | 2.3.2.1 | [6 empty] | 1 | Pitched roof covering
5 | 2.3.2.1.1 | [8 empty] | m²/nr | m² | 1 | Ceramic Tile | T2 - Roofing
5 | 2.3.2.1.2 | [8 empty] | m²/nr | m² | 2 | Clay Tile | T2 - Roofing
5 | 2.3.2.1.3 | [8 empty] | m²/nr | m² | 3 | Concrete (Un-Finished) | T2 - Roofing
5 | 2.3.2.1.4 | [8 empty] | m²/nr | m² | 4 | Concrete Tile | T2 - Roofing
5 | 2.3.2.1.5 | [8 empty] | m²/nr | m² | 5 | Copper | T2 - Roofing
5 | 2.3.2.1.6 | [8 empty] | m²/nr | m² | 6 | Glazed Panel | T2 - Roofing
5 | 2.3.2.1.7 | [8 empty] | m²/nr | m² | 7 | Kalzip | T2 - Roofing
5 | 2.3.2.1.8 | [8 empty] | m²/nr | m² | 8 | Lead | T2 - Roofing
5 | 2.3.2.1.9 | [8 empty] | m²/nr | m² | 9 | Slate Tile | T2 - Roofing
5 | 2.3.2.1.10 | [8 empty] | m²/nr | m² | 10 | Metal Cladding (Built Up) | T2 - Roofing
5 | 2.3.2.1.11 | [8 empty] | m²/nr | m² | 11 | Metal Cladding (Composite) | T2 - Roofing
5 | 2.3.2.1.12 | [8 empty] | m²/nr | m² | 12 | Metal Cladding (Profiled) | T2 - Roofing
5 | 2.3.2.1.13 | [8 empty] | m²/nr | m² | 13 | Plastisol Coated Steel Profiled Sheet | T2 - Roofing
5 | 2.3.2.1.14 | [8 empty] | m²/nr | m² | 14 | Steel Sheet | T2 - Roofing
4 | 2.3.2.2 | [6 empty] | 2 | Flat roof covering
5 | 2.3.2.2.1 | [8 empty] | m²/nr | m² | 1 | Asbestos | T2 - Roofing
5 | 2.3.2.2.2 | [8 empty] | m²/nr | m² | 2 | Asphalt | T2 - Roofing
5 | 2.3.2.2.3 | [8 empty] | m²/nr | m² | 3 | Bitumen | T2 - Roofing
5 | 2.3.2.2.4 | [8 empty] | m²/nr | m² | 4 | Felt | T2 - Roofing
5 | 2.3.2.2.5 | [8 empty] | m²/nr | m² | 5 | Felt (Built Up) | T2 - Roofing
5 | 2.3.2.2.6 | [8 empty] | m²/nr | m² | 6 | Glazed Panel | T2 - Roofing
5 | 2.3.2.2.7 | [8 empty] | m²/nr | m² | 7 | Kalzip | T2 - Roofing
5 | 2.3.2.2.8 | [8 empty] | m²/nr | m² | 8 | Lead | T2 - Roofing
5 | 2.3.2.2.9 | [8 empty] | m²/nr | m² | 9 | Liquid Applied Coating System | T2 - Roofing
5 | 2.3.2.2.10 | [8 empty] | m²/nr | m² | 10 | Metal Cladding (Built Up) | T2 - Roofing
5 | 2.3.2.2.11 | [8 empty] | m²/nr | m² | 11 | Metal Cladding (Composite) | T2 - Roofing
5 | 2.3.2.2.12 | [8 empty] | m²/nr | m² | 12 | Metal Cladding (Profiled) | T2 - Roofing
5 | 2.3.2.2.13 | [8 empty] | m²/nr | m² | 13 | Single Membrane | T2 - Roofing
5 | 2.3.2.2.14 | [8 empty] | m²/nr | m² | 14 | Ethylene Tetrafluoroethylene (ETFE) Roof - Cushion | T2 - Roofing
5 | 2.3.2.2.15 | [8 empty] | m²/nr | m² | 15 | Ethylene Tetrafluoroethylene (ETFE) Roof - Single Layer | T2 - Roofing
4 | 2.3.2.3 | [6 empty] | 3 | Solar Panels / Photovoltaic (PV)
5 | 2.3.2.3.1 | [8 empty] | m²/nr | nr | 1 | Solar Panels - Photovoltaic (PV) - Energy Storage | T2 - Roofing
5 | 2.3.2.3.2 | [8 empty] | m²/nr | nr | 2 | Photovoltaic (PV) System - Grid Connected | T2 - Roofing
5 | 2.3.2.3.3 | [8 empty] | m²/nr | nr | 3 | Large solar systems - Photovoltaic (PV) - Grid Connected | T2 - Roofing
4 | 2.3.2.4 | [6 empty] | 4 | Thermal Insulation
5 | 2.3.2.4.1 | [8 empty] | m²/nr | m² | 1 | Thermal Insulation - Sheet | T2 - Roofing
4 | 2.3.2.5 | [6 empty] | 5 | Roof paving
5 | 2.3.2.5.1 | [8 empty] | m²/nr | m² | 1 | Pre Cast Concrete Flag | T2 - Roofing
5 | 2.3.2.5.2 | [8 empty] | m²/nr | m² | 2 | Stone roof tiles | T2 - Roofing
4 | 2.3.2.6 | [6 empty] | 6 | Green Roofs and Gardens | m²/nr | m² |  |  | T2 - Roofing
4 | 2.3.2.7 | [6 empty] | 7 | Shingles | m²/nr | m² |  |  | T2 - Roofing
4 | 2.3.2.8 | [6 empty] | 8 | Solar Reflective Paint | m²/nr | m² |  |  | T2 - Roofing
4 | 2.3.2.9 | [6 empty] | 9 | Flashings
5 | 2.3.2.9.1 | [8 empty] | m | m | 1 | Flashings - Flat Roof Coverings | T2 - Roofing
5 | 2.3.2.9.2 | [8 empty] | m | m | 2 | Flashings - Metal | T2 - Roofing
5 | 2.3.2.9.3 | [8 empty] | m | m | 3 | Flashings - Parapet Walls | T2 - Roofing
5 | 2.3.2.9.4 | [8 empty] | m | m | 4 | Flashings - Roof Cladding | T2 - Roofing
3 | 2.3.3 |  |  |  |  | 3 | Specialist roof systems
4 | 2.3.3.1 | [6 empty] | 1 | Patent glazing | m²/nr | m² |  |  | T16 – Specialist
4 | 2.3.3.2 | [6 empty] | 2 | Glazed roofing system | m²/nr | m² |  |  | T16 – Specialist
4 | 2.3.3.3 | [6 empty] | 3 | Perspex roofing system | m²/nr | m² |  |  | T16 – Specialist
3 | 2.3.4 |  |  |  |  | 4 | Roof drainage
4 | 2.3.4.1 | [6 empty] | 1 | Gutters and downpipes
5 | 2.3.4.1.1 | [8 empty] | m/nr | m² | 1 | Aluminium | T7 – Sanitary and Plumbing Services
5 | 2.3.4.1.2 | [8 empty] | m/nr | m² | 2 | Asbestos | T7 – Sanitary and Plumbing Services
5 | 2.3.4.1.3 | [8 empty] | m/nr | m² | 3 | Cast Iron | T7 – Sanitary and Plumbing Services
5 | 2.3.4.1.4 | [8 empty] | m/nr | m² | 4 | Copper | T7 – Sanitary and Plumbing Services
5 | 2.3.4.1.5 | [8 empty] | m/nr | m² | 5 | Masonry | T7 – Sanitary and Plumbing Services
5 | 2.3.4.1.6 | [8 empty] | m/nr | m² | 6 | UPVC | T7 – Sanitary and Plumbing Services
4 | 2.3.4.2 | [6 empty] | 2 | Syphonic roof drainage | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 2.3.4.3 | [6 empty] | 3 | Gullies | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 2.3.4.4 | [6 empty] | 4 | Hoppers | nr | nr |  |  | T7 – Sanitary and Plumbing Services
3 | 2.3.5 |  |  |  |  | 5 | Roof lights, skylights and openings
4 | 2.3.5.1 | [6 empty] | 1 | Roof lights skylights and openings
5 | 2.3.5.1.1 | [8 empty] | nr/m² | nr | 1 | Roof lights skylights and openings Aluminium | T2 - Roofing
5 | 2.3.5.1.2 | [8 empty] | nr/m² | nr | 2 | GRP | T2 - Roofing
5 | 2.3.5.1.3 | [8 empty] | nr/m² | nr | 3 | Polycarbonate | T2 - Roofing
5 | 2.3.5.1.4 | [8 empty] | nr/m² | nr | 4 | Timber | T2 - Roofing
4 | 2.3.5.2 | [6 empty] | 2 | Sun pipes and tubes | nr | nr |  |  | T2 - Roofing
4 | 2.3.5.3 | [6 empty] | 3 | Pavement lights | nr/m² | nr |  |  | T2 - Roofing
4 | 2.3.5.4 | [6 empty] | 4 | Access hatches | nr | nr |  |  | T2 - Roofing
4 | 2.3.5.5 | [6 empty] | 5 | Smoke vents
5 | 2.3.5.5.1 | [8 empty] | nr | nr | 1 | Natural Smoke and Heat Exhaust Ventilators | T2 - Roofing
5 | 2.3.5.5.2 | [8 empty] | nr | nr | 2 | Powered Smoke and Heat Exhaust Ventilators | T2 - Roofing
4 | 2.3.5.6 | [6 empty] | 6 | Roof vents and cowls | nr | nr |  |  | T2 - Roofing
3 | 2.3.6 |  |  |  |  | 6 | Roof features
4 | 2.3.6.1 | [6 empty] | 1 | Turrets | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.2 | [6 empty] | 2 | Wind vanes | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.3 | [6 empty] | 3 | Spires | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.4 | [6 empty] | 4 | False chimneys | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.5 | [6 empty] | 5 | Roof enclosures | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.6 | [6 empty] | 6 | Personal anchor system | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.7 | [6 empty] | 7 | Fall arrest lanyards | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.8 | [6 empty] | 8 | Eyebolts | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.9 | [6 empty] | 9 | Retractable system | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.10 | [6 empty] | 10 | Abseiling connector | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.11 | [6 empty] | 11 | Abseiling eyebolt | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.12 | [6 empty] | 12 | Abseiling personal system | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.13 | [6 empty] | 13 | Fall restraint lanyard | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.14 | [6 empty] | 14 | Roof and Canopy Fall Protection Systems | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.15 | [6 empty] | 15 | Mobile Man Anchors | nr | nr |  |  | T2 - Roofing
4 | 2.3.6.16 | [6 empty] | 16 | Roof edge protection | nr | m |  |  | T2 - Roofing
4 | 2.3.6.17 | [6 empty] | 17 | Balustrading to roof edge | nr | m |  |  | T2 - Roofing
4 | 2.3.6.18 | [6 empty] | 18 | Connectors | nr | nr |  |  | T2 - Roofing
2 | 2.4 |  |  | 4 | Stairs and ramps
3 | 2.4.1 |  |  |  |  | 1 | Stair/ramp structure
4 | 2.4.1.1 | [6 empty] | 1 | Staircases | nr | nr |  |  | T1 - Building Structure
4 | 2.4.1.2 | [6 empty] | 2 | External Fire escapes | nr | nr |  |  | T1 - Building Structure
4 | 2.4.1.3 | [6 empty] | 3 | Access ramps | nr | nr |  |  | T1 - Building Structure
3 | 2.4.2 |  |  |  |  | 2 | Stair/ramp finishes
4 | 2.4.2.1 | [6 empty] | 1 | Stair finishes
5 | 2.4.2.1.1 | [10 empty] | 1 | See SUP - Internal Decoration | T5 - Internal Finishes
5 | 2.4.2.1.2 | [8 empty] | m² | m² | 2 | Stair finishes - external | T5 - Internal Finishes
4 | 2.4.2.2 | [6 empty] | 2 | Ramp finishes | m² | m² |  |  | T5 - Internal Finishes
3 | 2.4.3 |  |  |  |  | 3 | Stair/ramp balustrade and handrails
4 | 2.4.3.1 | [6 empty] | 1 | Balustrades and handrails
5 | 2.4.3.1.1 | [8 empty] | nr | m | 1 | Balustrades and handrails to stairs | T1 - Building Structure
5 | 2.4.3.1.2 | [8 empty] | nr | m | 2 | Balustrades and handrails to landings | T1 - Building Structure
3 | 2.4.4 |  |  |  |  | 4 | Ladders/chutes/slides
4 | 2.4.4.1 | [6 empty] | 1 | Fire escape ladder | nr | nr |  |  | T1 - Building Structure
4 | 2.4.4.2 | [6 empty] | 2 | Access ladders | nr | nr |  |  | T1 - Building Structure
4 | 2.4.4.3 | [6 empty] | 3 | Loft ladders incorporating access hatch | nr | nr |  |  | T1 - Building Structure
4 | 2.4.4.4 | [6 empty] | 4 | Chutes – Fire escape | nr | nr |  |  | T1 - Building Structure
4 | 2.4.4.5 | [6 empty] | 5 | Slides – Fire escape | nr | nr |  |  | T1 - Building Structure
2 | 2.5 |  |  | 5 | External walls
3 | 2.5.1 |  |  |  |  | 1 | External enclosing walls above ground floor level
4 | 2.5.1.1 | [6 empty] | 1 | External enclosing walls
5 | 2.5.1.1.1 | [8 empty] | m²/nr | m² | 1 | Curtain walling | T1 - Building Structure
5 | 2.5.1.1.2 | [8 empty] | m²/nr | m² | 2 | Structural glazing | T1 - Building Structure
5 | 2.5.1.1.3 | [8 empty] | m²/nr | m² | 3 | Profiled steel cladding systems | T1 - Building Structure
4 | 2.5.1.2 | [6 empty] | 2 | Parapet walls, including copings and cappings | m²/nr | m |  |  | T1 - Building Structure
4 | 2.5.1.3 | [6 empty] | 3 | Chimneys | m²/nr | nr |  |  | T1 - Building Structure
4 | 2.5.1.4 | [6 empty] | 4 | Ext Wall Options
5 | 2.5.1.4.1 | [8 empty] | m²/nr | m² | 1 | Curtain walling | T1 - Building Structure
5 | 2.5.1.4.2 | [8 empty] | m²/nr | m² | 2 | Structural glazing | T1 - Building Structure
5 | 2.5.1.4.3 | [8 empty] | m²/nr | m² | 3 | Profiled steel cladding systems | T1 - Building Structure
5 | 2.5.1.4.4 | [8 empty] | m²/nr | m² | 4 | Rigid sheet cladding including framework | T1 - Building Structure
5 | 2.5.1.4.5 | [8 empty] | m²/nr | m² | 5 | Panelled walling systems | T1 - Building Structure
5 | 2.5.1.4.6 | [8 empty] | m²/nr | m² | 6 | Internal skins/backing to walling systems | T1 - Building Structure
5 | 2.5.1.4.7 | [8 empty] | m²/nr | m² | 7 | Concrete walls | T1 - Building Structure
5 | 2.5.1.4.8 | [8 empty] | m²/nr | m² | 8 | Masonry walls | T1 - Building Structure
5 | 2.5.1.4.9 | [8 empty] | m²/nr | m² | 9 | Lightweight steel frame systems | T1 - Building Structure
5 | 2.5.1.4.10 | [8 empty] | m²/nr | m² | 10 | Timber and plastic cladding systems | T1 - Building Structure
5 | 2.5.1.4.11 | [8 empty] | m²/nr | m² | 11 | Insulating render systems | T1 - Building Structure
5 | 2.5.1.4.12 | [8 empty] | m²/nr | m² | 12 | Planted green walls | T1 - Building Structure
4 | 2.5.1.5 | [6 empty] | 5 | Safety barriers
5 | 2.5.1.5.1 | [8 empty] | m | m | 1 | Safety Barriers - Fixed Position | T1 - Building Structure
5 | 2.5.1.5.2 | [8 empty] | m | nr | 2 | Safety Barriers - Moveable Barriers | T1 - Building Structure
5 | 2.5.1.5.3 | [8 empty] | m | m | 3 | Safety Barriers - With Glass Insert | T1 - Building Structure
3 | 2.5.2 |  |  |  |  | 2 | External enclosing walls below ground floor level
4 | 2.5.2.1 | [6 empty] | 1 | External enclosing walls below ground level
5 | 2.5.2.1.1 | [8 empty] | m²/nr | m² | 1 | Profiled steel cladding systems | T1 - Building Structure
5 | 2.5.2.1.2 | [8 empty] | m²/nr | m² | 2 | Rigid sheet cladding including framework | T1 - Building Structure
5 | 2.5.2.1.3 | [8 empty] | m²/nr | m² | 3 | Panelled walling systems | T1 - Building Structure
5 | 2.5.2.1.4 | [8 empty] | m²/nr | m² | 4 | Concrete walls | T1 - Building Structure
5 | 2.5.2.1.5 | [8 empty] | m²/nr | m² | 5 | Masonry walls | T1 - Building Structure
3 | 2.5.3 |  |  |  |  | 3 | Solar/rain screen cladding
4 | 2.5.3.1 | [6 empty] | 1 | Vertical solar/rain screening | m² | m² |  |  | T1 - Building Structure
4 | 2.5.3.2 | [6 empty] | 2 | Brise soleil and framework | m² | m² |  |  | T1 - Building Structure
3 | 2.5.4 |  |  |  |  | 4 | External soffits
4 | 2.5.4.1 | [6 empty] | 1 | External soffits
5 | 2.5.4.1.1 | [8 empty] | m²/nr | m² | 1 | In situ board ceilings/soffits | T1 - Building Structure
5 | 2.5.4.1.2 | [8 empty] | m²/nr | m² | 2 | Demountable suspended ceiling systems | T1 - Building Structure
5 | 2.5.4.1.3 | [8 empty] | m²/nr | m² | 3 | Insulation fixed to underside of ceiling or laid on soffit | T1 - Building Structure
3 | 2.5.5 |  |  |  |  | 5 | Subsidiary walls, balustrades, handrails, railings and proprietary balconies
4 | 2.5.5.1 | [6 empty] | 1 | Low level or dwarf walls, balustrades, handrails and railing to external walkways | m/nr | m |  |  | T1 - Building Structure
4 | 2.5.5.2 | [6 empty] | 2 | Combined balustrades and handrails | m/nr | m |  |  | T1 - Building Structure
4 | 2.5.5.3 | [6 empty] | 3 | Wall handrails | m/nr | m |  |  | T1 - Building Structure
4 | 2.5.5.4 | [6 empty] | 4 | Railings and barriers | m/nr | m |  |  | T1 - Building Structure
3 | 2.5.6 |  |  |  |  | 6 | Facade access/cleaning systems
4 | 2.5.6.1 | [6 empty] | 1 | Window/facade cleaning cradles | nr | nr |  |  | T16 – Specialist
4 | 2.5.6.2 | [6 empty] | 2 | Combined facade/roof cleaning system | nr | nr |  |  | T16 – Specialist
4 | 2.5.6.3 | [6 empty] | 3 | Building maintenance units | nr | nr |  |  | T16 – Specialist
2 | 2.6 |  |  | 6 | Windows and external doors
3 | 2.6.1 |  |  |  |  | 1 | External windows
4 | 2.6.1.1 | [6 empty] | 1 | External windows
5 | 2.6.1.1.1 | [8 empty] | m²/nr | nr | 1 | Aluminium Framed Double Glazed | T3 - External Walls, Windows and Doors
5 | 2.6.1.1.2 | [8 empty] | m²/nr | nr | 2 | Timber Framed Single Glazed | T3 - External Walls, Windows and Doors
5 | 2.6.1.1.3 | [8 empty] | m²/nr | nr | 3 | Timber framed single glazed sliding sash | T3 - External Walls, Windows and Doors
5 | 2.6.1.1.4 | [8 empty] | m²/nr | nr | 4 | UPVC Framed Double Glazed | T3 - External Walls, Windows and Doors
5 | 2.6.1.1.5 | [8 empty] | m²/nr | nr | 5 | UPVC Framed Single Glazed | T3 - External Walls, Windows and Doors
5 | 2.6.1.1.6 | [8 empty] | m²/nr | nr | 6 | Aluminium Framed Single Glazed | T3 - External Walls, Windows and Doors
5 | 2.6.1.1.7 | [8 empty] | m²/nr | nr | 7 | Aluminium Framed Triple Glazed | T3 - External Walls, Windows and Doors
5 | 2.6.1.1.8 | [8 empty] | m²/nr | nr | 8 | Direct Glazed Single Glazed Narrow Rectangular | T3 - External Walls, Windows and Doors
5 | 2.6.1.1.9 | [8 empty] | m²/nr | nr | 9 | Secondary Glazing System | T3 - External Walls, Windows and Doors
5 | 2.6.1.1.10 | [8 empty] | m²/nr | nr | 10 | Stained Glass | T3 - External Walls, Windows and Doors
5 | 2.6.1.1.11 | [8 empty] | m²/nr | nr | 11 | Steel Window | T3 - External Walls, Windows and Doors
5 | 2.6.1.1.12 | [8 empty] | m²/nr | nr | 12 | Steel Framed Single Glazed | T3 - External Walls, Windows and Doors
5 | 2.6.1.1.13 | [8 empty] | m²/nr | nr | 13 | Timber Framed Double Glazed | T3 - External Walls, Windows and Doors
4 | 2.6.1.2 | [6 empty] | 2 | Solar/rain screen over cladding | nr (m²) | m² |  |  | T3 - External Walls, Windows and Doors
4 | 2.6.1.3 | [6 empty] | 3 | Photovoltaic glazing when integral to window | nr (m²) | nr |  |  | T3 - External Walls, Windows and Doors
4 | 2.6.1.4 | [6 empty] | 4 | Canopies | nr | nr |  |  | T3 - External Walls, Windows and Doors
4 | 2.6.1.5 | [6 empty] | 5 | Window restrictors | nr | nr |  |  | T3 - External Walls, Windows and Doors
4 | 2.6.1.6 | [6 empty] | 6 | Louvres
5 | 2.6.1.6.1 | [8 empty] | m²/nr | nr | 1 | Manual louvres | T3 - External Walls, Windows and Doors
5 | 2.6.1.6.2 | [8 empty] | nr (m²) | nr | 2 | Automatic louvres | T3 - External Walls, Windows and Doors
4 | 2.6.1.7 | [6 empty] | 7 | Shop fronts | nr (m²) | nr |  |  | T3 - External Walls, Windows and Doors
4 | 2.6.1.8 | [6 empty] | 8 | Roller shutters
5 | 2.6.1.8.1 | [8 empty] | nr (m²) | nr | 1 | Roller shutters - automatic | T3 - External Walls, Windows and Doors
5 | 2.6.1.8.2 | [8 empty] | nr/m² | nr | 2 | Roller shutters - manual | T3 - External Walls, Windows and Doors
4 | 2.6.1.9 | [6 empty] | 9 | Fly screens and storm windows | nr/m² | nr |  |  | T3 - External Walls, Windows and Doors
3 | 2.6.2 |  |  |  |  | 2 | External doors
4 | 2.6.2.1 | [6 empty] | 1 | External doors - Automatic
5 | 2.6.2.1.1 | [8 empty] | nr | nr | 1 | Aluminium | T3 - External Walls, Windows and Doors
5 | 2.6.2.1.2 | [8 empty] | nr | nr | 2 | Glass | T3 - External Walls, Windows and Doors
5 | 2.6.2.1.3 | [8 empty] | nr | nr | 3 | Steel | T3 - External Walls, Windows and Doors
5 | 2.6.2.1.4 | [8 empty] | nr | nr | 4 | Steel Grille Gate | T3 - External Walls, Windows and Doors
5 | 2.6.2.1.5 | [8 empty] | nr | nr | 5 | Timber (Hardwood Fire Rated) | T3 - External Walls, Windows and Doors
5 | 2.6.2.1.6 | [8 empty] | nr | nr | 6 | Door - Timber (Hardwood) | T3 - External Walls, Windows and Doors
5 | 2.6.2.1.7 | [8 empty] | nr | nr | 7 | Timber (Ornate) | T3 - External Walls, Windows and Doors
5 | 2.6.2.1.8 | [8 empty] | nr | nr | 8 | Timber (Softwood) | T3 - External Walls, Windows and Doors
4 | 2.6.2.2 | [6 empty] | 2 | External doors - Manual
5 | 2.6.2.2.1 | [8 empty] | nr | nr | 1 | Aluminium | T3 - External Walls, Windows and Doors
5 | 2.6.2.2.2 | [8 empty] | nr | nr | 2 | Glass | T3 - External Walls, Windows and Doors
5 | 2.6.2.2.3 | [8 empty] | nr | nr | 3 | Steel | T3 - External Walls, Windows and Doors
5 | 2.6.2.2.4 | [8 empty] | nr | nr | 4 | Steel Grille Gate | T3 - External Walls, Windows and Doors
5 | 2.6.2.2.5 | [8 empty] | nr | nr | 5 | Timber (Hardwood Fire Rated) | T3 - External Walls, Windows and Doors
5 | 2.6.2.2.6 | [8 empty] | nr | nr | 6 | Door - Timber (Hardwood) | T3 - External Walls, Windows and Doors
5 | 2.6.2.2.7 | [8 empty] | nr | nr | 7 | Timber (Ornate) | T3 - External Walls, Windows and Doors
5 | 2.6.2.2.8 | [8 empty] | nr | nr | 8 | Timber (Softwood) | T3 - External Walls, Windows and Doors
4 | 2.6.2.3 | [6 empty] | 3 | Fly screens and storm doors | nr | nr |  |  | T3 - External Walls, Windows and Doors
4 | 2.6.2.4 | [6 empty] | 4 | Revolving doors | nr | nr |  |  | T3 - External Walls, Windows and Doors
4 | 2.6.2.5 | [6 empty] | 5 | External shop front doors | nr | nr |  |  | T3 - External Walls, Windows and Doors
4 | 2.6.2.6 | [6 empty] | 6 | Rolling and sliding shutters | nr | nr |  |  | T3 - External Walls, Windows and Doors
4 | 2.6.2.7 | [6 empty] | 7 | Garage doors | nr | nr |  |  | T3 - External Walls, Windows and Doors
4 | 2.6.2.8 | [6 empty] | 8 | Canopies | nr | nr |  |  | T3 - External Walls, Windows and Doors
4 | 2.6.2.9 | [6 empty] | 9 | Grilles to doorways | nr | nr |  |  | T3 - External Walls, Windows and Doors
4 | 2.6.2.10 | [6 empty] | 10 | Folding doors | nr | nr |  |  | T3 - External Walls, Windows and Doors
2 | 2.7 |  |  | 7 | Internal walls and partitions
3 | 2.7.1 |  |  |  |  | 1 | Walls and partitions
4 | 2.7.1.1 | [6 empty] | 1 | Load bearing internal walls | m² | m² |  |  | T1 - Building Structure
4 | 2.7.1.2 | [6 empty] | 2 | Walls forming cubicles | m² | m² |  |  | T1 - Building Structure
4 | 2.7.1.3 | [6 empty] | 3 | Borrowed lights and glazed screens | m² | nr |  |  | T1 - Building Structure
4 | 2.7.1.4 | [6 empty] | 4 | Access hatches | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 2.7.2 |  |  |  |  | 2 | Balustrades and handrails
4 | 2.7.2.1 | [6 empty] | 1 | Balustrades and handrails | m | m |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 2.7.3 |  |  |  |  | 3 | Movable room dividers
4 | 2.7.3.1 | [6 empty] | 1 | Moveable room dividers | m | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 2.7.4 |  |  |  |  | 4 | Cubicles
4 | 2.7.4.1 | [6 empty] | 1 | Cubicles | nr (m/m²) | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 2.7.4.2 | [6 empty] | 2 | Fixed partitions | nr (m/m²) | m² |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
2 | 2.8 |  |  | 8 | Internal doors
3 | 2.8.1 |  |  |  |  | 1 | Internal doors
4 | 2.8.1.1 | [6 empty] | 1 | Internal doors - manual
5 | 2.8.1.1.1 | [8 empty] | nr | nr | 1 | Door - Aluminium | T4 – Internal Walls and Doors
5 | 2.8.1.1.2 | [8 empty] | nr | nr | 2 | Door - Glass | T4 – Internal Walls and Doors
5 | 2.8.1.1.3 | [8 empty] | nr | nr | 3 | Door - Hygienic (Altro Whiterock) | T4 – Internal Walls and Doors
5 | 2.8.1.1.4 | [8 empty] | nr | nr | 4 | Door - Steel | T4 – Internal Walls and Doors
5 | 2.8.1.1.5 | [8 empty] | nr | nr | 5 | Door - Steel Grille Gate | T4 – Internal Walls and Doors
5 | 2.8.1.1.6 | [8 empty] | nr | nr | 6 | Door - Timber (Hardwood Fire Rated) | T4 – Internal Walls and Doors
5 | 2.8.1.1.7 | [8 empty] | nr | nr | 7 | Door - Timber (Hardwood) | T4 – Internal Walls and Doors
5 | 2.8.1.1.8 | [8 empty] | nr | nr | 8 | Door - Timber (Ornate) | T4 – Internal Walls and Doors
5 | 2.8.1.1.9 | [8 empty] | nr | nr | 9 | Door - Timber (Softwood) | T4 – Internal Walls and Doors
5 | 2.8.1.1.10 | [8 empty] | nr | nr | 10 | High Security Doors | T4 – Internal Walls and Doors
5 | 2.8.1.1.11 | [8 empty] | nr | nr | 11 | Doors - Folding | T4 – Internal Walls and Doors
4 | 2.8.1.2 | [6 empty] | 2 | Internal doors - automatic
5 | 2.8.1.2.1 | [8 empty] | nr | nr | 1 | Door - Aluminium | T4 – Internal Walls and Doors
5 | 2.8.1.2.2 | [8 empty] | nr | nr | 2 | Door - Glass | T4 – Internal Walls and Doors
5 | 2.8.1.2.3 | [8 empty] | nr | nr | 3 | Door - Hygienic (Altro Whiterock) | T4 – Internal Walls and Doors
5 | 2.8.1.2.4 | [8 empty] | nr | nr | 4 | Door - Steel | T4 – Internal Walls and Doors
5 | 2.8.1.2.5 | [8 empty] | nr | nr | 5 | Door - Steel Grille Gate | T4 – Internal Walls and Doors
5 | 2.8.1.2.6 | [8 empty] | nr | nr | 6 | Door - Timber (Hardwood Fire Rated) | T4 – Internal Walls and Doors
5 | 2.8.1.2.7 | [8 empty] | nr | nr | 7 | Door - Timber (Hardwood) | T4 – Internal Walls and Doors
5 | 2.8.1.2.8 | [8 empty] | nr | nr | 8 | Door - Timber (Ornate) | T4 – Internal Walls and Doors
5 | 2.8.1.2.9 | [8 empty] | nr | nr | 9 | Door - Timber (Softwood) | T4 – Internal Walls and Doors
5 | 2.8.1.2.10 | [8 empty] | nr | nr | 10 | High Security Doors | T4 – Internal Walls and Doors
5 | 2.8.1.2.11 | [8 empty] | nr | nr | 11 | Doors - Folding | T4 – Internal Walls and Doors
4 | 2.8.1.3 | [6 empty] | 3 | Fire Doors | nr | nr |  |  | T4 – Internal Walls and Doors
4 | 2.8.1.4 | [6 empty] | 4 | Roller /sliding shutters
5 | 2.8.1.4.1 | [8 empty] | nr | nr | 1 | Roller Shutter Doors - Powered | T4 – Internal Walls and Doors
5 | 2.8.1.4.2 | [8 empty] | nr | nr | 2 | Roller Shutter Doors - Manual | T4 – Internal Walls and Doors
1 | 3 | 3 | Internal finishes
2 | 3.1 |  |  | 1 | Wall finishes
3 | 3.1.1 |  |  |  |  | 1 | Finishes to walls
4 | 3.1.1.1 | [6 empty] | 1 | Wall finishes
5 | 3.1.1.1.1 | [8 empty] | m² | m² | 1 | Insitu coatings applied to walls | T5 - Internal Finishes
5 | 3.1.1.1.2 | [8 empty] | m² | m² | 2 | Sprayed monolithic protective coatings | T5 - Internal Finishes
5 | 3.1.1.1.3 | [8 empty] | m² | m² | 3 | Plasterboard or other sheet lining inc jointing | T5 - Internal Finishes
5 | 3.1.1.1.4 | [8 empty] | m² | m² | 4 | Ceramic wall lining | T5 - Internal Finishes
5 | 3.1.1.1.5 | [8 empty] | m² | m² | 5 | Decorative sheet coverings | T5 - Internal Finishes
5 | 3.1.1.1.6 | [8 empty] | m² | m² | 6 | Insulation that provides a wall finish | T5 - Internal Finishes
5 | 3.1.1.1.7 | [8 empty] | m² | m² | 7 | Acoustic insulation | T5 - Internal Finishes
5 | 3.1.1.1.8 | [8 empty] | m² | m² | 8 | Acoustic tile | T5 - Internal Finishes
5 | 3.1.1.1.9 | [8 empty] | m² | m² | 9 | Resin finishes | T5 - Internal Finishes
5 | 3.1.1.1.10 | [8 empty] | m² | m² | 10 | Timber panel | T5 - Internal Finishes
4 | 3.1.1.2 | [6 empty] | 2 | Wall finishes - specialist
5 | 3.1.1.2.1 | [8 empty] | m² | m² | 1 | Copper Sheet | T5 - Internal Finishes
5 | 3.1.1.2.2 | [8 empty] | m² | m² | 2 | Glazed Blocks | T5 - Internal Finishes
5 | 3.1.1.2.3 | [8 empty] | m² | m² | 3 | Hygienic Cladding | T5 - Internal Finishes
5 | 3.1.1.2.4 | [8 empty] | m² | m² | 4 | IPS Panel | T5 - Internal Finishes
5 | 3.1.1.2.5 | [8 empty] | m² | m² | 5 | Marble | T5 - Internal Finishes
5 | 3.1.1.2.6 | [8 empty] | m² | m² | 6 | Steel Chequer Plate | T5 - Internal Finishes
5 | 3.1.1.2.7 | [8 empty] | m² | m² | 7 | Stone Tile | T5 - Internal Finishes
4 | 3.1.1.3 | [6 empty] | 3 | Impact and bumper guards | m² | nr |  |  | T5 - Internal Finishes
2 | 3.2 |  |  | 2 | Floor finishes
3 | 3.2.1 |  |  |  |  | 1 | Finishes to floors
4 | 3.2.1.1 | [6 empty] | 1 | Floor finishes
5 | 3.2.1.1.1 | [8 empty] | m²/nr | m² | 1 | Non structural screeds inc damp proof membranes | T5 - Internal Finishes
5 | 3.2.1.1.2 | [8 empty] | m²/nr | m² | 2 | Latex screeds | T5 - Internal Finishes
5 | 3.2.1.1.3 | [8 empty] | m²/nr | m² | 3 | Chemical surface hardeners | T5 - Internal Finishes
5 | 3.2.1.1.4 | [8 empty] | m²/nr | m² | 4 | Floating floors | T5 - Internal Finishes
5 | 3.2.1.1.5 | [8 empty] | m²/nr | m² | 5 | Resin bonded resilient layers | T5 - Internal Finishes
5 | 3.2.1.1.6 | [8 empty] | m²/nr | m² | 6 | Bare Concrete | T5 - Internal Finishes
5 | 3.2.1.1.7 | [8 empty] | m²/nr | m² | 7 | Polished Concrete | T5 - Internal Finishes
5 | 3.2.1.1.8 | [8 empty] | m²/nr | m² | 8 | Terrazzo | T5 - Internal Finishes
5 | 3.2.1.1.9 | [8 empty] | m²/nr | m² | 9 | Carpet Tile | T5 - Internal Finishes
5 | 3.2.1.1.10 | [8 empty] | m²/nr | m² | 10 | Ceramic Tile | T5 - Internal Finishes
5 | 3.2.1.1.11 | [8 empty] | m²/nr | m² | 11 | Quarry Tile | T5 - Internal Finishes
5 | 3.2.1.1.12 | [8 empty] | m²/nr | m² | 12 | Stone Cobble | T5 - Internal Finishes
5 | 3.2.1.1.13 | [8 empty] | m²/nr | m² | 13 | Stone Slab | T5 - Internal Finishes
5 | 3.2.1.1.14 | [8 empty] | m²/nr | m² | 14 | Stone Tile | T5 - Internal Finishes
5 | 3.2.1.1.15 | [8 empty] | m²/nr | m² | 15 | Vinyl Tile | T5 - Internal Finishes
5 | 3.2.1.1.16 | [8 empty] | m²/nr | m² | 16 | Wood blook flooring | T5 - Internal Finishes
5 | 3.2.1.1.17 | [8 empty] | m²/nr | m² | 17 | Proprietary thin tiled and strip flooring | T5 - Internal Finishes
5 | 3.2.1.1.18 | [8 empty] | m²/nr | m² | 18 | Floor painting and sealing | T5 - Internal Finishes
5 | 3.2.1.1.19 | [8 empty] | m²/nr | m² | 19 | Edge fixed carpet including underlay | T5 - Internal Finishes
5 | 3.2.1.1.20 | [8 empty] | m²/nr | m² | 20 | Rubber tile/sheet | T5 - Internal Finishes
5 | 3.2.1.1.21 | [8 empty] | m²/nr | m² | 21 | Vinyl sheet | T5 - Internal Finishes
5 | 3.2.1.1.22 | [8 empty] | m²/nr | m² | 22 | Vinyl anti slip | T5 - Internal Finishes
5 | 3.2.1.1.23 | [8 empty] | m²/nr | m² | 23 | Anti-static flooring | T5 - Internal Finishes
4 | 3.2.1.2 | [6 empty] | 2 | Timber sprung floors | m² | m² |  |  | T5 - Internal Finishes
4 | 3.2.1.3 | [6 empty] | 3 | Mat wells and mats | nr | nr |  |  | T5 - Internal Finishes
4 | 3.2.1.4 | [6 empty] | 4 | Finishes to swimming pools tanks | m² | m² |  |  | T16 – Specialist
4 | 3.2.1.5 | [6 empty] | 5 | Line markings | m | m |  |  | T5 - Internal Finishes
3 | 3.2.2 |  |  |  |  | 2 | Raised access floors
4 | 3.2.2.1 | [6 empty] | 1 | Raised access floor systems | m² | m² |  |  | T5 - Internal Finishes
2 | 3.3 |  |  | 3 | Ceiling finishes
3 | 3.3.1 |  |  |  |  | 1 | Finishes to ceilings
4 | 3.3.1.1 | [6 empty] | 1 | Ceiling finishes
5 | 3.3.1.1.1 | [8 empty] | m²/nr | m² | 1 | PVC Cladding | T5 - Internal Finishes
5 | 3.3.1.1.2 | [8 empty] | m²/nr | m² | 2 | Wood Panelling | T5 - Internal Finishes
5 | 3.3.1.1.3 | [8 empty] | m²/nr | m² | 3 | Sprayed monolithic coatings | T5 - Internal Finishes
5 | 3.3.1.1.4 | [8 empty] | m²/nr | m² | 4 | Specialist ceiling finishes | T5 - Internal Finishes
3 | 3.3.2 |  |  |  |  | 2 | False ceilings
4 | 3.3.2.1 | [6 empty] | 1 | False ceilings
5 | 3.3.2.1.1 | [8 empty] | m²/nr | m² | 1 | Wooden | T5 - Internal Finishes
5 | 3.3.2.1.2 | [8 empty] | m²/nr | m² | 2 | Plasterboard | T5 - Internal Finishes
5 | 3.3.2.1.3 | [8 empty] | m²/nr | m² | 3 | Stretch/Tensioned | T5 - Internal Finishes
5 | 3.3.2.1.4 | [8 empty] | m²/nr | m² | 4 | Chilled | T5 - Internal Finishes
5 | 3.3.2.1.5 | [8 empty] | m²/nr | m² | 5 | Concealed Grid | T5 - Internal Finishes
5 | 3.3.2.1.6 | [8 empty] | m²/nr | m² | 6 | Exposed Grid | T5 - Internal Finishes
5 | 3.3.2.1.7 | [8 empty] | m²/nr | m² | 7 | Metal Furring Channel | T5 - Internal Finishes
5 | 3.3.2.1.8 | [8 empty] | m²/nr | m² | 8 | Semi-Concealed Grid | T5 - Internal Finishes
5 | 3.3.2.1.9 | [8 empty] | m²/nr | m² | 9 | Walk-On | T5 - Internal Finishes
4 | 3.3.2.2 | [6 empty] | 2 | Access hatches | m²/nr | nr |  |  | T5 - Internal Finishes
3 | 3.3.3 |  |  |  |  | 3 | Demountable suspended ceilings
4 | 3.3.3.1 | [6 empty] | 1 | Demountable suspended ceilings | m²/nr | m² |  |  | T5 - Internal Finishes
4 | 3.3.3.2 | [6 empty] | 2 | Access hatches | nr | nr |  |  | T5 - Internal Finishes
1 | 4 | 4 | Fittings, furnishings and equipment
2 | 4.1 |  |  | 1 | Fittings, furnishings and equipment
3 | 4.1.1 |  |  |  |  | 1 | General fittings, furnishings and equipment
4 | 4.1.1.1 | [6 empty] | 1 | Counters, desks, benches and worktops | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.2 | [6 empty] | 2 | Mirrors not integral to any other item | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.3 | [6 empty] | 3 | Curtains, track rails and pelmets | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.4 | [6 empty] | 4 | Fireplace surrounds and hearths | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.5 | [6 empty] | 5 | Storage racks, shelves and shelving support systems
5 | 4.1.1.5.1 | [8 empty] | nr | nr | 1 | Shelving - Retail | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.1.5.2 | [8 empty] | nr | nr | 2 | Shelving - Warehouse | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.1.5.3 | [8 empty] | nr | nr | 3 | Shelving - Longspan | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.1.5.4 | [8 empty] | nr | nr | 4 | Shelving - Mobile Bases | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.1.5.5 | [8 empty] | nr | nr | 5 | Adjustable Pallet Racking and Shelving | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.1.5.6 | [8 empty] | nr | nr | 6 | High Bay Racking and Carpet Racking | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.6 | [6 empty] | 6 | Fitted seating upholstery | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.7 | [6 empty] | 7 | Bathroom furniture, vanity units and the like | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.8 | [6 empty] | 8 | Blinds
5 | 4.1.1.8.1 | [8 empty] | nr | nr | 1 | Blinds | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.1.8.2 | [8 empty] | nr | nr | 2 | Internal Window Blinds | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.9 | [6 empty] | 9 | Wall hangings | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.10 | [6 empty] | 10 | Loose carpets | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.11 | [6 empty] | 11 | Tables and chairs | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.12 | [6 empty] | 12 | Bedroom furniture | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.13 | [6 empty] | 13 | Lockers, hat and coal rails | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.14 | [6 empty] | 14 | Bins, wheelie bins and continental bins | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.15 | [6 empty] | 15 | Safes | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.16 | [6 empty] | 16 | Vacuum cleaners and cleaning equipment | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.17 | [6 empty] | 17 | Televisions, hi-fi and computers | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.18 | [6 empty] | 18 | Vending machines
5 | 4.1.1.18.1 | [8 empty] | nr | nr | 1 | Hot Drinks Vending Machine | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.1.18.2 | [8 empty] | nr | nr | 2 | Cold food and drink vending machines | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.1.18.3 | [8 empty] | nr | nr | 3 | Ticket Vending Machines | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.19 | [6 empty] | 19 | Telephone booths and enclosure | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.1.20 | [6 empty] | 20 | Pay Station | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 4.1.2 |  |  |  |  | 2 | Domestic kitchen fittings and equipment
4 | 4.1.2.1 | [6 empty] | 1 | Kitchen units include base units, worktops and cupboards | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.2.2 | [6 empty] | 2 | Sink taps, waste fittings and waste disposal | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 4.1.3 |  |  |  |  | 3 | Special-purpose fittings, furnishings and equipment
4 | 4.1.3.1 | [6 empty] | 1 | Fittings - non mechanical and non electrical | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.3.2 | [6 empty] | 2 | Furnishings - non mechanical and non electrical | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.3.3 | [6 empty] | 3 | Equipment - non mechanical and non electrical | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 4.1.4 |  |  |  |  | 4 | Signs and notices
4 | 4.1.4.1 | [6 empty] | 1 | Directional signboards | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.4.2 | [6 empty] | 2 | Notice boards, white boards, etc. | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.4.3 | [6 empty] | 3 | Sign writing | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.4.4 | [6 empty] | 4 | Shop front lettering, emblems and symbols | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.4.5 | [6 empty] | 5 | Door or floor numbering or lettering | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.4.6 | [6 empty] | 6 | Nameplates¦ Plaques and ID symbols | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.4.7 | [6 empty] | 7 | Lettering emblems and directional symbols | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 4.1.5 |  |  |  |  | 5 | Works of art
4 | 4.1.5.1 | [6 empty] | 1 | Objects d'art and other ornamental features
5 | 4.1.5.1.1 | [8 empty] | Excluded | nr | 1 | Objects d'art and other ornamental features | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.5.1.2 | [8 empty] | Excluded | nr | 2 | Fish tanks including those set into internal walls | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 4.1.6 |  |  |  |  | 6 | Non mechanical and non electrical equipment
4 | 4.1.6.1 | [6 empty] | 1 | Removable disable access equipment
5 | 4.1.6.1.1 | [8 empty] | nr | nr | 1 | Evacuation Chairs | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.6.1.2 | [8 empty] | nr | nr | 2 | Lifting Slings - for a person | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.6.1.3 | [8 empty] | nr | nr | 3 | Manual wheelchair | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.6.2 | [6 empty] | 2 | Removable ladders | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 4.1.7 |  |  |  |  | 7 | Internal planting
4 | 4.1.7.1 | [6 empty] | 1 | Plants and shrub beds
5 | 4.1.7.1.1 | [8 empty] | nr/m² | nr | 1 | Planting container grown plants | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.7.1.2 | [8 empty] | nr/m² | nr | 2 | Planting shrubs | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.7.1.3 | [8 empty] | nr/m² | nr | 3 | Planting to containers which are integral part of building | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 4.1.7.1.4 | [8 empty] | nr/m² | nr | 4 | Artificial plants including any fixing and coverings | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.7.2 | [6 empty] | 2 | Plant containers | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.7.3 | [6 empty] | 3 | Trees | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 4.1.7.4 | [6 empty] | 4 | Tree planters | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 4.1.8 |  |  |  |  | 8 | Bird and vermin control
4 | 4.1.8.1 | [6 empty] | 1 | Wires, nets and traps | nr | nr |  |  | T16 – Specialist
4 | 4.1.8.2 | [6 empty] | 2 | Electronic and sonic systems | System | System |  |  | T16 – Specialist
4 | 4.1.8.3 | [6 empty] | 3 | Bird repellent coatings | m² | m² |  |  | T16 – Specialist
1 | 5 | 5 | Services
2 | 5.1 |  |  | 1 | Sanitary installations
3 | 5.1.1 |  |  |  |  | 1 | Sanitary appliances
4 | 5.1.1.1 | [6 empty] | 1 | Water Closets (WC)
5 | 5.1.1.1.1 | [8 empty] | nr | nr | 1 | Vitreous china/ fireclay/ uPVC | T7 – Sanitary and Plumbing Services
5 | 5.1.1.1.2 | [8 empty] | nr | nr | 2 | Cast iron/ stainless steel | T7 – Sanitary and Plumbing Services
4 | 5.1.1.2 | [6 empty] | 2 | Sinks
5 | 5.1.1.2.1 | [8 empty] | nr | nr | 1 | Vitreous china/ fireclay/ uPVC | T7 – Sanitary and Plumbing Services
5 | 5.1.1.2.2 | [8 empty] | nr | nr | 2 | Cast iron/ stainless steel | T7 – Sanitary and Plumbing Services
4 | 5.1.1.3 | [6 empty] | 3 | Wash basins
5 | 5.1.1.3.1 | [8 empty] | nr | nr | 1 | Vitreous china/ fireclay/ uPVC | T7 – Sanitary and Plumbing Services
5 | 5.1.1.3.2 | [8 empty] | nr | nr | 2 | Cast iron/ stainless steel | T7 – Sanitary and Plumbing Services
4 | 5.1.1.4 | [6 empty] | 4 | Bidets
5 | 5.1.1.4.1 | [8 empty] | nr | nr | 1 | Vitreous china/ fireclay/ uPVC | T7 – Sanitary and Plumbing Services
5 | 5.1.1.4.2 | [8 empty] | nr | nr | 2 | Cast iron/ stainless steel | T7 – Sanitary and Plumbing Services
4 | 5.1.1.5 | [6 empty] | 5 | Cisterns | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.1.1.6 | [6 empty] | 6 | Baths
5 | 5.1.1.6.1 | [8 empty] | nr | nr | 1 | Vitreous china/ fireclay/ uPVC | T7 – Sanitary and Plumbing Services
5 | 5.1.1.6.2 | [8 empty] | nr | nr | 2 | Cast iron/ stainless steel | T7 – Sanitary and Plumbing Services
4 | 5.1.1.7 | [6 empty] | 7 | Pumps
5 | 5.1.1.7.X | [8 empty] | nr | nr | X | See SUP - Pumps | T7 – Sanitary and Plumbing Services
4 | 5.1.1.8 | [6 empty] | 8 | Showers
5 | 5.1.1.8.1 | [8 empty] | nr | nr | 1 | Electric | T7 – Sanitary and Plumbing Services
5 | 5.1.1.8.2 | [8 empty] | nr | nr | 2 | Non-Thermostatic Mixing Valve - Type 1 | T7 – Sanitary and Plumbing Services
5 | 5.1.1.8.3 | [8 empty] | nr | nr | 3 | Thermostatic Mixing Valve (TMV) - Type 2 | T7 – Sanitary and Plumbing Services
5 | 5.1.1.8.4 | [8 empty] | nr | nr | 4 | Thermostatic Mixing Valve (TMV) - Type 3 | T7 – Sanitary and Plumbing Services
5 | 5.1.1.8.5 | [8 empty] | nr | nr | 5 | Push Button Shower Valves | T7 – Sanitary and Plumbing Services
4 | 5.1.1.9 | [6 empty] | 9 | Shower trays | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.1.1.10 | [6 empty] | 10 | Drinking fountains
5 | 5.1.1.10.1 | [8 empty] | nr | nr | 1 | Bottled Water Cooler | T7 – Sanitary and Plumbing Services
5 | 5.1.1.10.2 | [8 empty] | nr | nr | 2 | Point of Use Water Dispenser | T7 – Sanitary and Plumbing Services
5 | 5.1.1.10.3 | [8 empty] | nr | nr | 3 | Instantaneous Potable Chilled Water Tap (Fluorinated Gas) | T7 – Sanitary and Plumbing Services
5 | 5.1.1.10.4 | [8 empty] | nr | nr | 4 | Instantaneous Potable Chilled Water Tap (Non-Fluorinated Gas) | T7 – Sanitary and Plumbing Services
5 | 5.1.1.10.5 | [8 empty] | nr | nr | 5 | Instantaneous Potable Combination Hot, Chilled and Carbonated Water Tap (Fluorinated Gas) | T7 – Sanitary and Plumbing Services
5 | 5.1.1.10.6 | [8 empty] | nr | nr | 6 | Instantaneous Potable Combination Hot, Chilled and Carbonated Water Tap (Non-Fluorinated Gas) | T7 – Sanitary and Plumbing Services
4 | 5.1.1.11 | [6 empty] | 11 | Taps
5 | 5.1.1.11.X | [8 empty] | nr | nr | X | See SUP - Taps | T7 – Sanitary and Plumbing Services
4 | 5.1.1.12 | [6 empty] | 12 | Water saving devices | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.1.1.13 | [6 empty] | 13 | Water filters | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.1.1.14 | [6 empty] | 14 | Urinals
5 | 5.1.1.14.1 | [8 empty] | nr | nr | 1 | Vitreous china/ fireclay/ uPVC | T7 – Sanitary and Plumbing Services
5 | 5.1.1.14.2 | [8 empty] | nr | nr | 2 | Cast iron/ stainless steel | T7 – Sanitary and Plumbing Services
3 | 5.1.2 |  |  |  |  | 2 | Sanitary Ancillaries
4 | 5.1.2.1 | [6 empty] | 1 | Bath/shower curtain and rails | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.1.2.2 | [6 empty] | 2 | Grab/support rail | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.1.2.3 | [6 empty] | 3 | Towel rails and holders | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.1.2.4 | [6 empty] | 4 | Hand dryers | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.1.2.5 | [6 empty] | 5 | Paper towel dispensers | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.1.2.6 | [6 empty] | 6 | Sanitary incinerators (towel disposal) | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.1.2.7 | [6 empty] | 7 | Macerators | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.1.2.8 | [6 empty] | 8 | Combined Hand Washer/Dryer | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.1.2.9 | [6 empty] | 9 | Hair Dryer | nr | nr |  |  | T7 – Sanitary and Plumbing Services
2 | 5.2 |  |  | 2 | Services Equipment
3 | 5.2.1 |  |  |  |  | 1 | Catering equipment
4 | 5.2.1.1 | [6 empty] | 1 | Grease Traps | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.2 | [6 empty] | 2 | Bain Marie/Counter
5 | 5.2.1.2.1 | [8 empty] | nr | nr | 1 | Bain Marie/Counter - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.2.2 | [8 empty] | nr | nr | 2 | Bain Marie/Counter - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.3 | [6 empty] | 3 | Cup Warmer | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.4 | [6 empty] | 4 | Heat Lamps and Gantry | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.5 | [6 empty] | 5 | Heated Mobile Trolley | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.6 | [6 empty] | 6 | Hot Cupboard
5 | 5.2.1.6.1 | [8 empty] | nr | nr | 1 | Hot Cupboard - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.6.2 | [8 empty] | nr | nr | 2 | Hot Cupboard - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.7 | [6 empty] | 7 | Hot Display Counter - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.8 | [6 empty] | 8 | Hot Plate - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.9 | [6 empty] | 9 | Plate Warmer | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.10 | [6 empty] | 10 | Servery | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.11 | [6 empty] | 11 | Tray Conveyors | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.12 | [6 empty] | 12 | Heated 'Grab & Go' Unit - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.13 | [6 empty] | 13 | Hot Chicken Display Counter - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.14 | [6 empty] | 14 | Coffee Machine
5 | 5.2.1.14.1 | [8 empty] | nr | nr | 1 | Coffee Machine (Non Pressurised) - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.14.2 | [8 empty] | nr | nr | 2 | Coffee Machine (Non Pressurised) - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.14.3 | [8 empty] | nr | nr | 3 | Coffee Machine (Pressurised) - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.14.4 | [8 empty] | nr | nr | 4 | Coffee Machine (Pressurised) - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.15 | [6 empty] | 15 | Cold Food and Drink Vending Machines | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.16 | [6 empty] | 16 | Hot Chocolate Machine - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.17 | [6 empty] | 17 | Hot Drinks Vending Machine | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.18 | [6 empty] | 18 | Fat Fryer (Open Topped)
5 | 5.2.1.18.1 | [8 empty] | nr | nr | 1 | Fat Fryer (Open Topped) - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.18.2 | [8 empty] | nr | nr | 2 | Fat Fryer (Open Topped) - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.19 | [6 empty] | 19 | Griddle/Grill
5 | 5.2.1.19.1 | [8 empty] | nr | nr | 1 | Griddle/Grill - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.19.2 | [8 empty] | nr | nr | 2 | Griddle/Grill - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.20 | [6 empty] | 20 | Salamander
5 | 5.2.1.20.1 | [8 empty] | nr | nr | 1 | Salamander - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.20.2 | [8 empty] | nr | nr | 2 | Salamander - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.21 | [6 empty] | 21 | Grill - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.22 | [6 empty] | 22 | Bratt Pan
5 | 5.2.1.22.1 | [8 empty] | nr | nr | 1 | Bratt Pan - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.22.2 | [8 empty] | nr | nr | 2 | Bratt Pan - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.23 | [6 empty] | 23 | Kettle (Non Pressurised) - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.24 | [6 empty] | 24 | Kettle (Pressurised) - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.25 | [6 empty] | 25 | Tilting Kettle (Non Pressurised)
5 | 5.2.1.25.1 | [8 empty] | nr | nr | 1 | Tilting Kettle (Non Pressurised) - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.25.2 | [8 empty] | nr | nr | 2 | Tilting Kettle (Non Pressurised) - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.26 | [6 empty] | 26 | Tilting Kettle (Pressurised)
5 | 5.2.1.26.1 | [8 empty] | nr | nr | 1 | Tilting Kettle (Pressurised) - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.26.2 | [8 empty] | nr | nr | 2 | Tilting Kettle (Pressurised) - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.27 | [6 empty] | 27 | Water Boiler (Non Pressurised)
5 | 5.2.1.27.1 | [8 empty] | nr | nr | 1 | Water Boiler (Non Pressurised) - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.27.2 | [8 empty] | nr | nr | 2 | Water Boiler (Non Pressurised) - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.28 | [6 empty] | 28 | Water Boiler (Pressurised)
5 | 5.2.1.28.1 | [8 empty] | nr | nr | 1 | Water Boiler (Pressurised) - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.28.2 | [8 empty] | nr | nr | 2 | Water Boiler (Pressurised) - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.29 | [6 empty] | 29 | Boiling Pan (Non Pressurised)
5 | 5.2.1.29.1 | [8 empty] | nr | nr | 1 | Boiling Pan (Non Pressurised) - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.29.2 | [8 empty] | nr | nr | 2 | Boiling Pan (Non Pressurised) - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.30 | [6 empty] | 30 | Boiling Pan (Pressurised)
5 | 5.2.1.30.1 | [8 empty] | nr | nr | 1 | Boiling Pan (Pressurised) - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.30.2 | [8 empty] | nr | nr | 2 | Boiling Pan (Pressurised) - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.31 | [6 empty] | 31 | Kettle (Non Pressurised) - Gas | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.32 | [6 empty] | 32 | Kettle (Pressurised) - Gas | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.33 | [6 empty] | 33 | Soup Kettle - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.34 | [6 empty] | 34 | Coffee Grinder | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.35 | [6 empty] | 35 | Crepe Machine | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.36 | [6 empty] | 36 | Degreasing Tank - Electrical | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.37 | [6 empty] | 37 | Dough Kneader - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.38 | [6 empty] | 38 | Dough/Pastry Sheeter | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.39 | [6 empty] | 39 | Food Processor | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.40 | [6 empty] | 40 | Frozen Yogurt Machine | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.41 | [6 empty] | 41 | Gas Appliances - Kitchens | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.42 | [6 empty] | 42 | Glazing Machine | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.43 | [6 empty] | 43 | Hand Held Stick Blender | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.44 | [6 empty] | 44 | Ice Cream Machine | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.45 | [6 empty] | 45 | Insect Killer | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.46 | [6 empty] | 46 | Juice Dispenser | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.47 | [6 empty] | 47 | Juice Maker | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.48 | [6 empty] | 48 | LPG BBQ | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.49 | [6 empty] | 49 | Mixer - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.50 | [6 empty] | 50 | Pasta Maker - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.51 | [6 empty] | 51 | Pasta Roller | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.52 | [6 empty] | 52 | Pot Wash Scrubber | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.53 | [6 empty] | 53 | Rice Cooker - Electric - Bench Standing | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.54 | [6 empty] | 54 | Salad Washer | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.55 | [6 empty] | 55 | Sandwich Toaster | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.56 | [6 empty] | 56 | Kitchen Scales | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.57 | [6 empty] | 57 | Slush Machine | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.58 | [6 empty] | 58 | Toaster
5 | 5.2.1.58.1 | [8 empty] | nr | nr | 1 | Toaster - Conveyor/Rotary | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.58.2 | [8 empty] | nr | nr | 2 | Toaster - Pop Up | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.59 | [6 empty] | 59 | Utensil Washer | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.60 | [6 empty] | 60 | Waste Disposal Unit | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.61 | [6 empty] | 61 | Dishwasher
5 | 5.2.1.61.1 | [8 empty] | nr | nr | 1 | Dishwashers Glassware | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.61.2 | [8 empty] | nr | nr | 2 | Dishwashers Pass Through - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.61.3 | [8 empty] | nr | nr | 3 | Dishwashers Rack and Flight - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.61.4 | [8 empty] | nr | nr | 4 | Dishwashers Undercounter | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.62 | [6 empty] | 62 | Can Crusher
5 | 5.2.1.62.1 | [8 empty] | nr | nr | 1 | Can Crusher - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.62.2 | [8 empty] | nr | nr | 2 | Can Crusher - Manual | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.63 | [6 empty] | 63 | Cutlery Polisher | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.64 | [6 empty] | 64 | Pasta Cooker
5 | 5.2.1.64.1 | [8 empty] | nr | nr | 1 | Pasta Cooker - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.64.2 | [8 empty] | nr | nr | 2 | Pasta Cooker - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.65 | [6 empty] | 65 | Toasted Panini Machine | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.66 | [6 empty] | 66 | Vacuum Packer | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.67 | [6 empty] | 67 | Mincing Machine | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.68 | [6 empty] | 68 | Central Temperature Monitor | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.69 | [6 empty] | 69 | Dishwasher Condensing Hoods | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.70 | [6 empty] | 70 | Re-circulation Cooker Hood | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.71 | [6 empty] | 71 | Dishwasher Heat Exchangers | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.72 | [6 empty] | 72 | Bake Off Oven
5 | 5.2.1.72.1 | [8 empty] | nr | nr | 1 | Bake Off Oven - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.72.2 | [8 empty] | nr | nr | 2 | Bake Off Oven - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.73 | [6 empty] | 73 | Baked Potato Oven - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.74 | [6 empty] | 74 | Bread Oven
5 | 5.2.1.74.1 | [8 empty] | nr | nr | 1 | Bread Oven - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.74.2 | [8 empty] | nr | nr | 2 | Bread Oven - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.75 | [6 empty] | 75 | Bulls Eye Range - Gas | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.76 | [6 empty] | 76 | Combination Oven
5 | 5.2.1.76.1 | [8 empty] | nr | nr | 1 | Combination Oven - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.76.2 | [8 empty] | nr | nr | 2 | Combination Oven - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.77 | [6 empty] | 77 | Convection Oven
5 | 5.2.1.77.1 | [8 empty] | nr | nr | 1 | Convection Oven - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.77.2 | [8 empty] | nr | nr | 2 | Convection Oven - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.78 | [6 empty] | 78 | Deck Oven
5 | 5.2.1.78.1 | [8 empty] | nr | nr | 1 | Deck Oven - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.78.2 | [8 empty] | nr | nr | 2 | Deck Oven - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.79 | [6 empty] | 79 | Hob
5 | 5.2.1.79.1 | [8 empty] | nr | nr | 1 | Hobs - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.79.2 | [8 empty] | nr | nr | 2 | Hobs - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.80 | [6 empty] | 80 | Microwave
5 | 5.2.1.80.1 | [8 empty] | nr | nr | 1 | Microwave Combination Oven | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.80.2 | [8 empty] | nr | nr | 2 | Microwave Oven | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.80.3 | [8 empty] | nr | nr | 3 | Microwave Convection Oven | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.81 | [6 empty] | 81 | Rack Oven
5 | 5.2.1.81.1 | [8 empty] | nr | nr | 1 | Rack Oven - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.81.2 | [8 empty] | nr | nr | 2 | Rack Oven - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.82 | [6 empty] | 82 | Range
5 | 5.2.1.82.1 | [8 empty] | nr | nr | 1 | Range - Solid Top - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.82.2 | [8 empty] | nr | nr | 2 | Range - Solid Top - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.83 | [6 empty] | 83 | Rotisserie
5 | 5.2.1.83.1 | [8 empty] | nr | nr | 1 | Rotisserie - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.83.2 | [8 empty] | nr | nr | 2 | Rotisserie - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.84 | [6 empty] | 84 | Steaming Oven
5 | 5.2.1.84.1 | [8 empty] | nr | nr | 1 | Steaming Oven - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.84.2 | [8 empty] | nr | nr | 2 | Steaming Oven - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.85 | [6 empty] | 85 | Steaming Oven (Pressurised)
5 | 5.2.1.85.1 | [8 empty] | nr | nr | 1 | Steaming Oven (Pressurised) - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.85.2 | [8 empty] | nr | nr | 2 | Steaming Oven (Pressurised) - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.86 | [6 empty] | 86 | Induction Hobs | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.87 | [6 empty] | 87 | Domestic Style Cooker
5 | 5.2.1.87.1 | [8 empty] | nr | nr | 1 | Domestic Style Cooker - Electric | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.1.87.2 | [8 empty] | nr | nr | 2 | Domestic Style Cooker - Gas | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.88 | [6 empty] | 88 | Regeneration Oven - Electric | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.89 | [6 empty] | 89 | Bread Slicer | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.90 | [6 empty] | 90 | Meat Slicer | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.91 | [6 empty] | 91 | Potato Chipper | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.92 | [6 empty] | 92 | Potato Peeler | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.93 | [6 empty] | 93 | Vegetable Slicer/Prep Machine | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.94 | [6 empty] | 94 | Fat Filter | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.95 | [6 empty] | 95 | Sinks | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.1.101 | [6 empty] | 101 | Kitchen Deep clean | m²/nr | m² |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 5.2.2 |  |  |  |  | 2 | Food storage equipment
4 | 5.2.2.96 | [6 empty] | 96 | Cold Rooms | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.2.97 | [6 empty] | 97 | Refrigerated Display Cabinets | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.2.98 | [6 empty] | 98 | Cold Room Heater Mat System | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.2.99 | [6 empty] | 99 | Fridges, Freezers and Blast Chillers | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.2.100 | [6 empty] | 100 | Refrigerated Milk Dispenser | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 5.2.3 |  |  |  |  | 3 | Catering water treatment
4 | 5.2.3.1 | [6 empty] | 1 | Dosing systems
5 | 5.2.3.1.1 | [8 empty] | nr | nr | 1 | Bacterial and Enzyme Drain Dosing Systems | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.2.3.1.2 | [8 empty] | nr | nr | 2 | External Chemical Dosing - Dishwashers and Glassware | T6 - Fixed Furniture / Fittings & Service Equipment
3 | 5.2.4 |  |  |  |  | 4 | Mechanical handling Equipment
4 | 5.2.4.1 | [6 empty] | 1 | Pallet wrapper | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.4.2 | [6 empty] | 2 | Pallet inverter | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.2.4.3 | [6 empty] | 3 | Cleaning Machines - Sweeper/Scrubber | nr | nr |  |  | T6 - Fixed Furniture / Fittings & Service Equipment
2 | 5.3 |  |  | 3 | Disposal Installations
3 | 5.3.1 |  |  |  |  | 1 | Foul drainage above ground
4 | 5.3.1.1 | [6 empty] | 1 | Waste pipes and fittings
5 | 5.3.1.1.1 | [8 empty] | nr | m² | 1 | Polypropylene; muPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.1.1.2 | [8 empty] | nr | m² | 2 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.1.1.3 | [8 empty] | nr | m² | 3 | Ductile iron | T7 – Sanitary and Plumbing Services
4 | 5.3.1.2 | [6 empty] | 2 | Prefabricated Pipeline Assemblies
5 | 5.3.1.2.1 | [8 empty] | nr | m² | 1 | Polypropylene; muPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.1.2.2 | [8 empty] | nr | m² | 2 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.1.2.3 | [8 empty] | nr | m² | 3 | Ductile iron | T7 – Sanitary and Plumbing Services
4 | 5.3.1.3 | [6 empty] | 3 | Prefabricated Floor Channels and Gratings
5 | 5.3.1.3.1 | [8 empty] | nr | nr | 1 | Polypropylene; muPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.1.3.2 | [8 empty] | nr | nr | 2 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.1.3.3 | [8 empty] | nr | nr | 3 | Ductile iron | T7 – Sanitary and Plumbing Services
4 | 5.3.1.4 | [6 empty] | 4 | Sanitary Waste - Traps
5 | 5.3.1.4.1 | [8 empty] | nr | nr | 1 | Polypropylene; muPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.1.4.2 | [8 empty] | nr | nr | 2 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.1.4.3 | [8 empty] | nr | nr | 3 | Ductile iron | T7 – Sanitary and Plumbing Services
4 | 5.3.1.5 | [6 empty] | 5 | Sanitary Waste - Soil Stacks
5 | 5.3.1.5.1 | [8 empty] | nr | m² | 1 | Polypropylene; muPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.1.5.2 | [8 empty] | nr | m² | 2 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.1.5.3 | [8 empty] | nr | m² | 3 | Ductile iron | T7 – Sanitary and Plumbing Services
4 | 5.3.1.6 | [6 empty] | 6 | Ventilation stacks and pipes
5 | 5.3.1.6.1 | [8 empty] | nr | m² | 1 | Polypropylene; muPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.1.6.2 | [8 empty] | nr | m² | 2 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.1.6.3 | [8 empty] | nr | m² | 3 | Ductile iron | T7 – Sanitary and Plumbing Services
4 | 5.3.1.7 | [6 empty] | 7 | Traps access points and rodding eyes
5 | 5.3.1.7.1 | [8 empty] | nr | m² | 1 | Polypropylene; muPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.1.7.2 | [8 empty] | nr | m² | 2 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.1.7.3 | [8 empty] | nr | m² | 3 | Ductile iron | T7 – Sanitary and Plumbing Services
4 | 5.3.1.8 | [6 empty] | 8 | Prefabricated floor channels and gratings |  | nr
5 | 5.3.1.8.1 | [8 empty] | nr | m² | 1 | Polypropylene; muPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.1.8.2 | [8 empty] | nr | m² | 2 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.1.8.3 | [8 empty] | nr | m² | 3 | Ductile iron | T7 – Sanitary and Plumbing Services
4 | 5.3.1.9 | [6 empty] | 9 | Sump pumps
5 | 5.3.1.9.X | [8 empty] | nr | nr | X | See SUP - Pumps | T7 – Sanitary and Plumbing Services
4 | 5.3.1.10 | [6 empty] | 10 | Air admittance valves
5 | 5.3.1.10.X | [8 empty] | nr | nr | X | See SUP - Valves | T7 – Sanitary and Plumbing Services
3 | 5.3.2 |  |  |  |  | 2 | Chemical, toxic and industrial liquid waste drainage
4 | 5.3.2.1 | [6 empty] | 1 | Pipe work systems
5 | 5.3.2.1.1 | [8 empty] | nr | m² | 1 | Glass | T7 – Sanitary and Plumbing Services
5 | 5.3.2.1.2 | [8 empty] | nr | m² | 2 | Polypropylene; uPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.2.1.3 | [8 empty] | nr | m² | 3 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.2.1.4 | [8 empty] | nr | m² | 4 | Ductile iron | T7 – Sanitary and Plumbing Services
4 | 5.3.2.2 | [6 empty] | 2 | Traps access points and rodding eyes
5 | 5.3.2.2.1 | [8 empty] | nr | m² | 1 | Polypropylene; uPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.2.2.2 | [8 empty] | nr | m² | 2 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.2.2.3 | [8 empty] | nr | m² | 3 | Ductile iron | T7 – Sanitary and Plumbing Services
4 | 5.3.2.3 | [6 empty] | 3 | Gullies
5 | 5.3.2.3.1 | [8 empty] | nr | nr | 1 | Polypropylene; uPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.2.3.2 | [8 empty] | nr | nr | 2 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.2.3.3 | [8 empty] | nr | nr | 3 | Ductile iron | T7 – Sanitary and Plumbing Services
4 | 5.3.2.4 | [6 empty] | 4 | Storage tanks and vessels | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.3.2.5 | [6 empty] | 5 | Settlement tanks | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.3.2.6 | [6 empty] | 6 | Effluent treatment plant
5 | 5.3.2.6.1 | [8 empty] | nr | nr | 1 | Package Systems | T7 – Sanitary and Plumbing Services
5 | 5.3.2.6.2 | [8 empty] | nr | nr | 2 | Wastewater Treatment - Extended Aeration and Oxidation Ditch Systems | T7 – Sanitary and Plumbing Services
5 | 5.3.2.6.3 | [8 empty] | m² | m² | 3 | Drainage Fields | T7 – Sanitary and Plumbing Services
5 | 5.3.2.6.4 | [8 empty] | nr | nr | 4 | Settlement Tanks | T7 – Sanitary and Plumbing Services
5 | 5.3.2.6.5 | [8 empty] | nr | nr | 5 | Separator Systems | T7 – Sanitary and Plumbing Services
5 | 5.3.2.6.6 | [8 empty] | nr | nr | 6 | Wastewater Treatment - Rotating Biological Contactors and Percolating Filters | T7 – Sanitary and Plumbing Services
5 | 5.3.2.6.7 | [8 empty] | nr | nr | 7 | Wastewater Treatment - Sequencing Batch Reactors | T7 – Sanitary and Plumbing Services
5 | 5.3.2.6.8 | [8 empty] | m² | m² | 8 | Wastewater Treatment - Constructed Wetlands | T7 – Sanitary and Plumbing Services
4 | 5.3.2.7 | [6 empty] | 7 | Dosing equipment
5 | 5.3.2.7.1 | [8 empty] | nr | nr | 1 | Chemical Dosing Pots - Manual Operation | T7 – Sanitary and Plumbing Services
5 | 5.3.2.7.2 | [8 empty] | nr | nr | 2 | Bacterial and Enzyme Drain Dosing Systems | T7 – Sanitary and Plumbing Services
5 | 5.3.2.7.3 | [8 empty] | nr | nr | 3 | Chemical Dosing Pots - Automatic Operation | T7 – Sanitary and Plumbing Services
5 | 5.3.2.7.4 | [8 empty] | nr | nr | 4 | Chemical Dosing - Probes | T7 – Sanitary and Plumbing Services
5 | 5.3.2.7.5 | [8 empty] | nr | nr | 5 | Chemical Dosing - Chemical Feed Units | T7 – Sanitary and Plumbing Services
5 | 5.3.2.7.6 | [8 empty] | nr | nr | 6 | Chemical Dosing - Automatic Units | T7 – Sanitary and Plumbing Services
4 | 5.3.2.8 | [6 empty] | 8 | Sterilisation equipment
5 | 5.3.2.8.1 | [8 empty] | nr | nr | 1 | Ultraviolet Disinfection Unit | T7 – Sanitary and Plumbing Services
5 | 5.3.2.8.2 | [8 empty] | nr | nr | 2 | Ozonation Plant | T7 – Sanitary and Plumbing Services
4 | 5.3.2.9 | [6 empty] | 9 | Thermal insulation
5 | 5.3.2.9.1 | [8 empty] | m² | m² | 1 | Thermal Insulation - Sheet | T7 – Sanitary and Plumbing Services
5 | 5.3.2.9.2 | [8 empty] | m² | m² | 2 | Thermal Insulation - Pipe | T7 – Sanitary and Plumbing Services
4 | 5.3.2.10 | [6 empty] | 10 | Separator Systems for Light Oils - Petrol and Oil
5 | 5.3.2.10.1 | [8 empty] | nr | nr | 1 | Polypropylene; uPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.2.10.2 | [8 empty] | nr | nr | 2 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.2.10.3 | [8 empty] | nr | nr | 3 | Ductile iron | T7 – Sanitary and Plumbing Services
5 | 5.3.2.10.4 | [8 empty] | nr | nr | 4 | Steel | T7 – Sanitary and Plumbing Services
4 | 5.3.2.11 | [6 empty] | 11 | Interceptors - Blowdown and Sumps
5 | 5.3.2.11.1 | [8 empty] | nr | nr | 1 | Polypropylene; uPVC | T7 – Sanitary and Plumbing Services
5 | 5.3.2.11.2 | [8 empty] | nr | nr | 2 | Plastic | T7 – Sanitary and Plumbing Services
5 | 5.3.2.11.3 | [8 empty] | nr | nr | 3 | Ductile iron | T7 – Sanitary and Plumbing Services
5 | 5.3.2.11.4 | [8 empty] | nr | nr | 4 | Steel | T7 – Sanitary and Plumbing Services
4 | 5.3.2.12 | [6 empty] | 12 | Grease Traps | nr | nr |  |  | T7 – Sanitary and Plumbing Services
3 | 5.3.3 |  |  |  |  | 3 | Refuse disposal
4 | 5.3.3.1 | [6 empty] | 1 | Baler | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.3.3.2 | [6 empty] | 2 | Compactor | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.3.3.3 | [6 empty] | 3 | Refuse chutes and ducts | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.3.3.4 | [6 empty] | 4 | Macerators | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.3.3.5 | [6 empty] | 5 | Refuse collection equipment | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.3.3.6 | [6 empty] | 6 | Gas Incinerator | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.3.3.7 | [6 empty] | 7 | Waste Incinerator | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.3.3.8 | [6 empty] | 8 | Wet Scrubber System | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.3.3.9 | [6 empty] | 9 | Fabric Filter System | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.3.3.10 | [6 empty] | 10 | Paper shredders
5 | 5.3.3.10.1 | [8 empty] | nr | nr | 1 | Paper shredders - commercial offices | T6 - Fixed Furniture / Fittings & Service Equipment
5 | 5.3.3.10.2 | [8 empty] | nr | nr | 2 | Paper shredders - industrial types | T6 - Fixed Furniture / Fittings & Service Equipment
4 | 5.3.3.11 | [6 empty] | 11 | Emergency Stop Buttons | nr | nr |  |  | T12 – Safety Systems
2 | 5.4 |  |  | 4 | Water Installations
3 | 5.4.1 |  |  |  |  | 1 | Mains water supply
4 | 5.4.1.1 | [6 empty] | 1 | Pipework In General
5 | 5.4.1.1.X | [8 empty] | nr/m² | m² | X | See SUP - Pipework | T7 – Sanitary and Plumbing Services
5 | 5.4.1.2 | [6 empty] | 2 | Valves
5 | 5.4.1.2.X | [8 empty] | nr | nr | X | See SUP - Valves | T7 – Sanitary and Plumbing Services
4 | 5.4.1.3 | [6 empty] | 3 | Water meters | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.1.4 | [6 empty] | 4 | Rising main to storage tanks | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.1.5 | [6 empty] | 5 | Electrical Trace Heating | nr | m² |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.1.6 | [6 empty] | 6 | Thermal insulation
4 | 5.4.1.6.1 | [8 empty] | m² | m² | 1 | Thermal Insulation - Sheet | T7 – Sanitary and Plumbing Services
4 | 5.4.1.6.2 | [8 empty] | m² | m² | 2 | Thermal Insulation - Pipe | T7 – Sanitary and Plumbing Services
5 | 5.4.2 |  |  |  |  | 2 | Cold water distribution
5 | 5.4.2.1 | [6 empty] | 1 | Pipework In General
3 | 5.4.2.1.X | [8 empty] | nr/m² | m² | X | See SUP - Pipework | T7 – Sanitary and Plumbing Services
4 | 5.4.2.2 | [6 empty] | 2 | Valves
5 | 5.4.2.2.X | [8 empty] | nr | nr | X | See SUP - Valves | T7 – Sanitary and Plumbing Services
5 | 5.4.2.3 | [6 empty] | 3 | Water saving devices | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.2.4 | [6 empty] | 4 | Taps
4 | 5.4.2.4.X | [8 empty] | nr | nr | X | See SUP - Taps | T7 – Sanitary and Plumbing Services
5 | 5.4.2.5 | [6 empty] | 5 | Pumps
4 | 5.4.2.5.X | [8 empty] | nr | nr | X | See SUP - Pumps | T7 – Sanitary and Plumbing Services
4 | 5.4.2.6 | [6 empty] | 6 | Pressurisation units | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.2.7 | [6 empty] | 7 | Pressure booster sets | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.2.8 | [6 empty] | 8 | Cold water storage tanks and cisterns
5 | 5.4.2.8.1 | [8 empty] | nr | nr | 1 | Cold Water Storage Tanks and Cisterns | T7 – Sanitary and Plumbing Services
4 | 5.4.2.8.2 | [8 empty] | nr | nr | 2 | Break Tank and Pump (Fluid Category 5 Backflow Protection) | T7 – Sanitary and Plumbing Services
4 | 5.4.2.8.3 | [8 empty] | nr | nr | 3 | Feed and Expansion (F&E) Tanks | T7 – Sanitary and Plumbing Services
4 | 5.4.2.9 | [6 empty] | 9 | Electrical Trace Heating | nr/m² | m² |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.2.10 | [6 empty] | 10 | Instrumentation and controls
5 | 5.4.2.10.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T7 – Sanitary and Plumbing Services
5 | 5.4.2.11 | [6 empty] | 11 | Thermal insulation
4 | 5.4.2.11.1 | [8 empty] | nr/m² | m² | 1 | Thermal Insulation - Sheet | T7 – Sanitary and Plumbing Services
4 | 5.4.2.11.2 | [8 empty] | nr/m² | m² | 2 | Thermal Insulation - Pipe | T7 – Sanitary and Plumbing Services
5 | 5.4.2.12 | [6 empty] | 12 | Electrical ancillaries
4 | 5.4.2.12.X | [8 empty] | nr | nr | X | See SUP - Electrical ancillaries | T7 – Sanitary and Plumbing Services
5 | 5.4.2.13 | [6 empty] | 13 | Starters
5 | 5.4.2.13.X | [8 empty] | nr | nr | X | See SUP - Starters | T7 – Sanitary and Plumbing Services
4 | 5.4.2.14 | [6 empty] | 14 | Filters
5 | 5.4.2.14.X | [8 empty] | nr | nr | X | See SUP - Filters | T7 – Sanitary and Plumbing Services
4 | 5.4.2.15 | [6 empty] | 15 | Storage tanks
5 | 5.4.2.15.1 | [8 empty] | nr | nr | 1 | Cast iron | T7 – Sanitary and Plumbing Services
4 | 5.4.2.15.2 | [8 empty] | nr | nr | 2 | Steel - galvanised | T7 – Sanitary and Plumbing Services
5 | 5.4.2.15.3 | [8 empty] | nr | nr | 3 | Mild steel, treated | T7 – Sanitary and Plumbing Services
4 | 5.4.2.15.4 | [8 empty] | nr | nr | 4 | Plastic or non-metallic | T7 – Sanitary and Plumbing Services
5 | 5.4.2.16 | [6 empty] | 16 | Rainwater harvesting | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.2.17 | [6 empty] | 17 | Grey water collection pipe systems | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.2.18 | [6 empty] | 18 | Train water points | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.2.19 | [6 empty] | 19 | Vehicle Wash - Air/Water Tower | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.2.20 | [6 empty] | 20 | Vehicle Wash - Bay Cleaning | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.2.21 | [6 empty] | 21 | Vehicle Wash - Jetwash | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.2.22 | [6 empty] | 22 | Vehicle Wash - Vacuum Equipment | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.2.23 | [6 empty] | 23 | Vehicle Wash - Water Reclamation Equipment | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.2.24 | [6 empty] | 24 | Vehicle Washing Equipment | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.2.25 | [6 empty] | 25 | Vehicle Washing Plant | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.3 |  |  |  |  | 3 | Hot water distribution
4 | 5.4.3.1 | [6 empty] | 1 | Instantaneous Electric Water Heaters (Non Drinks Type) | nr/m² | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.3.2 | [6 empty] | 2 | Packaged Electric Water Heaters - Cistern Type (Non Drinks) | nr/m² | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.3.3 | [6 empty] | 3 | Hot and Cold Water Services - General | nr/m² | m² |  |  | T7 – Sanitary and Plumbing Services
3 | 5.4.3.4 | [6 empty] | 4 | Unvented Hot Water Systems | nr/m² | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.3.5 | [6 empty] | 5 | Vented Hot Water Systems | nr/m² | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.3.6 | [6 empty] | 6 | Pipework In General
4 | 5.4.3.6.X | [8 empty] | m² | m² | X | See SUP - Pipework | T7 – Sanitary and Plumbing Services
4 | 5.4.3.7 | [6 empty] | 7 | Valves
4 | 5.4.3.7.X | [8 empty] | nr | nr | X | See SUP - Valves | T7 – Sanitary and Plumbing Services
4 | 5.4.3.8 | [6 empty] | 8 | Water saving devices | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.3.9 | [6 empty] | 9 | Taps
5 | 5.4.3.9.X | [8 empty] | nr | nr | X | See SUP - Taps | T7 – Sanitary and Plumbing Services
5 | 5.4.3.10 | [6 empty] | 10 | Pumps
5 | 5.4.3.10.X | [8 empty] | nr | nr | X | See SUP - Pumps | T7 – Sanitary and Plumbing Services
4 | 5.4.3.11 | [6 empty] | 11 | Heat exchangers
5 | 5.4.3.11.1 | [8 empty] | nr | nr | 1 | Heat Exchangers - Water to Air | T7 – Sanitary and Plumbing Services
4 | 5.4.3.11.2 | [8 empty] | nr | nr | 2 | Plate Recuperator | T7 – Sanitary and Plumbing Services
4 | 5.4.3.11.3 | [8 empty] | nr | nr | 3 | Run Around Heat Recovery Coils | T7 – Sanitary and Plumbing Services
5 | 5.4.3.11.4 | [8 empty] | nr | nr | 4 | Heating Calorifiers - MTHW, HTHW or Steam | T7 – Sanitary and Plumbing Services
4 | 5.4.3.11.5 | [8 empty] | nr | nr | 5 | Heat Recovery Units | T7 – Sanitary and Plumbing Services
5 | 5.4.3.11.6 | [8 empty] | nr | nr | 6 | Heat Exchangers - Indirect Gas Fired to Air | T7 – Sanitary and Plumbing Services
4 | 5.4.3.11.7 | [8 empty] | nr | nr | 7 | Heat Exchangers - Water to Water | T7 – Sanitary and Plumbing Services
5 | 5.4.3.11.8 | [8 empty] | nr | nr | 8 | Plate Heat Exchangers | T7 – Sanitary and Plumbing Services
5 | 5.4.3.11.9 | [8 empty] | nr | nr | 9 | Electric/Air Heater | T7 – Sanitary and Plumbing Services
5 | 5.4.3.12 | [6 empty] | 12 | Hot Water Calorifiers - Heated by LTHW
5 | 5.4.3.12.1 | [8 empty] | nr | nr | 1 | Copper | T7 – Sanitary and Plumbing Services
5 | 5.4.3.12.2 | [8 empty] | nr | nr | 2 | Steel, galvanised | T7 – Sanitary and Plumbing Services
5 | 5.4.3.13 | [6 empty] | 13 | Hot Water Calorifiers - Heated by MTHW, HTHW or Steam | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.3.14 | [6 empty] | 14 | Hot Water Calorifiers - Heated by Electricity | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.3.15 | [6 empty] | 15 | Hot Water Cylinders | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.3.16 | [6 empty] | 16 | Thermal Storage Cylinder (Individual Dwellings for DHWS) | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.3.17 | [6 empty] | 17 | Electrical Trace Heating | nr/m² | m² |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.3.18 | [6 empty] | 18 | Hot water storage tanks
5 | 5.4.3.18.1 | [8 empty] | nr | nr | 1 | Open | T7 – Sanitary and Plumbing Services
4 | 5.4.3.18.2 | [8 empty] | nr | nr | 2 | Closed (with membrane) | T7 – Sanitary and Plumbing Services
4 | 5.4.3.18.3 | [8 empty] | nr | nr | 3 | Unvented HW | T7 – Sanitary and Plumbing Services
4 | 5.4.3.19 | [6 empty] | 19 | Immersion heaters | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.3.20 | [6 empty] | 20 | Insulation combination units | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.3.21 | [6 empty] | 21 | Water softeners
4 | 5.4.3.21.1 | [8 empty] | nr | nr | 1 | Ion Exchange Plant - Base Exchange Softening - Commercial | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.2 | [8 empty] | nr | nr | 2 | Ion Exchange Plant - Base Exchange Softening - Domestic (capacity usually below 50 litres) | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.3 | [8 empty] | nr | nr | 3 | Special Water Treatment Devices | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.4 | [8 empty] | nr | nr | 4 | Water Treatment - Iron Removal | T7 – Sanitary and Plumbing Services
4 | 5.4.3.21.5 | [8 empty] | nr | nr | 5 | Water Treatment - pH Correction | T7 – Sanitary and Plumbing Services
4 | 5.4.3.21.6 | [8 empty] | nr | nr | 6 | Water Treatment - Activated Carbon Filtration | T7 – Sanitary and Plumbing Services
4 | 5.4.3.21.7 | [8 empty] | nr | nr | 7 | Water Treatment - Turbidity Treatment | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.8 | [8 empty] | nr | nr | 8 | Water Filtration and Conditioning - Active Carbon Cartridge Filter | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.9 | [8 empty] | nr | nr | 9 | Water Filtration and Conditioning - Bacterial Removal Filters | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.10 | [8 empty] | nr | nr | 10 | Water Filtration and Conditioning - Sealed or Combined Type | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.11 | [8 empty] | nr | nr | 11 | Water Filtration and Conditioning - Sediment Removal Filters | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.12 | [8 empty] | nr | nr | 12 | Water Filtration and Conditioning - Magnetic Water Conditioners | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.13 | [8 empty] | nr | nr | 13 | Reverse Osmosis | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.14 | [8 empty] | nr | nr | 14 | Chlorine Dioxide Low Dosing Domestic Water Systems | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.15 | [8 empty] | nr | nr | 15 | Carbon Dioxide Dosing System | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.16 | [8 empty] | nr | nr | 16 | Chlorine Analyser/Controller System | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.17 | [8 empty] | nr | nr | 17 | Concentrate Filling Station (Haemodialysis) | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.18 | [8 empty] | nr | nr | 18 | Water Purification and Demineralisation Equipment | T7 – Sanitary and Plumbing Services
5 | 5.4.3.21.19 | [8 empty] | nr | nr | 19 | Chemical dosing system | T7 – Sanitary and Plumbing Services
5 | 5.4.3.22 | [6 empty] | 22 | Instrumentation and controls
5 | 5.4.3.22.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T7 – Sanitary and Plumbing Services
5 | 5.4.3.23 | [6 empty] | 23 | Thermal insulation
5 | 5.4.3.23.1 | [8 empty] | m² | m² | 1 | Thermal Insulation - Sheet | T7 – Sanitary and Plumbing Services
5 | 5.4.3.23.2 | [8 empty] | m² | m² | 2 | Thermal Insulation - Pipe | T7 – Sanitary and Plumbing Services
5 | 5.4.3.24 | [6 empty] | 24 | Gas-Fired Heater Batteries - Indirect | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.3.25 | [6 empty] | 25 | Expansion vessel | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.3.26 | [6 empty] | 26 | Vacuum Degasser | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 5.4.4 |  |  |  |  | 4 | Local hot water distribution
4 | 5.4.4.1 | [6 empty] | 1 | Instant water heaters
5 | 5.4.4.1.1 | [8 empty] | nr | nr | 1 | Direct Fired Water Heaters | T7 – Sanitary and Plumbing Services
5 | 5.4.4.1.2 | [8 empty] | nr | nr | 2 | Instantaneous Electric Water Heaters (Non Drinks Type) | T7 – Sanitary and Plumbing Services
4 | 5.4.4.2 | [6 empty] | 2 | Under-sink, multipoint and over sink units | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 5.4.5 |  |  |  |  | 5 | Steam and condensate distribution
4 | 5.4.5.1 | [6 empty] | 1 | Steam services pipe work systems
3 | 5.4.5.1.1 | [8 empty] | nr/m² | m² | 1 | Mild steel | T8 – Mechanical Services
4 | 5.4.5.1.2 | [8 empty] | nr/m² | m² | 2 | Steel, galvanised | T8 – Mechanical Services
5 | 5.4.5.2 | [6 empty] | 2 | Valves
5 | 5.4.5.2.X | [8 empty] | nr | nr | X | See SUP - Valves | T8 – Mechanical Services
4 | 5.4.5.3 | [6 empty] | 3 | Steam reduction stations | nr | nr |  |  | T8 – Mechanical Services
3 | 5.4.5.4 | [6 empty] | 4 | Condensate receivers | nr | nr |  |  | T8 – Mechanical Services
4 | 5.4.5.5 | [6 empty] | 5 | Condensate pump sets
5 | 5.4.5.5.1 | [8 empty] | nr | nr | 1 | Large Float / Automatic Condensate Steam Pump | T8 – Mechanical Services
5 | 5.4.5.5.2 | [8 empty] | nr | nr | 2 | Ogden Steam Pump | T8 – Mechanical Services
4 | 5.4.5.6 | [6 empty] | 6 | Steam connection outlets | nr | nr |  |  | T8 – Mechanical Services
5 | 5.4.5.7 | [6 empty] | 7 | Taps
4 | 5.4.5.7.X | [8 empty] | nr | nr | X | See SUP - Taps | T8 – Mechanical Services
4 | 5.4.5.8 | [6 empty] | 8 | Heat Exchangers - Steam to Air | N/A | nr |  |  | T8 – Mechanical Services
4 | 5.4.5.9 | [6 empty] | 9 | Heating Calorifiers - MTHW, HTHW or Steam
5 | 5.4.5.9.1 | [8 empty] | nr | nr | 1 | Copper | T8 – Mechanical Services
5 | 5.4.5.9.2 | [8 empty] | nr | nr | 2 | Mild steel | T8 – Mechanical Services
4 | 5.4.5.9.3 | [8 empty] | nr | nr | 3 | Steel, galvanised | T8 – Mechanical Services
4 | 5.4.5.10 | [6 empty] | 10 | Hot Water Calorifiers - Heated by MTHW, HTHW or Steam | nr | nr |  |  | T8 – Mechanical Services
5 | 5.4.5.11 | [6 empty] | 11 | Instrumentation and controls
4 | 5.4.5.11.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T8 – Mechanical Services
4 | 5.4.5.12 | [6 empty] | 12 | Thermal insulation
5 | 5.4.5.12.1 | [8 empty] | nr/m² | m² | 1 | Thermal Insulation - Sheet | T8 – Mechanical Services
5 | 5.4.5.12.2 | [8 empty] | nr/m² | m² | 2 | Thermal Insulation - Pipe | T8 – Mechanical Services
5 | 5.4.5.13 | [6 empty] | 13 | Flash Steam Vessel | nr | nr |  |  | T8 – Mechanical Services
4 | 5.4.5.14 | [6 empty] | 14 | Steam Trap Monitor | nr | nr |  |  | T8 – Mechanical Services
4 | 5.4.5.15 | [6 empty] | 15 | Hotwell/Boiler Feed Tank | nr | nr |  |  | T8 – Mechanical Services
5 | 5.4.5.16 | [6 empty] | 16 | Steam Meter | nr | nr |  |  | T8 – Mechanical Services
4 | 5.5 |  |  | 5 | Heat Source
5 | 5.5.1 |  |  |  |  | 1 | Heat Source
5 | 5.5.1.1 | [6 empty] | 1 | Boilers biomass | nr | nr |  |  | T8 – Mechanical Services
4 | 5.5.1.2 | [6 empty] | 2 | Boilers gas/oil
4 | 5.5.1.2.1 | [8 empty] | nr | nr | 1 | Atmospheric Gas Burner - Free Standing Boiler | T8 – Mechanical Services
4 | 5.5.1.2.2 | [8 empty] | nr | nr | 2 | Atmospheric Gas Burner - Condensing Boiler | T8 – Mechanical Services
4 | 5.5.1.2.3 | [8 empty] | nr | nr | 3 | Blown Gas Burner Condensing Boiler | T8 – Mechanical Services
2 | 5.5.1.2.4 | [8 empty] | nr | nr | 4 | Blown Gas Burner Modular Boiler | T8 – Mechanical Services
3 | 5.5.1.2.5 | [8 empty] | nr | nr | 5 | Forced Draught Gas Condensing Boiler | T8 – Mechanical Services
4 | 5.5.1.2.6 | [8 empty] | nr | nr | 6 | Oil Condensing Boiler - Forced Draught (Pressure Jet) | T8 – Mechanical Services
4 | 5.5.1.2.7 | [8 empty] | nr | nr | 7 | Boilers MTHW up to 120ºC | T8 – Mechanical Services
5 | 5.5.1.2.8 | [8 empty] | nr | nr | 8 | Boilers LTHW up to 95ºC | T8 – Mechanical Services
5 | 5.5.1.2.9 | [8 empty] | nr | nr | 9 | Atmospheric Gas Burner Boiler - Small and/or Wall Hung for Domestic/Light Commercial Installation | T8 – Mechanical Services
5 | 5.5.1.2.10 | [8 empty] | nr | nr | 10 | Combination Atmospheric Burner Gas Boiler | T8 – Mechanical Services
5 | 5.5.1.2.11 | [8 empty] | nr | nr | 11 | Atmospheric Gas Burner/Condensing Combination Boiler | T8 – Mechanical Services
5 | 5.5.1.2.12 | [8 empty] | nr | nr | 12 | Atmospheric Gas Burners | T8 – Mechanical Services
5 | 5.5.1.2.13 | [8 empty] | nr | nr | 13 | Blown Gas Burner | T8 – Mechanical Services
5 | 5.5.1.2.14 | [8 empty] | nr | nr | 14 | Forced Draught Gas Burner | T8 – Mechanical Services
5 | 5.5.1.2.15 | [8 empty] | nr | nr | 15 | Oil Burner - Forced Draught (Pressure Jet) | T8 – Mechanical Services
5 | 5.5.1.2.16 | [8 empty] | nr | nr | 16 | Light Oil Vaporising Pot Burner | T8 – Mechanical Services
5 | 5.5.1.2.17 | [8 empty] | nr | nr | 17 | Gas/Oil Burners - Dual Fuel | T8 – Mechanical Services
5 | 5.5.1.2.18 | [8 empty] | nr | nr | 18 | Medium Temperature Hot Water (MTHW) Boilers - Operational Checks | T8 – Mechanical Services
5 | 5.5.1.3 | [6 empty] | 3 | Coal Fired Boilers - Coal and Ash Handling inc | nr | nr |  |  | T8 – Mechanical Services
5 | 5.5.1.4 | [6 empty] | 4 | Coal Fired Boilers - Bunkers and Conveyors | nr | nr |  |  | T8 – Mechanical Services
5 | 5.5.1.5 | [6 empty] | 5 | Ash Handling System | nr | nr |  |  | T8 – Mechanical Services
5 | 5.5.1.6 | [6 empty] | 6 | Coal Feed Mechanisms - Under Feed Stokers | nr | nr |  |  | T8 – Mechanical Services
5 | 5.5.1.7 | [6 empty] | 7 | Coal Feed Mechanisms - Chain Grate Stokers | nr | nr |  |  | T8 – Mechanical Services
5 | 5.5.1.8 | [6 empty] | 8 | Storage Silo - Coal | nr | nr |  |  | T8 – Mechanical Services
5 | 5.5.1.9 | [6 empty] | 9 | Boilers electric
4 | 5.5.1.9.1 | [8 empty] | nr | nr | 1 | Electric Boilers | T8 – Mechanical Services
4 | 5.5.1.9.2 | [8 empty] | nr | nr | 2 | Electrode Boilers | T8 – Mechanical Services
4 | 5.5.1.10 | [6 empty] | 10 | Packaged steam generators
4 | 5.5.1.10.1 | [8 empty] | nr | nr | 1 | Packaged Steam Generators | T8 – Mechanical Services
4 | 5.5.1.10.2 | [8 empty] | nr | nr | 2 | Packaged Steam Generators - Electric | T8 – Mechanical Services
4 | 5.5.1.11 | [6 empty] | 11 | Waste and wood burning appliances – fire safety circuits | nr | nr |  |  | T8 – Mechanical Services
4 | 5.5.1.12 | [6 empty] | 12 | Waste and wood burning appliances - combustion chamber | nr | nr |  |  | T8 – Mechanical Services
5 | 5.5.1.13 | [6 empty] | 13 | Waste and wood burning appliances – Boiler | nr | nr |  |  | T8 – Mechanical Services
5 | 5.5.1.14 | [6 empty] | 14 | Storage silo - wood chip / pellets | nr | nr |  |  | T8 – Mechanical Services
4 | 5.5.1.15 | [6 empty] | 15 | Central combined heat and power plant
5 | 5.5.1.15.1 | [8 empty] | nr | nr | 1 | Combined Heat and Power (CHP) - Diesel Fuel Engine | T8 – Mechanical Services
5 | 5.5.1.15.2 | [8 empty] | nr | nr | 2 | Combined Heat and Power (CHP) - Gaseous Fuel Engine | T8 – Mechanical Services
4 | 5.5.1.16 | [6 empty] | 16 | Heat pumps
4 | 5.5.1.16.1 | [8 empty] | nr | nr | 1 | Air to Water Heat Pump | T8 – Mechanical Services
4 | 5.5.1.16.2 | [8 empty] | nr | nr | 2 | Water to Water Heat Pump | T8 – Mechanical Services
4 | 5.5.1.17 | [6 empty] | 17 | Ground source heating | nr | nr |  |  | T8 – Mechanical Services
4 | 5.5.1.18 | [6 empty] | 18 | Pumps
5 | 5.5.1.18.X | [8 empty] | nr | nr | X | See SUP - Pumps | T8 – Mechanical Services
5 | 5.5.1.19 | [6 empty] | 19 | Solar thermal panels
4 | 5.5.1.19.1 | [8 empty] | nr | nr | 1 | Solar Hot Water Panels and Similar Collecting Devices - Plate Type | T8 – Mechanical Services
5 | 5.5.1.19.2 | [8 empty] | nr | nr | 2 | Solar Hot Water Panels and Similar Collecting Devices - Vacuum Tube Type | T8 – Mechanical Services
5 | 5.5.1.20 | [6 empty] | 20 | Water tanks |  | nr
4 | 5.5.1.20.1 | [8 empty] | nr | nr | 1 | Cold Water Storage Tanks and Cisterns | T8 – Mechanical Services
4 | 5.5.1.20.2 | [8 empty] | nr | nr | 2 | Feed and Expansion (F&E) Tanks | T8 – Mechanical Services
5 | 5.5.1.21 | [6 empty] | 21 | Instrumentation and controls
4 | 5.5.1.21.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T8 – Mechanical Services
5 | 5.5.1.22 | [6 empty] | 22 | Forced draft fans | nr | nr |  |  | T8 – Mechanical Services
5 | 5.5.1.23 | [6 empty] | 23 | Gantries | nr | nr |  |  | T8 – Mechanical Services
4 | 5.5.1.24 | [6 empty] | 24 | Flues - All Combustible Fuels
5 | 5.5.1.24.1 | [8 empty] | nr | nr | 1 | Flues outside and inside | T8 – Mechanical Services
5 | 5.5.1.24.2 | [8 empty] | nr | nr | 2 | Flues inside (brick or concrete) | T8 – Mechanical Services
4 | 5.5.1.24.3 | [8 empty] | nr | nr | 3 | Flues inside (mild steel) | T8 – Mechanical Services
5 | 5.5.1.24.4 | [8 empty] | nr | nr | 4 | Flues inside (stainless steel) | T8 – Mechanical Services
4 | 5.5.1.25 | [6 empty] | 25 | Flue Gas Oxygen Control | nr | nr |  |  | T8 – Mechanical Services
4 | 5.5.1.26 | [6 empty] | 26 | Flues - Fan Dilution Units | nr | nr |  |  | T8 – Mechanical Services
4 | 5.5.1.28 | [6 empty] | 28 | Boilers steam | nr | nr |  |  | T8 – Mechanical Services
5 | 5.5.1.29 | [6 empty] | 29 | Sample Cooler | nr | nr |  |  | T8 – Mechanical Services
5 | 5.5.1.30 | [6 empty] | 30 | Electrical ancillaries
5 | 5.5.1.30.X | [8 empty] | nr | nr | X | See SUP - Electrical ancillaries | T8 – Mechanical Services
5 | 5.5.1.31 | [6 empty] | 31 | Starters
4 | 5.5.1.31.X | [8 empty] | nr | nr | X | See SUP - Starters | T8 – Mechanical Services
4 | 5.5.1.32 | [6 empty] | 32 | Expansion vessels | nr | nr |  |  | T8 – Mechanical Services
4 | 5.5.1.33 | [6 empty] | 33 | Valves
4 | 5.5.1.33.X | [8 empty] | nr | nr | X | See SUP - Valves | T8 – Mechanical Services
4 | 5.5.1.34 | [6 empty] | 34 | Deaerator | nr | nr |  |  | T8 – Mechanical Services
5 | 5.5.1.35 | [6 empty] | 35 | Biomass Fuel Supply Moving Floor | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6 |  |  | 6 | Space Heating and Air Conditioning
5 | 5.6.1 |  |  |  |  | 1 | Central Heating
4 | 5.6.1.1 | [6 empty] | 1 | Pipework In General
4 | 5.6.1.1.X | [8 empty] | m²/nr | m² | X | See SUP - Pipework | T8 – Mechanical Services
5 | 5.6.1.2 | [6 empty] | 2 | Air Dirt Separators | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.1.3 | [6 empty] | 3 | Heat emission units
4 | 5.6.1.3.1 | [8 empty] | m²/nr | nr | 1 | Heat Emitters - Unit Heaters | T8 – Mechanical Services
2 | 5.6.1.3.2 | [8 empty] | m²/nr | nr | 2 | Heat Emitters - Natural Convectors, Finned Convectors and Perimeter (Skirting) Heating | T8 – Mechanical Services
3 | 5.6.1.3.3 | [8 empty] | m²/nr | nr | 3 | Heat Emitters - Radiant Strip | T8 – Mechanical Services
4 | 5.6.1.3.4 | [8 empty] | nr | nr | 4 | Radiators — aluminium | T8 – Mechanical Services
5 | 5.6.1.3.5 | [8 empty] | nr | nr | 5 | Radiators — cast iron | T8 – Mechanical Services
5 | 5.6.1.3.6 | [8 empty] | nr | nr | 6 | Radiators — steel | T8 – Mechanical Services
5 | 5.6.1.4 | [6 empty] | 4 | Underfloor heating
5 | 5.6.1.4.1 | [8 empty] | m²/nr | m² | 1 | Underfloor heating - wet | T8 – Mechanical Services
4 | 5.6.1.4.2 | [8 empty] | m²/nr | m² | 2 | Underfloor heating - electric | T8 – Mechanical Services
4 | 5.6.1.5 | [6 empty] | 5 | Heating ceiling panels | m²/nr | m² |  |  | T8 – Mechanical Services
5 | 5.6.1.6 | [6 empty] | 6 | Warm air heating | m²/nr | m² |  |  | T8 – Mechanical Services
5 | 5.6.1.7 | [6 empty] | 7 | Convection systems | m²/nr | m² |  |  | T8 – Mechanical Services
5 | 5.6.1.8 | [6 empty] | 8 | Fan assisted convection systems
5 | 5.6.1.8.1 | [8 empty] | nr | nr | 1 | Heat Emitters - Fan Convector Type (LTHW or Steam) | T8 – Mechanical Services
5 | 5.6.1.8.2 | [8 empty] | nr | nr | 2 | Heat Emitters - Fan Convector Type (Electric) | T8 – Mechanical Services
5 | 5.6.1.9 | [6 empty] | 9 | Cable heating systems | m²/nr | m² |  |  | T8 – Mechanical Services
4 | 5.6.1.10 | [6 empty] | 10 | Plenum air-heating systems | m²/nr | m² |  |  | T8 – Mechanical Services
5 | 5.6.1.11 | [6 empty] | 11 | Electric Heaters - Radiators, Tubular Heaters and Oil Filled Heaters | m²/nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.1.12 | [6 empty] | 12 | Heated towel rails | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.1.13 | [6 empty] | 13 | Valves
4 | 5.6.1.13.X | [8 empty] | nr | nr | X | See SUP - Valves | T8 – Mechanical Services
4 | 5.6.1.14 | [6 empty] | 14 | Ductwork systems
4 | 5.6.1.14.X | [8 empty] | m²/nr | m² | X | See SUP - Ductwork | T8 – Mechanical Services
5 | 5.6.1.15 | [6 empty] | 15 | Air Handling Units | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.1.16 | [6 empty] | 16 | Gas-Fired Heater Batteries - Indirect | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.1.17 | [6 empty] | 17 | Ventilation Grilles - External | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.1.18 | [6 empty] | 18 | Louvres | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.1.19 | [6 empty] | 19 | Bird Screens | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.1.20 | [6 empty] | 20 | Insect Screens | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.1.21 | [6 empty] | 21 | Ventilation Grilles - Internal | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.1.22 | [6 empty] | 22 | Ventilation Diffusers | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.1.23 | [6 empty] | 23 | Plate recuperator | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.1.24 | [6 empty] | 24 | Thermal wheel | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.1.25 | [6 empty] | 25 | Duct heat battery – electric | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.1.26 | [6 empty] | 26 | Instrumentation and controls
4 | 5.6.1.26.X | [8 empty] | nr | nr / System | X | See SUP - Controllers and sensors | T8 – Mechanical Services
4 | 5.6.1.27 | [6 empty] | 27 | Thermal insulation
4 | 5.6.1.27.1 | [8 empty] | m²/nr | m² | 1 | Thermal Insulation - Sheet | T8 – Mechanical Services
4 | 5.6.1.27.2 | [8 empty] | m²/nr | m² | 2 | Thermal Insulation - Pipe | T8 – Mechanical Services
4 | 5.6.1.28 | [6 empty] | 28 | Actuators
4 | 5.6.1.28.X | [8 empty] | nr | nr | X | See SUP - Actuators | T8 – Mechanical Services
4 | 5.6.1.29 | [6 empty] | 29 | Expansion vessels | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.1.30 | [6 empty] | 30 | Pumps
4 | 5.6.1.30.X | [8 empty] | nr | nr | X | See SUP - Pumps | T8 – Mechanical Services
4 | 5.6.1.31 | [6 empty] | 31 | Heat Interface Unit
5 | 5.6.1.31.1 | [8 empty] | nr | nr | 1 | Direct | T8 – Mechanical Services
4 | 5.6.1.31.2 | [8 empty] | nr | nr | 2 | Indirect | T8 – Mechanical Services
5 | 5.6.2 |  |  |  |  | 2 | Local heating
5 | 5.6.2.1 | [6 empty] | 1 | Heat emitters
4 | 5.6.2.1.1 | [8 empty] | nr | nr | 1 | Oil Fired Space Heaters | T8 – Mechanical Services
5 | 5.6.2.1.2 | [8 empty] | nr | nr | 2 | LTHW Overdoor Air Curtain/Heater | T8 – Mechanical Services
4 | 5.6.2.1.3 | [8 empty] | nr | nr | 3 | Gas Fired Ceramic Plaque Infra-Red Heaters | T8 – Mechanical Services
4 | 5.6.2.1.4 | [8 empty] | nr | nr | 4 | Gas Radiant Tube Heaters | T8 – Mechanical Services
5 | 5.6.2.1.5 | [8 empty] | nr | nr | 5 | Gas Fired Radiant Heaters | T8 – Mechanical Services
4 | 5.6.2.1.6 | [8 empty] | nr | nr | 6 | Electric Heaters - Radiators, Tubular Heaters and Oil Filled Heaters | T8 – Mechanical Services
5 | 5.6.2.1.7 | [8 empty] | nr | nr | 7 | Gas Fire | T8 – Mechanical Services
5 | 5.6.2.1.8 | [8 empty] | nr | nr | 8 | Gas Fired Unit Heaters | T8 – Mechanical Services
3 | 5.6.2.1.9 | [8 empty] | nr | nr | 9 | Electric Overdoor Air Curtain/Heater | T8 – Mechanical Services
4 | 5.6.2.1.10 | [8 empty] | nr | nr | 10 | Gas Fired Natural and Fan Assisted Heaters - Conventional and Balanced Flue | T8 – Mechanical Services
5 | 5.6.2.2 | [6 empty] | 2 | Flues
5 | 5.6.2.2.1 | [8 empty] | nr | nr | 1 | Steel | T8 – Mechanical Services
5 | 5.6.2.3 | [6 empty] | 3 | Instrumentation and controls
5 | 5.6.2.3.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T8 – Mechanical Services
5 | 5.6.3 |  |  |  |  | 3 | Central cooling
5 | 5.6.3.1 | [6 empty] | 1 | Chilled beams | m²/nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.3.2 | [6 empty] | 2 | Terminal units – fan coils | m²/nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.3.3 | [6 empty] | 3 | Terminal units – VAV
5 | 5.6.3.3.1 | [8 empty] | m²/nr | nr | 1 | Terminal Units Vav - Self Powered | T8 – Mechanical Services
5 | 5.6.3.3.2 | [8 empty] | m²/nr | nr | 2 | Terminal Units Vav - Fan Powered | T8 – Mechanical Services
4 | 5.6.3.3.3 | [8 empty] | m²/nr | nr | 3 | Terminal Units Vav - Pneumatic Powered | T8 – Mechanical Services
5 | 5.6.3.4 | [6 empty] | 4 | Terminal units – VRV | m²/nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.3.5 | [6 empty] | 5 | Chillers
5 | 5.6.3.5.1 | [8 empty] | nr | nr | 1 | Packaged Chiller Units | T8 – Mechanical Services
3 | 5.6.3.5.2 | [8 empty] | nr | nr | 2 | Lithium Bromide/Water Absorption Chillers | T8 – Mechanical Services
4 | 5.6.3.5.3 | [8 empty] | nr | nr | 3 | Gas Fired Absorption Chiller Up to 18kw Cooling Capacity | T8 – Mechanical Services
4 | 5.6.3.5.4 | [8 empty] | nr | nr | 4 | Condensers - Water Cooled | T8 – Mechanical Services
4 | 5.6.3.5.5 | [8 empty] | nr | nr | 5 | Condensers - Air Cooled | T8 – Mechanical Services
5 | 5.6.3.5.6 | [8 empty] | nr | nr | 6 | Dry Coolers | T8 – Mechanical Services
5 | 5.6.3.5.7 | [8 empty] | nr | nr | 7 | Refrigeration Evaporators | T8 – Mechanical Services
5 | 5.6.3.5.8 | [8 empty] | nr | nr | 8 | Solar Thermal Absorption Chillers | T8 – Mechanical Services
4 | 5.6.3.6 | [6 empty] | 6 | Central refrigeration plant | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.3.7 | [6 empty] | 7 | Cooling towers
5 | 5.6.3.7.1 | [8 empty] | nr | nr | 1 | Ceramic | T8 – Mechanical Services
5 | 5.6.3.7.2 | [8 empty] | nr | nr | 2 | Epoxy treated metal | T8 – Mechanical Services
5 | 5.6.3.7.3 | [8 empty] | nr | nr | 3 | Galvanised metal | T8 – Mechanical Services
5 | 5.6.3.7.4 | [8 empty] | nr | nr | 4 | Stainless steel | T8 – Mechanical Services
5 | 5.6.3.8 | [6 empty] | 8 | Adiabatic Coolers | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.3.9 | [6 empty] | 9 | Pipework systems
5 | 5.6.3.9.X | [8 empty] | m²/nr | m² | X | See SUP - Pipework | T8 – Mechanical Services
5 | 5.6.3.10 | [6 empty] | 10 | Valves
4 | 5.6.3.10.X | [8 empty] | nr | nr | X | See SUP - Valves | T8 – Mechanical Services
4 | 5.6.3.11 | [6 empty] | 11 | Pumps
5 | 5.6.3.11.X | [8 empty] | nr | nr | X | See SUP - Pumps | T8 – Mechanical Services
5 | 5.6.3.12 | [6 empty] | 12 | Ductwork systems
5 | 5.6.3.12.X | [8 empty] | m²/nr | m² | X | See SUP - Ductwork | T8 – Mechanical Services
5 | 5.6.3.13 | [6 empty] | 13 | Louvres | m²/nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.3.14 | [6 empty] | 14 | Bird Screens | m²/nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.3.15 | [6 empty] | 15 | Insect Screens | m²/nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.3.16 | [6 empty] | 16 | Air handling units
5 | 5.6.3.16.1 | [8 empty] | nr | nr | 1 | External located | T8 – Mechanical Services
5 | 5.6.3.16.2 | [8 empty] | nr | nr | 2 | Internal located | T8 – Mechanical Services
5 | 5.6.3.17 | [6 empty] | 17 | Belt drives | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.3.18 | [6 empty] | 18 | Instrumentation and controls
5 | 5.6.3.18.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T8 – Mechanical Services
4 | 5.6.3.19 | [6 empty] | 19 | Thermal insulation
5 | 5.6.3.19.1 | [8 empty] | nr (m²) | m² | 1 | Thermal Insulation - Sheet | T8 – Mechanical Services
4 | 5.6.3.19.2 | [8 empty] | nr (m²) | m² | 2 | Thermal Insulation - Pipe | T8 – Mechanical Services
5 | 5.6.3.20 | [6 empty] | 20 | Compressors
4 | 5.6.3.20.X | [8 empty] | nr | nr / System | X | See SUP - Compressors | T8 – Mechanical Services
4 | 5.6.3.21 | [6 empty] | 21 | Electrical ancillaries
4 | 5.6.3.21.X | [8 empty] | nr | nr | X | See SUP - Electrical ancillaries | T8 – Mechanical Services
4 | 5.6.3.22 | [6 empty] | 22 | Starters
5 | 5.6.3.22.X | [8 empty] | nr | nr | X | See SUP - Starters | T8 – Mechanical Services
5 | 5.6.3.23 | [6 empty] | 23 | Actuators
4 | 5.6.3.23.X | [8 empty] | nr | nr | X | See SUP - Actuators | T8 – Mechanical Services
4 | 5.6.3.24 | [6 empty] | 24 | Side Stream Filtration Units | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.4 |  |  |  |  | 4 | Local cooling
4 | 5.6.4.1 | [6 empty] | 1 | Air conditioning units
5 | 5.6.4.1.1 | [8 empty] | nr | nr | 1 | DX Split Systems (With Gas, Electric or Hot Water Heaters) | T8 – Mechanical Services
5 | 5.6.4.1.2 | [8 empty] | nr | nr | 2 | Data Centre Cooling Plant - Direct Expansion (DX) | T8 – Mechanical Services
4 | 5.6.4.2 | [6 empty] | 2 | Pipework systems
5 | 5.6.4.2.X | [8 empty] | nr (m²) | m² | X | See SUP - Pipework | T8 – Mechanical Services
4 | 5.6.4.3 | [6 empty] | 3 | Refrigerant Distribution System | nr (m²) | m² |  |  | T8 – Mechanical Services
5 | 5.6.4.4 | [6 empty] | 4 | Valves
4 | 5.6.4.4.X | [8 empty] | nr | nr | X | See SUP - Valves | T8 – Mechanical Services
5 | 5.6.4.5 | [6 empty] | 5 | Ductwork systems
4 | 5.6.4.5.X | [8 empty] | nr (m²) | m² | X | See SUP - Ductwork | T8 – Mechanical Services
5 | 5.6.4.6 | [6 empty] | 6 | Ventilation Grilles - External | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.4.7 | [6 empty] | 7 | Louvres | m²/nr | nr |  |  | T8 – Mechanical Services
3 | 5.6.4.8 | [6 empty] | 8 | Bird Screens | m²/nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.4.9 | [6 empty] | 9 | Insect Screens | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.4.10 | [6 empty] | 10 | Ventilation Grilles - Internal | m²/nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.4.11 | [6 empty] | 11 | Ventilation Diffusers | m²/nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.4.12 | [6 empty] | 12 | Instrumentation and controls
5 | 5.6.4.12.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T8 – Mechanical Services
5 | 5.6.4.13 | [6 empty] | 13 | Thermal insulation
5 | 5.6.4.13.1 | [8 empty] | nr (m²) | m² | 1 | Thermal Insulation - Sheet | T8 – Mechanical Services
5 | 5.6.4.13.2 | [8 empty] | nr (m²) | m² | 2 | Thermal Insulation - Pipe | T8 – Mechanical Services
4 | 5.6.4.14 | [6 empty] | 14 | Heat pumps
4 | 5.6.4.14.1 | [8 empty] | nr | nr | 1 | Air to Water Heat Pump | T8 – Mechanical Services
5 | 5.6.4.14.2 | [8 empty] | nr | nr | 2 | Water to Water Heat Pump | T8 – Mechanical Services
4 | 5.6.4.14.3 | [8 empty] | nr | nr | 3 | Brine to Water Heat Pump | T8 – Mechanical Services
5 | 5.6.4.15 | [6 empty] | 15 | Actuators
4 | 5.6.4.15.X | [8 empty] | nr | nr | X | See SUP - Actuators | T8 – Mechanical Services
4 | 5.6.4.16 | [6 empty] | 16 | Chilled and Condenser Water Systems | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.5 |  |  |  |  | 5 | Central heating and cooling
4 | 5.6.5.1 | [6 empty] | 1 | Terminal units – fan coils
4 | 5.6.5.1.1 | [8 empty] | m²/nr | nr | 1 | Terminal Units - Fan Coil | T8 – Mechanical Services
4 | 5.6.5.1.2 | [8 empty] | m²/nr | nr | 2 | Variable Refrigerant Flow (VRF) Indoor Units | T8 – Mechanical Services
4 | 5.6.5.2 | [6 empty] | 2 | Terminal units – VAV
5 | 5.6.5.2.1 | [8 empty] | m²/nr | nr | 1 | Terminal Units Vav - Self Powered | T8 – Mechanical Services
4 | 5.6.5.2.2 | [8 empty] | m²/nr | nr | 2 | Terminal Units Vav - Fan Powered | T8 – Mechanical Services
5 | 5.6.5.2.3 | [8 empty] | m²/nr | nr | 3 | Terminal Units Vav - Pneumatic Powered | T8 – Mechanical Services
5 | 5.6.5.3 | [6 empty] | 3 | Reverse cycle heat pump systems
4 | 5.6.5.3.1 | [8 empty] | nr | nr | 1 | DX Split Systems (With Gas, Electric or Hot Water Heaters) | T8 – Mechanical Services
5 | 5.6.5.3.2 | [8 empty] | nr | nr | 2 | Data Centre Cooling Plant - Chilled Water | T8 – Mechanical Services
5 | 5.6.5.3.3 | [8 empty] | nr | nr | 3 | Data Centre Cooling Plant - Direct Expansion (DX) | T8 – Mechanical Services
5 | 5.6.5.3.4 | [8 empty] | nr | nr | 4 | Variable Refrigerant Flow (VRF) Indoor Units | T8 – Mechanical Services
4 | 5.6.5.3.5 | [8 empty] | nr | nr | 5 | Condensers - Air Cooled | T8 – Mechanical Services
5 | 5.6.5.4 | [6 empty] | 4 | Chillers
4 | 5.6.5.4.1 | [8 empty] | nr | nr | 1 | Packaged Chiller Units | T8 – Mechanical Services
3 | 5.6.5.4.2 | [8 empty] | nr | nr | 2 | Lithium Bromide/Water Absorption Chillers | T8 – Mechanical Services
4 | 5.6.5.4.3 | [8 empty] | nr | nr | 3 | Gas Fired Absorption Chiller Up to 18kw Cooling Capacity | T8 – Mechanical Services
5 | 5.6.5.4.4 | [8 empty] | nr | nr | 4 | Condensers - Water Cooled | T8 – Mechanical Services
5 | 5.6.5.4.5 | [8 empty] | nr | nr | 5 | Condensers - Air Cooled | T8 – Mechanical Services
4 | 5.6.5.4.6 | [8 empty] | nr | nr | 6 | Dry Coolers | T8 – Mechanical Services
5 | 5.6.5.4.7 | [8 empty] | nr | nr | 7 | Refrigeration Evaporators | T8 – Mechanical Services
5 | 5.6.5.4.8 | [8 empty] | nr | nr | 8 | Solar Thermal Absorption Chillers | T8 – Mechanical Services
5 | 5.6.5.5 | [6 empty] | 5 | Pipework In General
4 | 5.6.5.5.X | [8 empty] | m² | m² | X | See SUP - Pipework | T8 – Mechanical Services
5 | 5.6.5.6 | [6 empty] | 6 | Air Dirt Separators | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.5.7 | [6 empty] | 7 | Refrigerant Distribution System | m² | m² |  |  | T8 – Mechanical Services
5 | 5.6.5.8 | [6 empty] | 8 | Valves
5 | 5.6.5.8.X | [8 empty] | nr | nr | X | See SUP - Valves | T8 – Mechanical Services
5 | 5.6.5.9 | [6 empty] | 9 | Pumps
4 | 5.6.5.9.X | [8 empty] | nr | nr | X | See SUP - Pumps | T8 – Mechanical Services
5 | 5.6.5.10 | [6 empty] | 10 | Ductwork system
5 | 5.6.5.10.X | [8 empty] | m²/nr | m² | X | See SUP - Ductwork | T8 – Mechanical Services
5 | 5.6.5.11 | [6 empty] | 11 | Ventilation Grilles - External | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.5.12 | [6 empty] | 12 | Louvres | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.5.13 | [6 empty] | 13 | Bird Screens | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.5.14 | [6 empty] | 14 | Insect Screens | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.5.15 | [6 empty] | 15 | Ventilation Grilles - Internal | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.5.16 | [6 empty] | 16 | Ventilation Diffusers | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.5.17 | [6 empty] | 17 | Air handling units
5 | 5.6.5.17.1 | [8 empty] | nr | nr | 1 | Internal located | T8 – Mechanical Services
5 | 5.6.5.17.2 | [8 empty] | nr | nr | 2 | External located | T8 – Mechanical Services
5 | 5.6.5.18 | [6 empty] | 18 | Gas-Fired Heater Batteries - Indirect | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.5.19 | [6 empty] | 19 | Instrumentation and controls
4 | 5.6.5.19.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T8 – Mechanical Services
4 | 5.6.5.20 | [6 empty] | 20 | Thermal insulation
4 | 5.6.5.20.1 | [8 empty] | nr (m²) | m² | 1 | Thermal Insulation - Sheet | T8 – Mechanical Services
5 | 5.6.5.20.2 | [8 empty] | nr (m²) | m² | 2 | Thermal Insulation - Pipe | T8 – Mechanical Services
4 | 5.6.5.21 | [6 empty] | 21 | Fans
5 | 5.6.5.21.X | [8 empty] | nr | nr | X | See SUP - Fans | T8 – Mechanical Services
4 | 5.6.5.22 | [6 empty] | 22 | Compressors
5 | 5.6.5.22.X | [8 empty] | nr | nr | X | See SUP - Compressors | T8 – Mechanical Services
4 | 5.6.5.23 | [6 empty] | 23 | Electrical ancillaries
4 | 5.6.5.23.X | [8 empty] | nr | nr | X | See SUP - Electrical ancillaries | T8 – Mechanical Services
4 | 5.6.5.24 | [6 empty] | 24 | Starters
4 | 5.6.5.24.X | [8 empty] | nr | nr | X | See SUP - Starters | T8 – Mechanical Services
4 | 5.6.5.25 | [6 empty] | 25 | Actuators
4 | 5.6.5.25.X | [8 empty] | nr | nr | X | See SUP - Actuators | T8 – Mechanical Services
4 | 5.6.5.26 | [6 empty] | 26 | Expansion vessels | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.6 |  |  |  |  | 6 | Local heating and cooling
5 | 5.6.6.1 | [6 empty] | 1 | Split systems / DX systems
4 | 5.6.6.1.1 | [8 empty] | nr | nr | 1 | Condensers - Air Cooled | T8 – Mechanical Services
4 | 5.6.6.1.2 | [8 empty] | nr | nr | 2 | Variable Refrigerant Flow (VRF) Indoor Units | T8 – Mechanical Services
5 | 5.6.6.1.3 | [8 empty] | nr | nr | 3 | DX Split Systems (With Gas, Electric or Hot Water Heaters) | T8 – Mechanical Services
4 | 5.6.6.2 | [6 empty] | 2 | Pipework In General
5 | 5.6.6.2.X | [8 empty] | nr (m²) | m² | X | See SUP - Pipework | T8 – Mechanical Services
5 | 5.6.6.3 | [6 empty] | 3 | Refrigerant Distribution System | nr (m²) | m² |  |  | T8 – Mechanical Services
4 | 5.6.6.4 | [6 empty] | 4 | Valves
5 | 5.6.6.4.X | [8 empty] | nr | nr | X | See SUP - Valves | T8 – Mechanical Services
4 | 5.6.6.5 | [6 empty] | 5 | Pumps
5 | 5.6.6.5.X | [8 empty] | nr | nr | X | See SUP - Pumps | T8 – Mechanical Services
4 | 5.6.6.6 | [6 empty] | 6 | Ductwork systems
5 | 5.6.6.6.X | [8 empty] | nr (m²) | m² | X | See SUP - Ductwork | T8 – Mechanical Services
4 | 5.6.6.7 | [6 empty] | 7 | Ventilation Grilles - External | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.6.8 | [6 empty] | 8 | Louvres | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.6.9 | [6 empty] | 9 | Bird Screens | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.6.10 | [6 empty] | 10 | Insect Screens | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.6.11 | [6 empty] | 11 | Ventilation Grilles - Internal | nr | nr |  |  | T8 – Mechanical Services
3 | 5.6.6.12 | [6 empty] | 12 | Ventilation Diffusers | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.6.13 | [6 empty] | 13 | Instrumentation and controls
5 | 5.6.6.13.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T8 – Mechanical Services
5 | 5.6.6.14 | [6 empty] | 14 | Thermal insulation
5 | 5.6.6.14.1 | [8 empty] | nr (m²) | m² | 1 | Thermal Insulation - Sheet | T8 – Mechanical Services
4 | 5.6.6.14.2 | [8 empty] | nr (m²) | m² | 2 | Thermal Insulation - Pipe | T8 – Mechanical Services
5 | 5.6.6.15 | [6 empty] | 15 | Fans
5 | 5.6.6.15.X | [8 empty] | nr | nr | X | See SUP - Fans | T8 – Mechanical Services
5 | 5.6.6.16 | [6 empty] | 16 | Electrical ancillaries
5 | 5.6.6.16.X | [8 empty] | nr | nr | X | See SUP - Electrical ancillaries | T8 – Mechanical Services
4 | 5.6.6.17 | [6 empty] | 17 | Starters
4 | 5.6.6.17.X | [8 empty] | nr | nr | X | See SUP - Starters | T8 – Mechanical Services
5 | 5.6.6.18 | [6 empty] | 18 | Actuators
4 | 5.6.6.18.X | [8 empty] | nr | nr | X | See SUP - Actuators | T8 – Mechanical Services
5 | 5.6.7 |  |  |  |  | 7 | Central air conditioning
4 | 5.6.7.1 | [6 empty] | 1 | Plenum air – heating systems | m²/nr | m² |  |  | T8 – Mechanical Services
5 | 5.6.7.2 | [6 empty] | 2 | Central air conditioning systems – VAV
4 | 5.6.7.2.1 | [8 empty] | m²/nr | nr | 1 | Terminal Units VAV - Self Powered | T8 – Mechanical Services
4 | 5.6.7.2.2 | [8 empty] | m²/nr | nr | 2 | Terminal Units VAV - Fan Powered | T8 – Mechanical Services
4 | 5.6.7.2.3 | [8 empty] | m²/nr | nr | 3 | Terminal Units VAV - Pneumatic Powered | T8 – Mechanical Services
4 | 5.6.7.3 | [6 empty] | 3 | Humidifiers
4 | 5.6.7.3.X | [8 empty] | nr | nr | X | See SUP - Humidifiers | T8 – Mechanical Services
4 | 5.6.7.4 | [6 empty] | 4 | Multi-zone air conditioning systems | m²/nr | m² |  |  | T8 – Mechanical Services
4 | 5.6.7.5 | [6 empty] | 5 | Induction air conditioning systems | m²/nr | m² |  |  | T8 – Mechanical Services
5 | 5.6.7.6 | [6 empty] | 6 | Hybrid air conditioning systems | m²/nr | m² |  |  | T8 – Mechanical Services
4 | 5.6.7.7 | [6 empty] | 7 | Chillers
5 | 5.6.7.7.1 | [8 empty] | nr | nr | 1 | Packaged Chiller Units | T8 – Mechanical Services
5 | 5.6.7.7.2 | [8 empty] | nr | nr | 2 | Lithium Bromide/Water Absorption Chillers | T8 – Mechanical Services
4 | 5.6.7.7.3 | [8 empty] | nr | nr | 3 | Gas Fired Absorption Chiller Up to 18kw Cooling Capacity | T8 – Mechanical Services
5 | 5.6.7.7.4 | [8 empty] | nr | nr | 4 | Condensers - Water Cooled | T8 – Mechanical Services
4 | 5.6.7.7.5 | [8 empty] | nr | nr | 5 | Condensers - Air Cooled | T8 – Mechanical Services
5 | 5.6.7.7.6 | [8 empty] | nr | nr | 6 | Dry Coolers | T8 – Mechanical Services
4 | 5.6.7.7.7 | [8 empty] | nr | nr | 7 | Refrigeration Evaporators | T8 – Mechanical Services
5 | 5.6.7.7.8 | [8 empty] | nr | nr | 8 | Solar Thermal Absorption Chillers | T8 – Mechanical Services
4 | 5.6.7.8 | [6 empty] | 8 | Air handling units
5 | 5.6.7.8.1 | [8 empty] | nr | nr | 1 | Internally located | T8 – Mechanical Services
3 | 5.6.7.8.2 | [8 empty] | nr | nr | 2 | Externally located | T8 – Mechanical Services
4 | 5.6.7.9 | [6 empty] | 9 | Gas-Fired Heater Batteries - Indirect | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.7.10 | [6 empty] | 10 | Terminal units / emitters
5 | 5.6.7.10.1 | [8 empty] | nr | nr | 1 | Terminal Units - Constant Volume including Mixing | T8 – Mechanical Services
5 | 5.6.7.10.2 | [8 empty] | nr | nr | 2 | Terminal Units - Induction Units | T8 – Mechanical Services
5 | 5.6.7.10.3 | [8 empty] | nr | nr | 3 | Terminal Units - Fan Coil | T8 – Mechanical Services
4 | 5.6.7.10.4 | [8 empty] | nr | nr | 4 | Variable Refrigerant Flow (VRF) Indoor Units | T8 – Mechanical Services
5 | 5.6.7.11 | [6 empty] | 11 | Pipework In General
4 | 5.6.7.11.X | [8 empty] | m²/nr | m² | X | See SUP - Pipework | T8 – Mechanical Services
4 | 5.6.7.12 | [6 empty] | 12 | Refrigerant Distribution System | m²/nr | m² |  |  | T8 – Mechanical Services
4 | 5.6.7.13 | [6 empty] | 13 | Valves
4 | 5.6.7.13.X | [8 empty] | nr | nr | X | See SUP - Valves | T8 – Mechanical Services
5 | 5.6.7.14 | [6 empty] | 14 | Pumps
5 | 5.6.7.14.X | [8 empty] | nr | nr | X | See SUP - Pumps | T8 – Mechanical Services
5 | 5.6.7.15 | [6 empty] | 15 | Ductwork systems
5 | 5.6.7.15.X | [8 empty] | m²/nr | m² | X | See SUP - Ductwork | T8 – Mechanical Services
5 | 5.6.7.16 | [6 empty] | 16 | Ventilation Grilles - External | m²/nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.7.17 | [6 empty] | 17 | Louvres | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.7.18 | [6 empty] | 18 | Bird Screens | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.7.19 | [6 empty] | 19 | Insect Screens | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.7.20 | [6 empty] | 20 | Ventilation Grilles - Internal | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.7.21 | [6 empty] | 21 | Ventilation Diffusers | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.7.22 | [6 empty] | 22 | Instrumentation and controls
4 | 5.6.7.22.X | [8 empty] | nr | nr / System | X | See SUP - Controllers and sensors | T8 – Mechanical Services
4 | 5.6.7.23 | [6 empty] | 23 | Thermal insulation
5 | 5.6.7.23.1 | [8 empty] | nr (m²) | m² | 1 | Thermal Insulation - Sheet | T8 – Mechanical Services
5 | 5.6.7.23.2 | [8 empty] | nr (m²) | m² | 2 | Thermal Insulation - Pipe | T8 – Mechanical Services
5 | 5.6.7.24 | [6 empty] | 24 | Fans
5 | 5.6.7.24.X | [8 empty] | nr | nr | X | See SUP - Fans | T8 – Mechanical Services
4 | 5.6.7.25 | [6 empty] | 25 | Compressors
5 | 5.6.7.25.X | [8 empty] | nr | nr / System | X | See SUP - Compressors | T8 – Mechanical Services
5 | 5.6.7.26 | [6 empty] | 26 | Electrical ancillaries
5 | 5.6.7.26.X | [8 empty] | nr | nr | X | See SUP - Electrical ancillaries | T8 – Mechanical Services
5 | 5.6.7.27 | [6 empty] | 27 | Starters
4 | 5.6.7.27.X | [8 empty] | nr | nr | X | See SUP - Starters | T8 – Mechanical Services
4 | 5.6.7.28 | [6 empty] | 28 | Actuators
5 | 5.6.7.28.X | [8 empty] | nr | nr | X | See SUP - Actuators | T8 – Mechanical Services
4 | 5.6.8 |  |  |  |  | 8 | Local air conditioning
5 | 5.6.8.1 | [6 empty] | 1 | Room air conditioning units | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.8.2 | [6 empty] | 2 | Clean room air conditioning units
5 | 5.6.8.2.1 | [8 empty] | nr | nr | 1 | DX Split Systems (With Gas, Electric or Hot Water Heaters) | T8 – Mechanical Services
4 | 5.6.8.2.2 | [8 empty] | nr | nr | 2 | Data Centre Cooling Plant - Chilled Water | T8 – Mechanical Services
4 | 5.6.8.2.3 | [8 empty] | nr | nr | 3 | Data Centre Cooling Plant - Direct Expansion (DX) | T8 – Mechanical Services
4 | 5.6.8.3 | [6 empty] | 3 | Pipework In General
4 | 5.6.8.3.X | [8 empty] | m² | m² | X | See SUP - Pipework | T8 – Mechanical Services
4 | 5.6.8.4 | [6 empty] | 4 | Refrigerant Distribution System | m² | m² |  |  | T8 – Mechanical Services
4 | 5.6.8.5 | [6 empty] | 5 | Valves
4 | 5.6.8.5.X | [8 empty] | nr | nr | X | See SUP - Valves | T8 – Mechanical Services
5 | 5.6.8.6 | [6 empty] | 6 | Pumps
4 | 5.6.8.6.X | [8 empty] | nr | nr | X | See SUP - Pumps | T8 – Mechanical Services
5 | 5.6.8.7 | [6 empty] | 7 | Ductwork systems
5 | 5.6.8.7.X | [8 empty] | nr (m²) | m² | X | See SUP - Ductwork | T8 – Mechanical Services
4 | 5.6.8.8 | [6 empty] | 8 | Ventilation Grilles - External | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.8.9 | [6 empty] | 9 | Louvres | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.8.10 | [6 empty] | 10 | Bird Screens | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.8.11 | [6 empty] | 11 | Insect Screens | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.8.12 | [6 empty] | 12 | Ventilation Grilles - Internal | nr | nr |  |  | T8 – Mechanical Services
5 | 5.6.8.13 | [6 empty] | 13 | Ventilation Diffusers | nr | nr |  |  | T8 – Mechanical Services
4 | 5.6.8.14 | [6 empty] | 14 | Instrumentation and controls
5 | 5.6.8.14.X | [8 empty] | nr / System | nr / System | X | See SUP - Controllers and sensors | T8 – Mechanical Services
4 | 5.6.8.15 | [6 empty] | 15 | Thermal insulation
5 | 5.6.8.15.1 | [8 empty] | nr (m²) | m² | 1 | Thermal Insulation - Sheet | T8 – Mechanical Services
3 | 5.6.8.15.2 | [8 empty] | nr (m²) | m² | 2 | Thermal Insulation - Pipe | T8 – Mechanical Services
4 | 5.6.8.16 | [6 empty] | 16 | Air curtains
4 | 5.6.8.16.1 | [8 empty] | nr | nr | 1 | Electric Overdoor Air Curtain/Heater | T8 – Mechanical Services
5 | 5.6.8.16.2 | [8 empty] | nr | nr | 2 | LTHW Overdoor Air Curtain/Heater | T8 – Mechanical Services
5 | 5.6.8.17 | [6 empty] | 17 | Fans
5 | 5.6.8.17.X | [8 empty] | nr | nr | X | See SUP - Fans | T8 – Mechanical Services
4 | 5.6.8.18 | [6 empty] | 18 | Filters
5 | 5.6.8.18.X | [8 empty] | nr | nr | X | See SUP - Filters | T8 – Mechanical Services
5 | 5.6.8.19 | [6 empty] | 19 | Electrical ancillaries
5 | 5.6.8.19.X | [8 empty] | nr | nr | X | See SUP - Electrical ancillaries | T8 – Mechanical Services
5 | 5.6.8.20 | [6 empty] | 20 | Starters
4 | 5.6.8.20.X | [8 empty] | nr | nr | X | See SUP - Starters | T8 – Mechanical Services
4 | 5.6.8.21 | [6 empty] | 21 | Actuators
5 | 5.6.8.21.X | [8 empty] | nr | nr | X | See SUP - Actuators | T8 – Mechanical Services
4 | 5.7 |  |  | 7 | Ventilation Systems
5 | 5.7.1 |  |  |  |  | 1 | Central ventilation
4 | 5.7.1.1 | [6 empty] | 1 | Ventilating Fans | nr | nr |  |  | T8 – Mechanical Services
5 | 5.7.1.2 | [6 empty] | 2 | Extract units/terminal units | m²/nr | nr |  |  | T8 – Mechanical Services
4 | 5.7.1.3 | [6 empty] | 3 | Fans
4 | 5.7.1.3.X | [8 empty] | nr | nr | X | See SUP - Fans | T8 – Mechanical Services
4 | 5.7.1.4 | [6 empty] | 4 | Ductwork systems
4 | 5.7.1.4.X | [8 empty] | m²/nr | m² | X | See SUP - Ductwork | T8 – Mechanical Services
4 | 5.7.1.5 | [6 empty] | 5 | Ventilation Grilles - External | nr | nr |  |  | T8 – Mechanical Services
4 | 5.7.1.6 | [6 empty] | 6 | Louvres | nr | nr |  |  | T8 – Mechanical Services
4 | 5.7.1.7 | [6 empty] | 7 | Bird Screens | nr | nr |  |  | T8 – Mechanical Services
5 | 5.7.1.8 | [6 empty] | 8 | Insect Screens | nr | nr |  |  | T8 – Mechanical Services
4 | 5.7.1.9 | [6 empty] | 9 | Ventilation Grilles - Internal | nr | nr |  |  | T8 – Mechanical Services
5 | 5.7.1.10 | [6 empty] | 10 | Ventilation Diffusers | nr | nr |  |  | T8 – Mechanical Services
5 | 5.7.1.11 | [6 empty] | 11 | Pipework In General
4 | 5.7.1.11.X | [8 empty] | m²/nr | m² | X | See SUP - Pipework | T8 – Mechanical Services
5 | 5.7.1.12 | [6 empty] | 12 | Valves
5 | 5.7.1.12.X | [8 empty] | nr | nr | X | See SUP - Valves | T8 – Mechanical Services
4 | 5.7.1.13 | [6 empty] | 13 | Pumps
5 | 5.7.1.13.X | [8 empty] | nr | nr | X | See SUP - Pumps | T8 – Mechanical Services
4 | 5.7.1.14 | [6 empty] | 14 | Instrumentation and controls
5 | 5.7.1.14.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T8 – Mechanical Services
4 | 5.7.1.15 | [6 empty] | 15 | Thermal insulation
5 | 5.7.1.15.1 | [8 empty] | nr (m²) | m² | 1 | Thermal Insulation - Sheet | T8 – Mechanical Services
4 | 5.7.1.15.2 | [8 empty] | nr (m²) | m² | 2 | Thermal Insulation - Pipe | T8 – Mechanical Services
5 | 5.7.1.16 | [6 empty] | 16 | Filters
4 | 5.7.1.16.X | [8 empty] | nr | nr | X | See SUP - Filters | T8 – Mechanical Services
5 | 5.7.1.17 | [6 empty] | 17 | Electrical ancillaries
2 | 5.7.1.17.X | [8 empty] | nr | nr | X | See SUP - Electrical ancillaries | T8 – Mechanical Services
3 | 5.7.1.18 | [6 empty] | 18 | Starters
4 | 5.7.1.18.X | [8 empty] | nr | nr | X | See SUP - Starters | T8 – Mechanical Services
4 | 5.7.1.19 | [6 empty] | 19 | Actuators
4 | 5.7.1.19.X | [8 empty] | nr | nr | X | See SUP - Actuators | T8 – Mechanical Services
5 | 5.7.1.20 | [6 empty] | 20 | Air handling units
4 | 5.7.1.20.1 | [8 empty] | nr | nr | 1 | Internally located | T8 – Mechanical Services
5 | 5.7.1.20.2 | [8 empty] | nr | nr | 2 | Externally located | T8 – Mechanical Services
4 | 5.7.2 |  |  |  |  | 2 | Local and special ventilation
4 | 5.7.2.1 | [6 empty] | 1 | Kitchen ventilation units | nr | nr |  |  | T8 – Mechanical Services
4 | 5.7.2.2 | [6 empty] | 2 | Safety cabinet and fume cupboards | nr | nr |  |  | T8 – Mechanical Services
4 | 5.7.2.3 | [6 empty] | 3 | Fume extracts
4 | 5.7.2.3.1 | [8 empty] | nr | nr | 1 | Local Exhaust Ventilation (LEV) Systems | T8 – Mechanical Services
4 | 5.7.2.3.2 | [8 empty] | nr | nr | 2 | Motor Driven Exhaust Hose Reel | T8 – Mechanical Services
4 | 5.7.2.3.3 | [8 empty] | nr | nr | 3 | Spring Recoil Hose Reel | T8 – Mechanical Services
5 | 5.7.2.3.4 | [8 empty] | nr | nr | 4 | Mobile Dust Separator for Spot Extraction | T8 – Mechanical Services
5 | 5.7.2.3.5 | [8 empty] | nr | nr | 5 | Vehicle Exhaust Rail System | T8 – Mechanical Services
5 | 5.7.2.4 | [6 empty] | 4 | Dust collection units | nr | nr |  |  | T8 – Mechanical Services
5 | 5.7.2.5 | [6 empty] | 5 | Anaesthetic gas extracts
4 | 5.7.2.5.1 | [8 empty] | nr | nr | 1 | Anaesthetic Gas Scavenging (AGS) Systems | T8 – Mechanical Services
5 | 5.7.2.5.2 | [8 empty] | nr | nr | 2 | Anaesthetic Gas Scavenging (AGS) Systems | T8 – Mechanical Services
4 | 5.7.2.6 | [6 empty] | 6 | Cyclone systems | nr | nr |  |  | T8 – Mechanical Services
5 | 5.7.2.7 | [6 empty] | 7 | Car parking ventilation | m²/nr | m² |  |  | T8 – Mechanical Services
4 | 5.7.2.8 | [6 empty] | 8 | Ductwork systems
5 | 5.7.2.8.X | [8 empty] | m²/nr | m² | X | See SUP - Ductwork | T8 – Mechanical Services
4 | 5.7.2.9 | [6 empty] | 9 | Ventilation Grilles - External | nr | nr |  |  | T8 – Mechanical Services
5 | 5.7.2.10 | [6 empty] | 10 | Louvres | nr | nr |  |  | T8 – Mechanical Services
5 | 5.7.2.11 | [6 empty] | 11 | Bird Screens | nr | nr |  |  | T8 – Mechanical Services
4 | 5.7.2.12 | [6 empty] | 12 | Insect Screens | nr | nr |  |  | T8 – Mechanical Services
5 | 5.7.2.13 | [6 empty] | 13 | Ventilation Grilles - Internal | nr | nr |  |  | T8 – Mechanical Services
4 | 5.7.2.14 | [6 empty] | 14 | Ventilation Diffusers | nr | nr |  |  | T8 – Mechanical Services
5 | 5.7.2.15 | [6 empty] | 15 | Instrumentation and controls
4 | 5.7.2.15.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T8 – Mechanical Services
5 | 5.7.2.16 | [6 empty] | 16 | Fans
4 | 5.7.2.16.X | [8 empty] | nr | nr | X | See SUP - Fans | T8 – Mechanical Services
5 | 5.7.2.17 | [6 empty] | 17 | Filters
4 | 5.7.2.17.X | [8 empty] | nr | nr | X | See SUP - Filters | T8 – Mechanical Services
5 | 5.7.2.18 | [6 empty] | 18 | Actuators
5 | 5.7.2.18.X | [8 empty] | nr | nr | X | See SUP - Actuators | T8 – Mechanical Services
3 | 5.7.2.19 | [6 empty] | 19 | Air Pressure Relief Damper | nr | nr |  |  | T8 – Mechanical Services
4 | 5.7.2.20 | [6 empty] | 20 | Room Pressure Gauges, Magnahelic Gauge Panel and Manometers | nr | nr |  |  | T8 – Mechanical Services
4 | 5.7.3 |  |  |  |  | 3 | Smoke extract/control
4 | 5.7.3.1 | [6 empty] | 1 | Smoke extract | nr | nr |  |  | T12 – Safety Systems
5 | 5.7.3.2 | [6 empty] | 2 | Automatic smoke compartmentalisation
5 | 5.7.3.2.1 | [8 empty] | m²/nr | nr | 1 | Smoke Relief - Powered Smoke and Heat Exhaust Ventilators | T12 – Safety Systems
5 | 5.7.3.2.2 | [8 empty] | nr | nr | 2 | Smoke Barrier - Active | T12 – Safety Systems
5 | 5.7.3.2.3 | [8 empty] | m²/nr | nr | 3 | Powered Pressurisation Fan Systems | T12 – Safety Systems
5 | 5.7.3.2.4 | [8 empty] | m²/nr | nr | 4 | Smoke Control Systems - Weekly, 3 Monthly and Annual Testing | T12 – Safety Systems
4 | 5.7.3.2.5 | [8 empty] | nr | nr | 5 | Smoke Barrier - Static | T12 – Safety Systems
4 | 5.7.3.2.6 | [8 empty] | nr | nr | 6 | Smoke Control Dampers (SCD) - Automatic | T12 – Safety Systems
5 | 5.7.3.2.7 | [8 empty] | nr | nr | 7 | Smoke Control Dampers (SCD) - Manual | T12 – Safety Systems
5 | 5.7.3.2.8 | [8 empty] | m²/nr | System | 8 | Smoke Control - Pressure Differential System (PDS) | T12 – Safety Systems
4 | 5.7.3.2.9 | [8 empty] | m²/nr | System | 9 | Smoke Control - Smoke Duct Sections | T12 – Safety Systems
4 | 5.7.3.2.10 | [8 empty] | m²/nr | System | 10 | Smoke Control - Covered or Enclosed Car Park System | T12 – Safety Systems
4 | 5.7.3.3 | [6 empty] | 3 | Fans
5 | 5.7.3.3.X | [8 empty] | m²/nr | nr | X | See SUP - Fans | T12 – Safety Systems
4 | 5.7.3.4 | [6 empty] | 4 | Ductwork systems
4 | 5.7.3.4.X | [8 empty] | m²/nr | m² | X | See SUP - Ductwork | T12 – Safety Systems
4 | 5.7.3.5 | [6 empty] | 5 | Ventilation Grilles - External | nr | nr |  |  | T12 – Safety Systems
4 | 5.7.3.6 | [6 empty] | 6 | Louvres | nr | nr |  |  | T12 – Safety Systems
4 | 5.7.3.7 | [6 empty] | 7 | Bird Screens | nr | nr |  |  | T12 – Safety Systems
4 | 5.7.3.8 | [6 empty] | 8 | Insect Screens | nr | nr |  |  | T12 – Safety Systems
4 | 5.7.3.9 | [6 empty] | 9 | Ventilation Grilles - Internal | nr | nr |  |  | T12 – Safety Systems
5 | 5.7.3.10 | [6 empty] | 10 | Ventilation Diffusers | nr | nr |  |  | T12 – Safety Systems
4 | 5.7.3.11 | [6 empty] | 11 | Instrumentation and controls
5 | 5.7.3.11.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T12 – Safety Systems
4 | 5.7.3.12 | [6 empty] | 12 | Filters
5 | 5.7.3.12.X | [8 empty] | nr | nr | X | See SUP - Filters | T12 – Safety Systems
4 | 5.7.3.13 | [6 empty] | 13 | Actuators
5 | 5.7.3.13.X | [8 empty] | nr | nr | X | See SUP - Actuators | T12 – Safety Systems
4 | 5.7.4 |  |  |  |  | 4 | Respiratory Protection
4 | 5.7.4.1 | [6 empty] | 1 | Respiratory Protective Equipment (RPE)
3 | 5.7.4.1.1 | [8 empty] | nr | nr | 1 | Breathing Apparatus | T12 – Safety Systems
4 | 5.7.4.1.2 | [8 empty] | nr | nr | 2 | Filtering Devices | T12 – Safety Systems
4 | 5.8 |  |  | 8 | Electrical Installations
5 | 5.8.1 |  |  |  |  | 1 | Electrical mains and sub mains distribution
5 | 5.8.1.1 | [6 empty] | 1 | Low Voltage (LV) Panel Board and Switchgear - Main Intake | m²/nr | nr |  |  | T9 – Electrical Services
5 | 5.8.1.2 | [6 empty] | 2 | Maximum Demand and Power Factor Correction | m²/nr | nr |  |  | T9 – Electrical Services
5 | 5.8.1.3 | [6 empty] | 3 | Power Distribution Unit (PDU) | m²/nr | nr |  |  | T9 – Electrical Services
5 | 5.8.1.4 | [6 empty] | 4 | HV switch gear
5 | 5.8.1.4.1 | [8 empty] | m²/nr | nr | 1 | HV Packaged Substations | T9 – Electrical Services
5 | 5.8.1.4.2 | [8 empty] | m²/nr | nr | 2 | Oil Switchgear including Oil Circuit Breakers and Oil Switches | T9 – Electrical Services
5 | 5.8.1.4.3 | [8 empty] | m²/nr | nr | 3 | Air Break Switchgear | T9 – Electrical Services
5 | 5.8.1.4.4 | [8 empty] | m²/nr | nr | 4 | Sulphur Hexafluoride Switchgear | T9 – Electrical Services
5 | 5.8.1.4.5 | [8 empty] | m²/nr | nr | 5 | Vacuum Switchgear | T9 – Electrical Services
4 | 5.8.1.4.6 | [8 empty] | m²/nr | nr | 6 | Vacuum Indoor Switchgear | T9 – Electrical Services
5 | 5.8.1.4.7 | [8 empty] | nr | nr | 7 | Ring Main Unit | T9 – Electrical Services
4 | 5.8.1.4.8 | [8 empty] | nr | nr | 8 | HV Switchpanel | T9 – Electrical Services
5 | 5.8.1.4.9 | [8 empty] | nr | nr | 9 | High Voltage (HV) Insulation | T9 – Electrical Services
4 | 5.8.1.4.10 | [8 empty] | nr | nr | 10 | High Voltage (HV) Interlocks | T9 – Electrical Services
4 | 5.8.1.4.11 | [8 empty] | nr | nr | 11 | High Voltage (HV) Insulation | T9 – Electrical Services
4 | 5.8.1.4.12 | [8 empty] | nr | nr | 12 | High Voltage (HV) Interlocks | T9 – Electrical Services
4 | 5.8.1.4.13 | [8 empty] | nr | nr | 13 | High Voltage (HV) Insulation | T9 – Electrical Services
4 | 5.8.1.4.14 | [8 empty] | nr | nr | 14 | High Voltage (HV) Interlocks | T9 – Electrical Services
4 | 5.8.1.4.15 | [8 empty] | nr | nr | 15 | High Voltage Switchgear and Controlgear (Main Intake) - England | T9 – Electrical Services
4 | 5.8.1.4.16 | [8 empty] | nr | nr | 16 | High Voltage Switchgear and Controlgear (Main Intake) - Scotland | T9 – Electrical Services
5 | 5.8.1.5 | [6 empty] | 5 | LV switchgear and distribution boards | nr | nr |  |  | T9 – Electrical Services
4 | 5.8.1.6 | [6 empty] | 6 | Power and Lighting Cabling
5 | 5.8.1.6.1 | [8 empty] | m² | m² | 1 | Mineral insulated | T9 – Electrical Services
4 | 5.8.1.6.2 | [8 empty] | m² | m² | 2 | Thermoplastic | T9 – Electrical Services
5 | 5.8.1.6.3 | [8 empty] | m² | m² | 3 | Thermosetting | T9 – Electrical Services
3 | 5.8.1.6.4 | [8 empty] | m² | m² | 4 | Fire performance | T9 – Electrical Services
4 | 5.8.1.7 | [6 empty] | 7 | Catenary Electrical Wiring | m² | m² |  |  | T9 – Electrical Services
5 | 5.8.1.8 | [6 empty] | 8 | Conduits | m² | m² |  |  | T9 – Electrical Services
5 | 5.8.1.9 | [6 empty] | 9 | Trunking | m² | m² |  |  | T9 – Electrical Services
2 | 5.8.1.10 | [6 empty] | 10 | Basket | m² | m² |  |  | T9 – Electrical Services
3 | 5.8.1.11 | [6 empty] | 11 | Busbar trunking | m²/nr | m² |  |  | T9 – Electrical Services
4 | 5.8.1.12 | [6 empty] | 12 | Earthing and bonding
4 | 5.8.1.12.1 | [8 empty] | m² | m² | 1 | LV Earthing | T9 – Electrical Services
4 | 5.8.1.12.2 | [8 empty] | nr | nr | 2 | High Voltage (HV) Earthing | T9 – Electrical Services
4 | 5.8.1.13 | [6 empty] | 13 | Transformers
5 | 5.8.1.13.1 | [8 empty] | nr | nr | 1 | 110V Wall Mounted Transformers | T9 – Electrical Services
5 | 5.8.1.13.2 | [8 empty] | nr | nr | 2 | Fluid Filled Transformer | T9 – Electrical Services
5 | 5.8.1.13.3 | [8 empty] | nr | nr | 3 | Cast Resin Transformer | T9 – Electrical Services
5 | 5.8.1.13.4 | [8 empty] | nr | nr | 4 | Frequency converter | T9 – Electrical Services
5 | 5.8.1.14 | [6 empty] | 14 | Fuse pillars, base units, etc. | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.1.15 | [6 empty] | 15 | Surge protection
5 | 5.8.1.15.1 | [8 empty] | nr | nr | 1 | Hazardous Areas - Flameproof Equipment | T9 – Electrical Services
5 | 5.8.1.15.2 | [8 empty] | nr | nr | 2 | Hazardous Areas - Lighting | T9 – Electrical Services
5 | 5.8.1.16 | [6 empty] | 16 | Electricity monitoring system | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.1.17 | [6 empty] | 17 | Instrumentation and controls
5 | 5.8.1.17.X | [8 empty] | nr / System | nr / System | X | See SUP - Controllers and sensors | T9 – Electrical Services
5 | 5.8.1.18 | [6 empty] | 18 | Electrical ancillaries
5 | 5.8.1.18.X | [8 empty] | nr | nr | X | See SUP - Electrical ancillaries | T9 – Electrical Services
5 | 5.8.2 |  |  |  |  | 2 | Power installations
5 | 5.8.2.1 | [6 empty] | 1 | Electrical Installation - Generally | m²/nr | m² |  |  | T9 – Electrical Services
5 | 5.8.2.2 | [6 empty] | 2 | LV Air Circuit Breakers | nr | nr |  |  | T9 – Electrical Services
4 | 5.8.2.3 | [6 empty] | 3 | Battery Tripping Units | nr | nr |  |  | T9 – Electrical Services
4 | 5.8.2.4 | [6 empty] | 4 | Thermal Imaging of Electrical Systems (under 1000 Va.c.) | m² | m² |  |  | T9 – Electrical Services
5 | 5.8.2.5 | [6 empty] | 5 | DC installations | m²/nr | nr |  |  | T9 – Electrical Services
5 | 5.8.2.6 | [6 empty] | 6 | LV switchgear | m²/nr | nr |  |  | T9 – Electrical Services
5 | 5.8.2.7 | [6 empty] | 7 | Uninterruptible Power Supplies | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.2.8 | [6 empty] | 8 | Batteries - Lead Acid - Unsealed | nr | nr |  |  | T9 – Electrical Services
4 | 5.8.2.9 | [6 empty] | 9 | Battery Charging Equipment | nr | nr |  |  | T9 – Electrical Services
4 | 5.8.2.10 | [6 empty] | 10 | Diesel rotary system | nr | nr |  |  | T9 – Electrical Services
4 | 5.8.2.11 | [6 empty] | 11 | Power and Lighting Cabling | m²/nr | m² |  |  | T9 – Electrical Services
4 | 5.8.2.12 | [6 empty] | 12 | Catenary Electrical Wiring | m²/nr | m² |  |  | T9 – Electrical Services
4 | 5.8.2.13 | [6 empty] | 13 | Conduits | m²/nr | m² |  |  | T9 – Electrical Services
4 | 5.8.2.14 | [6 empty] | 14 | Trunking | m²/nr | m² |  |  | T9 – Electrical Services
5 | 5.8.2.15 | [6 empty] | 15 | Basket | m²/nr | m² |  |  | T9 – Electrical Services
5 | 5.8.2.16 | [6 empty] | 16 | Earthing and bonding | m²/nr | m² |  |  | T9 – Electrical Services
4 | 5.8.2.17 | [6 empty] | 17 | Three Phase Circuits | m²/nr | m² |  |  | T9 – Electrical Services
5 | 5.8.2.18 | [6 empty] | 18 | Contactors | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.2.19 | [6 empty] | 19 | Power Filter (LV Active) | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.2.20 | [6 empty] | 20 | Trapped Key Interlocks | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.2.21 | [6 empty] | 21 | Train Shore Supply | nr | nr |  |  | T9 – Electrical Services
4 | 5.8.2.22 | [6 empty] | 22 | Electrical Sub Stations Infrastructure | m²/nr | m² |  |  | T9 – Electrical Services
4 | 5.8.2.23 | [6 empty] | 23 | Power Distribution Unit (PDU) | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.2.24 | [6 empty] | 24 | Distribution Boards | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.2.25 | [6 empty] | 25 | Instrumentation and controls
4 | 5.8.2.25.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T9 – Electrical Services
4 | 5.8.2.26 | [6 empty] | 26 | Electric Vehicle Charging Equipment
5 | 5.8.2.26.1 | [8 empty] | nr | nr | 1 | Mode 1 Domestic | T9 – Electrical Services
4 | 5.8.2.26.2 | [8 empty] | nr | nr | 2 | Mode 2 Domestic | T9 – Electrical Services
5 | 5.8.2.26.3 | [8 empty] | nr | nr | 3 | Mode 3 Domestic and Non Domestic | T9 – Electrical Services
3 | 5.8.2.26.4 | [8 empty] | nr | nr | 4 | Mode 4 Non Domestic | T9 – Electrical Services
4 | 5.8.2.27 | [6 empty] | 27 | General Electrical Services (excluding Electrical Controllers and Pneumatic Relays) | nr | nr |  |  | T9 – Electrical Services
4 | 5.8.3 |  |  |  |  | 3 | Lighting installations
4 | 5.8.3.1 | [6 empty] | 1 | Light fittings – general | T/E | T/E |  |  | T9 – Electrical Services
4 | 5.8.3.2 | [6 empty] | 2 | Emergency lighting
4 | 5.8.3.2.1 | [8 empty] | m²/nr | nr | 1 | Emergency Lighting - Monthly Testing | T9 – Electrical Services
4 | 5.8.3.2.2 | [8 empty] | m²/nr | m² | 2 | Emergency Lighting - Annual Testing | T9 – Electrical Services
4 | 5.8.3.2.3 | [8 empty] | nr | nr | 3 | Emergency Lighting System Self Testing - Self-contained | T9 – Electrical Services
4 | 5.8.3.2.4 | [8 empty] | nr | nr | 4 | Emergency Lighting - Centrally Powered Vented Batteries | T9 – Electrical Services
4 | 5.8.3.2.5 | [8 empty] | nr | nr | 5 | Emergency Lighting – Lamp Replacement | T9 – Electrical Services
4 | 5.8.3.2.6 | [8 empty] | nr | nr | 6 | Emergency Lighting - Centrally Powered | T9 – Electrical Services
4 | 5.8.3.2.7 | [8 empty] | nr | nr | 7 | Emergency Lighting - Self-Contained Fittings | T9 – Electrical Services
4 | 5.8.3.3 | [6 empty] | 3 | External lighting | m²/nr | nr |  |  | T9 – Electrical Services
4 | 5.8.3.4 | [6 empty] | 4 | LV switchgear | m²/nr | nr |  |  | T9 – Electrical Services
4 | 5.8.3.5 | [6 empty] | 5 | Cables and wiring
4 | 5.8.3.5.1 | [8 empty] | m² | m² | 1 | Power and Lighting Cabling | T9 – Electrical Services
4 | 5.8.3.5.2 | [8 empty] | m² | m² | 2 | Catenary Electrical Wiring | T9 – Electrical Services
4 | 5.8.3.6 | [6 empty] | 6 | Conduits and cable trunking | m²/nr | m² |  |  | T9 – Electrical Services
4 | 5.8.3.7 | [6 empty] | 7 | Earthing and bonding | nr | m² |  |  | T9 – Electrical Services
4 | 5.8.3.8 | [6 empty] | 8 | Fittings to lighting points | nr | N/A |  |  | T9 – Electrical Services
4 | 5.8.3.9 | [6 empty] | 9 | Lighting switches (Major) | nr | nr |  |  | T9 – Electrical Services
4 | 5.8.3.10 | [6 empty] | 10 | Luminaries/lamps
4 | 5.8.3.10.1 | [8 empty] | m²/nr | nr | 1 | Lamps - Tungsten Filament | T9 – Electrical Services
4 | 5.8.3.10.2 | [8 empty] | m²/nr | nr | 2 | Lamps - LED | T9 – Electrical Services
4 | 5.8.3.10.3 | [8 empty] | m²/nr | nr | 3 | Lamps - Fluorescent | T9 – Electrical Services
4 | 5.8.3.10.4 | [8 empty] | m²/nr | nr | 4 | Lamps - Discharge | T9 – Electrical Services
5 | 5.8.3.11 | [6 empty] | 11 | Lighting control equipment
4 | 5.8.3.11.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T9 – Electrical Services
5 | 5.8.3.12 | [6 empty] | 12 | Distribution boards | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.3.13 | [6 empty] | 13 | Control relays
5 | 5.8.3.13.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T9 – Electrical Services
5 | 5.8.3.14 | [6 empty] | 14 | Equipment Columns
4 | 5.8.3.14.1 | [8 empty] | nr | nr | 1 | Fixed | T9 – Electrical Services
3 | 5.8.3.14.2 | [8 empty] | nr | nr | 2 | Base-Hinged | T9 – Electrical Services
4 | 5.8.4 |  |  |  |  | 4 | Specialist lighting installations
4 | 5.8.4.1 | [6 empty] | 1 | Illuminated display units | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.4.2 | [6 empty] | 2 | Studio lighting | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.4.3 | [6 empty] | 3 | Auditorium lighting | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.4.4 | [6 empty] | 4 | Arena lighting | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.4.5 | [6 empty] | 5 | Operating theatre lighting | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.4.6 | [6 empty] | 6 | LV switchgear | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.4.7 | [6 empty] | 7 | Distribution boards | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.4.8 | [6 empty] | 8 | Lighting gantries | nr | nr |  |  | T9 – Electrical Services
4 | 5.8.4.9 | [6 empty] | 9 | Lighting control equipment
4 | 5.8.4.9.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T9 – Electrical Services
4 | 5.8.5 |  |  |  |  | 5 | Local electricity generation systems
5 | 5.8.5.1 | [6 empty] | 1 | Standby generator
5 | 5.8.5.1.1 | [8 empty] | nr | nr | 1 | Power Generation - Standby Generator | T9 – Electrical Services
4 | 5.8.5.1.2 | [8 empty] | nr | nr | 2 | Power Generation - Standby Generator with Life Safety System Duties | T9 – Electrical Services
4 | 5.8.5.2 | [6 empty] | 2 | Batteries - Lead Acid - Unsealed | nr | nr |  |  | T9 – Electrical Services
4 | 5.8.5.3 | [6 empty] | 3 | Battery Charging Equipment | nr | nr |  |  | T9 – Electrical Services
4 | 5.8.5.4 | [6 empty] | 4 | Power and Lighting Cabling | Building size | Building size |  |  | T9 – Electrical Services
4 | 5.8.5.5 | [6 empty] | 5 | Catenary Electrical Wiring | nr | nr |  |  | T9 – Electrical Services
5 | 5.8.5.6 | [6 empty] | 6 | Actuators
5 | 5.8.5.6.X | [8 empty] | nr | nr | X | See SUP - Actuators | T9 – Electrical Services
5 | 5.8.5.7 | [6 empty] | 7 | Wind turbines | nr | nr |  |  | T16 – Specialist
5 | 5.8.5.8 | [6 empty] | 8 | Photovoltaic devices
4 | 5.8.5.8.1 | [8 empty] | nr | nr | 1 | Solar Panels - Photovoltaic (PV) - Energy Storage | T16 – Specialist
5 | 5.8.5.8.2 | [8 empty] | nr | nr | 2 | Photovoltaic (PV) System - Grid Connected | T16 – Specialist
4 | 5.8.5.8.3 | [8 empty] | nr | nr | 3 | Large solar systems - Photovoltaic (PV) - Grid Connected | T16 – Specialist
4 | 5.8.5.9 | [6 empty] | 9 | Solar collectors
5 | 5.8.5.9.1 | [8 empty] | nr | nr | 1 | Solar Hot Water Panels and Similar Collecting Devices - Plate Type | T16 – Specialist
4 | 5.8.5.9.2 | [8 empty] | nr | nr | 2 | Solar Hot Water Panels and Similar Collecting Devices - Vacuum Tube Type | T16 – Specialist
5 | 5.8.6 |  |  |  |  | 6 | Earthing and bonding systems
5 | 5.8.6.1 | [6 empty] | 1 | Earthing and bonding cables
3 | 5.8.6.1.1 | [8 empty] | m²/nr | nr | 1 | Neutral Earth Panel | T9 – Electrical Services
4 | 5.8.6.1.2 | [8 empty] | m²/nr | m² | 2 | LV Earthing | T9 – Electrical Services
4 | 5.8.6.1.3 | [8 empty] | nr | nr | 3 | High Voltage (HV) Earthing | T9 – Electrical Services
4 | 5.8.6.2 | [6 empty] | 2 | Protective conductor earthing
4 | 5.8.6.2.1 | [8 empty] | m²/nr | m² | 1 | LV Earthing | T9 – Electrical Services
4 | 5.8.6.2.2 | [8 empty] | nr | nr | 2 | High Voltage (HV) Earthing | T9 – Electrical Services
4 | 5.8.6.2.3 | [8 empty] | nr | nr | 3 | Hazardous Areas - Earthing | T9 – Electrical Services
4 | 5.9 |  |  | 9 | Fuel Installations
4 | 5.9.1 |  |  |  |  | 1 | Fuel storage
4 | 5.9.1.1 | [6 empty] | 1 | Fuel Oil Transfer Pumps | nr | nr |  |  | T10 – Fuel Installations
5 | 5.9.1.2 | [6 empty] | 2 | Liquid Nitrogen Plant | nr | nr |  |  | T10 – Fuel Installations
3 | 5.9.1.3 | [6 empty] | 3 | Liquid Oxygen Vacuum Insulated Evaporator (VIE) Plant | nr | nr |  |  | T10 – Fuel Installations
4 | 5.9.1.4 | [6 empty] | 4 | Storage tanks and vessels
5 | 5.9.1.4.1 | [8 empty] | nr | nr | 1 | Storage Tanks - Liquefied Petroleum Gas (LPG) | T10 – Fuel Installations
5 | 5.9.1.4.2 | [8 empty] | nr | nr | 2 | Oil Storage Tanks - Above Ground | T10 – Fuel Installations
4 | 5.9.1.4.3 | [8 empty] | nr | nr | 3 | Oil Storage Tanks - Above Ground (Operational) | T10 – Fuel Installations
4 | 5.9.1.4.4 | [8 empty] | nr | nr | 4 | Oil Storage Tanks - Underground | T10 – Fuel Installations
4 | 5.9.1.5 | [6 empty] | 5 | Storage Silo
4 | 5.9.1.5.1 | [8 empty] | nr | nr | 1 | Storage Silo - Wood Chip/Pellets | T10 – Fuel Installations
4 | 5.9.1.5.2 | [8 empty] | nr | nr | 2 | Storage Silo - Coal | T10 – Fuel Installations
5 | 5.9.1.6 | [6 empty] | 6 | Thermal insulation
4 | 5.9.1.6.1 | [8 empty] | nr (m²) | m² | 1 | Thermal Insulation - Sheet | T10 – Fuel Installations
4 | 5.9.1.6.2 | [8 empty] | nr (m²) | m² | 2 | Thermal Insulation - Pipe | T10 – Fuel Installations
5 | 5.9.2 |  |  |  |  | 2 | Fuel distribution systems
5 | 5.9.2.1 | [6 empty] | 1 | Pipework systems
5 | 5.9.2.1.1 | [8 empty] | m²/nr | m² | 1 | Pipework - Low Pressure Natural Gas | T10 – Fuel Installations
4 | 5.9.2.1.2 | [8 empty] | m²/nr | m² | 2 | Pipework - Low Pressure Liquefied Petroleum Gas (LPG) | T10 – Fuel Installations
5 | 5.9.2.1.3 | [8 empty] | m²/nr | m² | 3 | Pipework - Oil and Liquid Fuels | T10 – Fuel Installations
5 | 5.9.2.1.4 | [8 empty] | m²/nr | nr | 4 | Fuel Polishing Filtration System | T10 – Fuel Installations
3 | 5.9.2.2 | [6 empty] | 2 | Fuel Oil Transfer Pumps | nr | nr |  |  | T10 – Fuel Installations
4 | 5.9.2.3 | [6 empty] | 3 | Valves
5 | 5.9.2.3.X | [8 empty] | nr | nr | X | See SUP - Valves | T10 – Fuel Installations
5 | 5.9.2.4 | [6 empty] | 4 | Safety Shut-off Valve (SSOV) | nr | nr |  |  | T10 – Fuel Installations
5 | 5.9.2.4.1 | [8 empty] | nr | nr | 1 | Safety Shut-Off Valve (SSOV) - Slam Shut - Gas | T10 – Fuel Installations
4 | 5.9.2.4.2 | [8 empty] | nr | nr | 2 | Safety Shut-Off Valve (SSOV) - Free Fall - Gas | T10 – Fuel Installations
5 | 5.9.2.4.3 | [8 empty] | nr | nr | 3 | Safety Shut-Off Valve (SSOV) - Solenoid - Gas | T10 – Fuel Installations
5 | 5.9.2.4.4 | [8 empty] | nr | nr | 4 | Safety Shut-Off Valve (SSOV) - Free Fall - Oil | T10 – Fuel Installations
5 | 5.9.2.4.5 | [8 empty] | nr | nr | 5 | Safety Shut-Off Valve (SSOV) - Capillary - Oil | T10 – Fuel Installations
2 | 5.9.2.4.6 | [8 empty] | nr | nr | 6 | Safety Shut-Off Valve (SSOV) - Lever - Oil | T10 – Fuel Installations
3 | 5.9.2.4.7 | [8 empty] | nr | nr | 7 | Safety Shut-Off Valve (SSOV) - Solenoid - Oil | T10 – Fuel Installations
4 | 5.9.2.5 | [6 empty] | 5 | Automatic Isolation Valve (AIV) | nr | nr |  |  | T10 – Fuel Installations
4 | 5.9.2.6 | [6 empty] | 6 | Gas Booster Sets | nr | nr |  |  | T10 – Fuel Installations
4 | 5.9.2.7 | [6 empty] | 7 | Gas Governor or Gas Regulator | nr | nr |  |  | T10 – Fuel Installations
4 | 5.9.2.8 | [6 empty] | 8 | Thermal insulation
5 | 5.9.2.8.1 | [8 empty] | nr (m²) | m² | 1 | Thermal Insulation - Sheet | T10 – Fuel Installations
5 | 5.9.2.8.2 | [8 empty] | nr (m²) | m² | 2 | Thermal Insulation - Pipe | T10 – Fuel Installations
5 | 5.9.2.9 | [6 empty] | 9 | Fuel monitoring equipment | nr | nr |  |  | T10 – Fuel Installations
5 | 5.10 |  |  | 10 | Lift and conveyor installations
4 | 5.10.1 |  |  |  |  | 1 | Lifts
5 | 5.10.1.1 | [6 empty] | 1 | Passenger lifts
5 | 5.10.1.1.1 | [8 empty] | nr | nr | 1 | Vertical Platform Lifts - Screw Driven | T11 – Lifts and Conveyors
4 | 5.10.1.1.2 | [8 empty] | nr | nr | 2 | Hydraulic Lifts - Passenger | T11 – Lifts and Conveyors
5 | 5.10.1.1.3 | [8 empty] | nr | nr | 3 | Inclined Platform Lift | T11 – Lifts and Conveyors
5 | 5.10.1.1.4 | [8 empty] | nr | nr | 4 | Electric Traction Lifts - Passenger | T11 – Lifts and Conveyors
3 | 5.10.1.1.5 | [8 empty] | nr | nr | 5 | Machine-Room-Less (MRL) Electric Traction Lifts - Passenger | T11 – Lifts and Conveyors
4 | 5.10.1.1.6 | [8 empty] | nr | nr | 6 | Machine-Room-Less (MRL) Hydraulic Lifts - Passenger | T11 – Lifts and Conveyors
5 | 5.10.1.1.7 | [8 empty] | nr | nr | 7 | Vertical Platform Lifts - Encapsulated Chain Drive | T11 – Lifts and Conveyors
5 | 5.10.1.1.8 | [8 empty] | nr | nr | 8 | Vertical Platform Lifts - Hydraulic | T11 – Lifts and Conveyors
5 | 5.10.1.2 | [6 empty] | 2 | Passenger Lifts – Fire fighting | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.1.3 | [6 empty] | 3 | Wall Climbing Lifts | nr | nr |  |  | T11 – Lifts and Conveyors
4 | 5.10.1.4 | [6 empty] | 4 | Goods lifts
4 | 5.10.1.4.1 | [8 empty] | nr | nr | 1 | Electric Traction Lifts - Goods Only | T11 – Lifts and Conveyors
5 | 5.10.1.4.2 | [8 empty] | nr | nr | 2 | Hydraulic Lifts - Goods Only | T11 – Lifts and Conveyors
4 | 5.10.1.4.3 | [8 empty] | nr | nr | 3 | Lifting Equipment - Trolley (Transfer Car) | T11 – Lifts and Conveyors
5 | 5.10.1.5 | [6 empty] | 5 | Chain Block and Anchorage | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.1.6 | [6 empty] | 6 | Chain Block and Trolley | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.1.7 | [6 empty] | 7 | Electric Chain Block | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.1.8 | [6 empty] | 8 | Enclosed hoists
5 | 5.10.1.8.1 | [8 empty] | nr | nr | 1 | Dumb waiters | T11 – Lifts and Conveyors
5 | 5.10.1.8.2 | [8 empty] | nr | nr | 2 | Construction Hoists - Rack and Pinion and Rope Driven Hoists | T11 – Lifts and Conveyors
5 | 5.10.1.8.3 | [8 empty] | nr | nr | 3 | Rack and Pinion Goods Only Hoists - Permanent Installations | T11 – Lifts and Conveyors
4 | 5.10.1.8.4 | [8 empty] | nr | nr | 4 | Construction Hoists - Temporary Installations | T11 – Lifts and Conveyors
4 | 5.10.1.9 | [6 empty] | 9 | Controls and electrical works
4 | 5.10.1.9.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T11 – Lifts and Conveyors
4 | 5.10.1.10 | [6 empty] | 10 | Davit and Winch | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.1.11 | [6 empty] | 11 | Vertical Platform Lifts - Screw Driven | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.1.12 | [6 empty] | 12 | Vertical Platform Lifts - Encapsulated Chain Drive | nr | nr |  |  | T11 – Lifts and Conveyors
4 | 5.10.1.13 | [6 empty] | 13 | Vertical Platform Lifts - Hydraulic | nr | nr |  |  | T11 – Lifts and Conveyors
2 | 5.10.2 |  |  |  |  | 2 | Escalators
3 | 5.10.2.1 | [6 empty] | 1 | Escalators | nr | nr |  |  | T11 – Lifts and Conveyors
4 | 5.10.2.2 | [6 empty] | 2 | Controls and electrical works
5 | 5.10.2.2.X | [8 empty] | nr | nr / System | X | See SUP - Controllers and sensors | T11 – Lifts and Conveyors
5 | 5.10.3 |  |  |  |  | 3 | Moving pavements
5 | 5.10.3.1 | [6 empty] | 1 | Moving Walks (Travelators) | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.3.2 | [6 empty] | 2 | Controls and electrical works
5 | 5.10.3.2.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T11 – Lifts and Conveyors
5 | 5.10.4 |  |  |  |  | 4 | Powered stair lifts
5 | 5.10.4.1 | [6 empty] | 1 | Powered stair lifts | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.4.2 | [6 empty] | 2 | Controls and electrical works
4 | 5.10.4.2.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T11 – Lifts and Conveyors
4 | 5.10.5 |  |  |  |  | 5 | Conveyors
4 | 5.10.5.1 | [6 empty] | 1 | Goods conveyors
5 | 5.10.5.1.1 | [8 empty] | nr | nr | 1 | Nerak Conveyor Elevator | T11 – Lifts and Conveyors
5 | 5.10.5.1.2 | [8 empty] | nr | nr | 2 | Conveyor Belts | T11 – Lifts and Conveyors
5 | 5.10.5.2 | [6 empty] | 2 | Specialist system (baggage handling) | nr | System |  |  | T11 – Lifts and Conveyors
4 | 5.10.5.3 | [6 empty] | 3 | Controls and electrical works
4 | 5.10.5.3.X | [8 empty] | nr | nr / System | X | See SUP - Controllers and sensors | T11 – Lifts and Conveyors
4 | 5.10.6 |  |  |  |  | 6 | Dock levellers and scissor lifts
4 | 5.10.6.1 | [6 empty] | 1 | Dock levellers | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.6.2 | [6 empty] | 2 | Scissor lifts | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.6.3 | [6 empty] | 3 | Controls and electrical works
5 | 5.10.6.3.X | [8 empty] | nr | nr / System | X | See SUP - Controllers and sensors | T11 – Lifts and Conveyors
5 | 5.10.7 |  |  |  |  | 7 | Cranes and unenclosed hoists
4 | 5.10.7.1 | [6 empty] | 1 | Cranes
5 | 5.10.7.1.1 | [8 empty] | nr | nr | 1 | Gantry Cranes | T11 – Lifts and Conveyors
4 | 5.10.7.1.2 | [8 empty] | nr | nr | 2 | Pillar Jib Cranes | T11 – Lifts and Conveyors
4 | 5.10.7.2 | [6 empty] | 2 | Controls and electrical works
4 | 5.10.7.2.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T11 – Lifts and Conveyors
4 | 5.10.7.3 | [6 empty] | 3 | Lifting equipment
3 | 5.10.7.3.1 | [8 empty] | nr | nr | 1 | Lifting Beams | T11 – Lifts and Conveyors
4 | 5.10.7.3.2 | [8 empty] | nr | nr | 2 | Metal Mesh Sling | T11 – Lifts and Conveyors
4 | 5.10.7.3.3 | [8 empty] | nr | nr | 3 | Mobile Racking | T11 – Lifts and Conveyors
5 | 5.10.7.3.4 | [8 empty] | nr | nr | 4 | Rigging Hooks | T11 – Lifts and Conveyors
3 | 5.10.7.3.5 | [8 empty] | nr | nr | 5 | Shackle | T11 – Lifts and Conveyors
4 | 5.10.7.3.6 | [8 empty] | nr | nr | 6 | Steel Chain Sling | T11 – Lifts and Conveyors
4 | 5.10.7.3.7 | [8 empty] | nr | nr | 7 | Synthetic Roundsling | T11 – Lifts and Conveyors
5 | 5.10.7.3.8 | [8 empty] | nr | nr | 8 | Synthetic Web Slings | T11 – Lifts and Conveyors
3 | 5.10.7.3.9 | [8 empty] | nr | nr | 9 | Vehicle Tail Lift | T11 – Lifts and Conveyors
4 | 5.10.7.3.10 | [8 empty] | nr | nr | 10 | Wire Rope Sling | T11 – Lifts and Conveyors
4 | 5.10.7.3.11 | [8 empty] | nr | nr | 11 | Powered Suspended Lighting Hoist (Chandeliers) | T11 – Lifts and Conveyors
5 | 5.10.7.4 | [6 empty] | 4 | Travelling cranes | nr | nr |  |  | T11 – Lifts and Conveyors
3 | 5.10.7.5 | [6 empty] | 5 | Unenclosed hoists | nr | nr |  |  | T11 – Lifts and Conveyors
4 | 5.10.8 |  |  |  |  | 8 | Car lifts, car stacking systems, turntables, etc.
5 | 5.10.8.1 | [6 empty] | 1 | Car lifts | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.8.2 | [6 empty] | 2 | Controls and electrical works
4 | 5.10.8.2.X | [8 empty] | nr | nr / System | X | See SUP - Controllers and sensors | T11 – Lifts and Conveyors
4 | 5.10.8.3 | [6 empty] | 3 | Car stacking | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.8.4 | [6 empty] | 4 | Vehicle turntables | nr | nr |  |  | T11 – Lifts and Conveyors
3 | 5.10.9 |  |  |  |  | 9 | Document handling/delivery systems
4 | 5.10.9.1 | [6 empty] | 1 | Warehouse picking systems
4 | 5.10.9.1.1 | [8 empty] | nr | nr | 1 | High Level Order Picker | T11 – Lifts and Conveyors
4 | 5.10.9.1.2 | [8 empty] | nr | nr | 2 | Low Level Order Picker/Ride on Pallet Truck | T11 – Lifts and Conveyors
5 | 5.10.9.1.3 | [8 empty] | nr | nr | 3 | Very Narrow Aisle (VNA) Combi | T11 – Lifts and Conveyors
3 | 5.10.9.2 | [6 empty] | 2 | Rail Dependent Storage and Retrieval Equipment | nr | nr |  |  | T11 – Lifts and Conveyors
4 | 5.10.10 |  |  |  |  | 10 | Other transport systems
5 | 5.10.10.1 | [6 empty] | 1 | Paternoster lifts | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.10.2 | [6 empty] | 2 | Disability hoist
4 | 5.10.10.2.1 | [8 empty] | nr | nr | 1 | Patient/Personnel Lift (Mobility) | T11 – Lifts and Conveyors
5 | 5.10.10.2.2 | [8 empty] | nr | nr | 2 | Evacuation Lifts | T11 – Lifts and Conveyors
4 | 5.10.10.2.3 | [8 empty] | nr | nr | 3 | Patient Bath Hoist | T11 – Lifts and Conveyors
5 | 5.10.10.2.4 | [8 empty] | nr | nr | 4 | Patient Bed Hoist | T11 – Lifts and Conveyors
5 | 5.10.10.2.5 | [8 empty] | nr | nr | 5 | Patient Bath Hoist | T11 – Lifts and Conveyors
5 | 5.10.10.2.6 | [8 empty] | nr | nr | 6 | Patient Bed Hoist | T11 – Lifts and Conveyors
5 | 5.10.10.3 | [6 empty] | 3 | Transport systems - Other
5 | 5.10.10.3.1 | [8 empty] | nr | nr | 1 | Articulated Swivel Truck | T11 – Lifts and Conveyors
5 | 5.10.10.3.2 | [8 empty] | nr | nr | 2 | Electric Tow Truck | T11 – Lifts and Conveyors
5 | 5.10.10.3.3 | [8 empty] | nr | nr | 3 | Powered Pallet Truck | T11 – Lifts and Conveyors
5 | 5.10.10.3.4 | [8 empty] | nr | nr | 4 | Reach Truck | T11 – Lifts and Conveyors
5 | 5.10.10.3.5 | [8 empty] | nr | nr | 5 | Electric Counter Balance | T11 – Lifts and Conveyors
5 | 5.10.10.3.6 | [8 empty] | nr | nr | 6 | Fixed Mast Stackers | T11 – Lifts and Conveyors
5 | 5.10.10.3.7 | [8 empty] | nr | nr | 7 | Internal Combustion Counter Balance | T11 – Lifts and Conveyors
4 | 5.10.10.4 | [6 empty] | 4 | Controls and electrical works
4 | 5.10.10.4.X | [8 empty] | nr / System | nr / System | X | See SUP - Controllers and sensors | T11 – Lifts and Conveyors
3 | 5.10.10.5 | [6 empty] | 5 | Electrically Powered Wheelchair | nr | nr |  |  | T11 – Lifts and Conveyors
4 | 5.10.10.6 | [6 empty] | 6 | Battery Change Over (Battery Powered Vehicles) | nr | nr |  |  | T11 – Lifts and Conveyors
4 | 5.10.10.7 | [6 empty] | 7 | Battery Topping (Battery Powered Vehicles) | nr | nr |  |  | T11 – Lifts and Conveyors
5 | 5.10.10.8 | [6 empty] | 8 | Work mobile platforms
4 | 5.10.10.8.1 | [8 empty] | nr | nr | 1 | Electric | T11 – Lifts and Conveyors
4 | 5.10.10.8.2 | [8 empty] | nr | nr | 2 | Internal Combustion | T11 – Lifts and Conveyors
3 | 5.11 |  |  | 11 | Fire and lightning protection
4 | 5.11.1 |  |  |  |  | 1 | Firefighting systems
5 | 5.11.1.1 | [6 empty] | 1 | Fire hose reels
5 | 5.11.1.1.1 | [8 empty] | nr | nr | 1 | Fire Hose Reels - Pressure Boosting Sets | T12 – Safety Systems
5 | 5.11.1.1.2 | [8 empty] | nr | nr | 2 | Fire Hose Reels - Static or Swinging | T12 – Safety Systems
4 | 5.11.1.2 | [6 empty] | 2 | Dry risers
3 | 5.11.1.2.1 | [8 empty] | nr | nr | 1 | Steel galvanised (open) | T12 – Safety Systems
4 | 5.11.1.2.2 | [8 empty] | nr | nr | 2 | Plastic or non-metallic | T12 – Safety Systems
4 | 5.11.1.3 | [6 empty] | 3 | Wet risers
5 | 5.11.1.3.1 | [8 empty] | nr | nr | 1 | Steel galvanised (closed) | T12 – Safety Systems
5 | 5.11.1.3.2 | [8 empty] | nr | nr | 2 | Plastic or non-metallic | T12 – Safety Systems
5 | 5.11.1.4 | [6 empty] | 4 | Fire and Smoke Curtains/Barriers |  |  |  |  | T12 – Safety Systems
5 | 5.11.1.4.1 | [8 empty] | nr | nr | 1 | Smoke Barrier - Active | T12 – Safety Systems
5 | 5.11.1.4.2 | [8 empty] | nr | nr | 2 | Smoke Barrier - Static | T12 – Safety Systems
5 | 5.11.1.4.3 | [8 empty] | nr | nr | 3 | Fire Curtains - Active | T12 – Safety Systems
4 | 5.11.1.4.4 | [8 empty] | nr | nr | 4 | Fire Curtains - Static | T12 – Safety Systems
5 | 5.11.1.5 | [6 empty] | 5 | Pipework In General
5 | 5.11.1.5.X | [8 empty] | m² | m² | X | See SUP - Pipework | T12 – Safety Systems
5 | 5.11.1.6 | [6 empty] | 6 | Fire Hydrants | nr | nr |  |  | T12 – Safety Systems
5 | 5.11.1.7 | [6 empty] | 7 | Thermal insulation
5 | 5.11.1.7.1 | [8 empty] | m² | m² | 1 | Thermal Insulation - Sheet | T12 – Safety Systems
5 | 5.11.1.7.2 | [8 empty] | m² | m² | 2 | Thermal Insulation - Pipe | T12 – Safety Systems
5 | 5.11.1.8 | [6 empty] | 8 | Control components
4 | 5.11.1.8.X | [8 empty] | nr | nr / System | X | See SUP - Controllers and sensors | T12 – Safety Systems
5 | 5.11.1.9 | [6 empty] | 9 | Firefighters switch | nr | nr |  |  | T12 – Safety Systems
4 | 5.11.1.10 | [6 empty] | 10 | Fire Extinguishers
4 | 5.11.1.10.1 | [8 empty] | nr | nr | 1 | Foam (Stored Pressure) | T12 – Safety Systems
4 | 5.11.1.10.2 | [8 empty] | nr | nr | 2 | Powder (Gas Cartridge) | T12 – Safety Systems
4 | 5.11.1.10.3 | [8 empty] | nr | nr | 3 | Water (Gas Cartridge) | T12 – Safety Systems
5 | 5.11.1.10.4 | [8 empty] | nr | nr | 4 | Water Stored Pressure | T12 – Safety Systems
5 | 5.11.1.10.5 | [8 empty] | nr | nr | 5 | Powder (Stored Pressure) | T12 – Safety Systems
2 | 5.11.1.10.6 | [8 empty] | nr | nr | 6 | Specialist Powder (Stored Pressure) | T12 – Safety Systems
3 | 5.11.1.10.7 | [8 empty] | nr | nr | 7 | Wet Chemical (Stored Pressure) | T12 – Safety Systems
4 | 5.11.1.11 | [6 empty] | 11 | Other Equipment
5 | 5.11.1.11.1 | [8 empty] | nr | nr | 1 | Gas Suppression (Portable) | T12 – Safety Systems
5 | 5.11.1.11.2 | [8 empty] | nr | nr | 2 | Carbon Dioxide | T12 – Safety Systems
4 | 5.11.1.12 | [6 empty] | 12 | Fire Shutters | nr | nr |  |  | T12 – Safety Systems
4 | 5.11.2 |  |  |  |  | 2 | Fire suppression systems
4 | 5.11.2.1 | [6 empty] | 1 | Sprinkler Systems
5 | 5.11.2.1.1 | [8 empty] | m²/nr | m² | 1 | Sprinkler systems - dry | T12 – Safety Systems
5 | 5.11.2.1.2 | [8 empty] | m²/nr | m² | 2 | Sprinkler systems - wet | T12 – Safety Systems
5 | 5.11.2.1.3 | [8 empty] | m²/nr | m² | 3 | Sprinkler Systems - Domestic and Residential | T12 – Safety Systems
5 | 5.11.2.2 | [6 empty] | 2 | Deluge systems | m²/nr | m² |  |  | T12 – Safety Systems
4 | 5.11.2.3 | [6 empty] | 3 | Gas firefighting systems
4 | 5.11.2.3.1 | [8 empty] | m²/nr | Item | 1 | Gas Extinguishing Systems | T12 – Safety Systems
4 | 5.11.2.3.2 | [8 empty] | m²/nr | Item | 2 | Fire Extinguishing System - Carbon Dioxide Total Flooding | T12 – Safety Systems
5 | 5.11.2.3.3 | [8 empty] | m²/nr | Item | 3 | Fire Extinguishing System – Condensed Aerosol Total Flooding | T12 – Safety Systems
5 | 5.11.2.3.4 | [8 empty] | m²/nr | Item | 4 | Fire Extinguishing System - Inert Gas Total Flooding | T12 – Safety Systems
4 | 5.11.2.4 | [6 empty] | 4 | Foam firefighting systems | System | System |  |  | T12 – Safety Systems
5 | 5.11.2.5 | [6 empty] | 5 | Distribution pipelines, ancillaries and fittings | m²/nr | m² |  |  | T12 – Safety Systems
4 | 5.11.2.6 | [6 empty] | 6 | Thermal insulation
4 | 5.11.2.6.1 | [8 empty] | m²/nr | m² | 1 | Thermal Insulation - Sheet | T12 – Safety Systems
5 | 5.11.2.6.2 | [8 empty] | m²/nr | m² | 2 | Thermal Insulation - Pipe | T12 – Safety Systems
5 | 5.11.2.7 | [6 empty] | 7 | Control components
5 | 5.11.2.7.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T12 – Safety Systems
5 | 5.11.2.8 | [6 empty] | 8 | Kitchen Fire Suppression System - Wet Chemical Extinguishant | System | System |  |  | T12 – Safety Systems
5 | 5.11.3 |  |  |  |  | 3 | Lightning protection
5 | 5.11.3.1 | [6 empty] | 1 | Lightning protection
5 | 5.11.3.1.1 | [8 empty] | m²/nr | m² | 1 | Lightning Conductor and Earth | T12 – Safety Systems
4 | 5.11.3.1.2 | [8 empty] | m²/nr | nr | 2 | Lightning Conductors in Hazardous Areas | T12 – Safety Systems
5 | 5.11.4 |  |  |  |  | 4 | Fire Stopping
5 | 5.11.4.1 | [6 empty] | 1 | Fire stopping | nr | nr |  |  | T12 – Safety Systems
4 | 5.11.5 |  |  |  |  | 5 | Fire Protection
3 | 5.11.5.1 | [6 empty] | 1 | Secure Information Boxes | nr | nr |  |  | T12 – Safety Systems
4 | 5.11.5.2 | [6 empty] | 2 | Evacuation Alert Systems | nr | nr |  |  | T12 – Safety Systems
5 | 5.11.5.3 | [6 empty] | 3 | Safety Signs | nr | nr |  |  | T12 – Safety Systems
5 | 5.11.5.4 | [6 empty] | 4 | Illuminated Safety Signs | nr | nr |  |  | T12 – Safety Systems
5 | 5.11.5.5 | [6 empty] | 5 | Fire Blankets | nr | nr |  |  | T12 – Safety Systems
4 | 5.11.6 |  |  |  |  | 6 | Fire doors and mechanisms
4 | 5.11.6.1 | [6 empty] | 1 | Electronically Secured Escape Doors and Fire Exits - Automatic Door Release Mechanisms | nr | nr |  |  | T12 – Safety Systems
5 | 5.11.6.2 | [6 empty] | 2 | Electrically Held Open Fire Doors - Automatic Door Release Mechanisms | nr | nr |  |  | T12 – Safety Systems
5 | 5.12 |  |  | 12 | Communication, security and control systems
5 | 5.12.1 |  |  |  |  | 1 | Communication systems
5 | 5.12.1.1 | [6 empty] | 1 | Intercom System | nr | nr |  |  | T13 – Communication, Security and Controls
4 | 5.12.1.2 | [6 empty] | 2 | Emergency Voice Communication (EVC) Systems | nr | nr |  |  | T13 – Communication, Security and Controls
4 | 5.12.1.3 | [6 empty] | 3 | Computer networking, modems, etc. | m²/nr | nr |  |  | T13 – Communication, Security and Controls
4 | 5.12.1.4 | [6 empty] | 4 | Multiplexes data terminals | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.1.5 | [6 empty] | 5 | Data Rack | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.1.6 | [6 empty] | 6 | Paging and emergency
4 | 5.12.1.6.1 | [8 empty] | m²/nr | nr | 1 | Aerials, radio and paging equipment | T13 – Communication, Security and Controls
5 | 5.12.1.6.2 | [8 empty] | m²/nr | nr | 2 | Emergency call buttons¦ Pull cords etc. | T13 – Communication, Security and Controls
4 | 5.12.1.6.3 | [8 empty] | m²/nr | nr | 3 | Paging and emergency call systems | T13 – Communication, Security and Controls
3 | 5.12.1.6.4 | [8 empty] | nr | nr | 4 | Bedhead Services | T13 – Communication, Security and Controls
4 | 5.12.1.6.5 | [8 empty] | nr | nr | 5 | Cell call systems | T13 – Communication, Security and Controls
5 | 5.12.1.7 | [6 empty] | 7 | Public address and conference audio
5 | 5.12.1.7.1 | [8 empty] | m²/nr | m² | 1 | Public address system | T13 – Communication, Security and Controls
3 | 5.12.1.7.2 | [8 empty] | m²/nr | nr | 2 | Conference audio facilities | T13 – Communication, Security and Controls
4 | 5.12.1.7.3 | [8 empty] | m²/nr | nr | 3 | Induction loop systems | T13 – Communication, Security and Controls
3 | 5.12.1.7.4 | [8 empty] | m²/nr | nr | 4 | Hospital radio facilities | T13 – Communication, Security and Controls
4 | 5.12.1.7.5 | [8 empty] | System | Item | 5 | Background noise systems | T13 – Communication, Security and Controls
4 | 5.12.1.7.6 | [8 empty] | m²/nr | m² | 6 | Microphones, amplifiers and speakers | T13 – Communication, Security and Controls
4 | 5.12.1.7.7 | [8 empty] | m²/nr | nr | 7 | Indicator boards | T13 – Communication, Security and Controls
4 | 5.12.1.8 | [6 empty] | 8 | Radio systems
4 | 5.12.1.8.1 | [8 empty] | nr | nr | 1 | Equipment High Masts - Fixed | T13 – Communication, Security and Controls
3 | 5.12.1.8.2 | [8 empty] | nr | nr | 2 | Equipment High Masts - Base-Hinged | T13 – Communication, Security and Controls
4 | 5.12.1.8.3 | [8 empty] | m²/nr | nr | 3 | Radios | T13 – Communication, Security and Controls
4 | 5.12.1.9 | [6 empty] | 9 | Projection systems
2 | 5.12.1.9.1 | [8 empty] | nr | nr | 1 | Cinematographic equipment | T13 – Communication, Security and Controls
3 | 5.12.1.9.2 | [8 empty] | nr | nr | 2 | Fixed and portable projectors | T13 – Communication, Security and Controls
4 | 5.12.1.9.3 | [8 empty] | nr | nr | 3 | Screens and back projection equipment | T13 – Communication, Security and Controls
4 | 5.12.1.9.4 | [8 empty] | nr | nr | 4 | Sound equipment | T13 – Communication, Security and Controls
4 | 5.12.1.10 | [6 empty] | 10 | Fire detection and alarm systems
4 | 5.12.1.10.1 | [8 empty] | m²/nr | m² | 1 | Fire Alarm - Voice Alarm Systems | T12 – Safety Systems
4 | 5.12.1.10.2 | [8 empty] | m²/nr | m² | 2 | Fire Alarm Installations - Domestic - Grade A Systems | T12 – Safety Systems
4 | 5.12.1.10.3 | [8 empty] | m²/nr | m² | 3 | Fire Alarm Installations - Domestic - Grade C Systems | T12 – Safety Systems
5 | 5.12.1.10.4 | [8 empty] | m²/nr | m² | 4 | Fire Alarm Installations - Domestic - Grade D1/D2 Systems | T12 – Safety Systems
5 | 5.12.1.10.5 | [8 empty] | m²/nr | m² | 5 | Fire Alarm Installations - Domestic - Grade F1/F2 Systems | T12 – Safety Systems
5 | 5.12.1.10.6 | [8 empty] | m²/nr | m² | 6 | Fire Alarm Installations - Non-Domestic - Category L1 Systems | T12 – Safety Systems
5 | 5.12.1.10.7 | [8 empty] | m²/nr | m² | 7 | Fire Alarm Installations - Non-Domestic - Category L2 Systems | T12 – Safety Systems
5 | 5.12.1.10.8 | [8 empty] | m²/nr | m² | 8 | Fire Alarm Installations - Non-Domestic - Category L3 Systems | T12 – Safety Systems
4 | 5.12.1.10.9 | [8 empty] | m²/nr | m² | 9 | Fire Alarm Installations - Non-Domestic - Category L4 Systems | T12 – Safety Systems
5 | 5.12.1.10.10 | [8 empty] | m²/nr | m² | 10 | Fire Alarm Installations - Non-Domestic - Category L5 Systems | T12 – Safety Systems
5 | 5.12.1.10.11 | [8 empty] | m²/nr | m² | 11 | Fire Alarm Installations - Non-Domestic - Category M Systems | T12 – Safety Systems
5 | 5.12.1.10.12 | [8 empty] | m²/nr | m² | 12 | Fire Alarm Installations - Non-Domestic - Category P1 Systems | T12 – Safety Systems
5 | 5.12.1.10.13 | [8 empty] | m²/nr | m² | 13 | Fire Alarm Installations - Non-Domestic - Category P2 Systems | T12 – Safety Systems
5 | 5.12.1.10.14 | [8 empty] | m²/nr | m² | 14 | Fire Alarm - Voice Alarm Systems (VAS) | T12 – Safety Systems
5 | 5.12.1.10.15 | [8 empty] | m²/nr | m² | 15 | Fire Alarm - Voice Alarm Systems (VAS) | T12 – Safety Systems
5 | 5.12.1.11 | [6 empty] | 11 | Carbon dioxide sensor
4 | 5.12.1.11.1 | [8 empty] | nr | nr | 1 | Gas Sensors - Carbon Dioxide - Wall-Mounted | T12 – Safety Systems
5 | 5.12.1.11.2 | [8 empty] | nr | nr | 2 | Gas Sensors - Carbon Dioxide - Duct-Mounted | T12 – Safety Systems
5 | 5.12.1.12 | [6 empty] | 12 | Heat detector
5 | 5.12.1.12.1 | [8 empty] | nr | nr | 1 | Heat Alarms - Residential and Domestic - England | T12 – Safety Systems
4 | 5.12.1.12.2 | [8 empty] | nr | nr | 2 | Heat Alarms - Residential and Domestic - Northern Ireland | T12 – Safety Systems
5 | 5.12.1.12.3 | [8 empty] | nr | nr | 3 | Heat Alarms - Residential and Domestic - Scotland | T12 – Safety Systems
5 | 5.12.1.12.4 | [8 empty] | nr | nr | 4 | Heat Alarms - Residential and Domestic - Wales | T12 – Safety Systems
5 | 5.12.1.13 | [6 empty] | 13 | Carbon monoxide sensor
5 | 5.12.1.13.1 | [8 empty] | nr | nr | 1 | Carbon Monoxide Alarms - Residential and Domestic - England | T12 – Safety Systems
4 | 5.12.1.13.2 | [8 empty] | nr | nr | 2 | Carbon Monoxide Alarms - Residential and Domestic - Northern Ireland | T12 – Safety Systems
5 | 5.12.1.13.3 | [8 empty] | nr | nr | 3 | Carbon Monoxide Alarms - Residential and Domestic - Scotland | T12 – Safety Systems
5 | 5.12.1.13.4 | [8 empty] | nr | nr | 4 | Carbon Monoxide Alarms - Residential and Domestic - Wales | T12 – Safety Systems
5 | 5.12.1.14 | [6 empty] | 14 | Gas Detection/Flammable
5 | 5.12.1.14.1 | [8 empty] | nr | nr | 1 | Gas Detection/Flammable | T12 – Safety Systems
5 | 5.12.1.14.2 | [8 empty] | nr | nr | 2 | Gas Detectors - Fixed - Flammable Gases and Oxygen | T12 – Safety Systems
5 | 5.12.1.15 | [6 empty] | 15 | Smoke detectors
5 | 5.12.1.15.1 | [8 empty] | nr | nr | 1 | Aspirating Smoke Detection (ASD) System | T12 – Safety Systems
5 | 5.12.1.15.2 | [8 empty] | nr | nr | 2 | Smoke Alarms - Residential and Domestic - England | T12 – Safety Systems
5 | 5.12.1.15.3 | [8 empty] | nr | nr | 3 | Smoke Alarms - Residential and Domestic - Northern Ireland | T12 – Safety Systems
5 | 5.12.1.15.4 | [8 empty] | nr | nr | 4 | Smoke Alarms - Residential and Domestic - Scotland | T12 – Safety Systems
5 | 5.12.1.15.5 | [8 empty] | nr | nr | 5 | Smoke Alarms - Residential and Domestic - Wales | T12 – Safety Systems
5 | 5.12.1.15.6 | [8 empty] | nr | nr | 6 | Smoke Detectors | T12 – Safety Systems
5 | 5.12.1.16 | [6 empty] | 16 | Batteries – lead acid unsealed | nr | nr |  |  | T12 – Safety Systems
5 | 5.12.1.17 | [6 empty] | 17 | Batteries – sealed | m²/nr | nr |  |  | T12 – Safety Systems
5 | 5.12.1.18 | [6 empty] | 18 | Battery charging equipment | m²/nr | nr |  |  | T12 – Safety Systems
4 | 5.12.1.19 | [6 empty] | 19 | Liquid detection systems | m²/nr | nr |  |  | T12 – Safety Systems
5 | 5.12.1.20 | [6 empty] | 20 | Clocks, card clocks and flexitime installations
5 | 5.12.1.20.1 | [8 empty] | nr | nr | 1 | Clocks - Mains and Battery Types | T13 – Communication, Security and Controls
4 | 5.12.1.20.2 | [8 empty] | nr | nr | 2 | Clocks - Master Type | T13 – Communication, Security and Controls
5 | 5.12.1.20.3 | [8 empty] | nr | nr | 3 | Time Clock (Clocking In Machines) | T13 – Communication, Security and Controls
5 | 5.12.1.20.4 | [8 empty] | nr | nr | 4 | Mechanical Heritage Clocks | T13 – Communication, Security and Controls
5 | 5.12.1.21 | [6 empty] | 21 | Television systems
5 | 5.12.1.21.1 | [8 empty] | nr | nr | 1 | Television and Signal Receiving Equipment | T13 – Communication, Security and Controls
4 | 5.12.1.21.2 | [8 empty] | nr | nr | 2 | TV Tuners and Control Panels | T13 – Communication, Security and Controls
5 | 5.12.1.22 | [6 empty] | 22 | TV monitors | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.1.23 | [6 empty] | 23 | Pneumatic message systems
5 | 5.12.1.23.1 | [8 empty] | nr | nr | 1 | Pneumatic Tube Systems | T13 – Communication, Security and Controls
5 | 5.12.1.23.2 | [8 empty] | nr | nr | 2 | Vacuum Tubes - Cash Handling | T13 – Communication, Security and Controls
4 | 5.12.1.23.3 | [8 empty] | m² | m² | 3 | Vacuum Tube POD System | T13 – Communication, Security and Controls
5 | 5.12.1.24 | [6 empty] | 24 | Video Detection Systems
5 | 5.12.1.24.1 | [8 empty] | nr | nr | 1 | Video Flame Detector (VFD) and Detection Systems | T13 – Communication, Security and Controls
4 | 5.12.1.24.2 | [8 empty] | nr | nr | 2 | Video Smoke Detection (VSD) | T13 – Communication, Security and Controls
5 | 5.12.2 |  |  |  |  | 2 | Security systems
5 | 5.12.2.1 | [6 empty] | 1 | Surveillance equipment
5 | 5.12.2.1.1 | [8 empty] | nr/m² | m² | 1 | Closed-Circuit Television (CCTV) | T13 – Communication, Security and Controls
5 | 5.12.2.1.2 | [8 empty] | m²/nr | m² | 2 | Video Surveillance System (VSS) | T13 – Communication, Security and Controls
5 | 5.12.2.1.3 | [8 empty] | nr | nr | 3 | Video Motion Detection | T13 – Communication, Security and Controls
5 | 5.12.2.2 | [6 empty] | 2 | Equipment Columns
4 | 5.12.2.2.1 | [8 empty] | nr | nr | 1 | Equipment Columns - Fixed | T13 – Communication, Security and Controls
4 | 5.12.2.2.2 | [8 empty] | nr | nr | 2 | Equipment Columns - Base-Hinged | T13 – Communication, Security and Controls
4 | 5.12.2.3 | [6 empty] | 3 | Intruder and Hold-Up Alarm Systems (I&HAS) - Grade 1 | m²/nr | m² |  |  | T13 – Communication, Security and Controls
4 | 5.12.2.4 | [6 empty] | 4 | Intruder and Hold-Up Alarm Systems (I&HAS) - Grade 2 | m²/nr | m² |  |  | T13 – Communication, Security and Controls
4 | 5.12.2.5 | [6 empty] | 5 | Intruder and Hold-Up Alarm Systems (I&HAS) - Grade 3 | m²/nr | m² |  |  | T13 – Communication, Security and Controls
5 | 5.12.2.6 | [6 empty] | 6 | Intruder and Hold-Up Alarm Systems (I&HAS) - Grade 4 | m²/nr | m² |  |  | T13 – Communication, Security and Controls
5 | 5.12.2.7 | [6 empty] | 7 | Occupancy Sensors | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.2.8 | [6 empty] | 8 | Light Level Sensors | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.2.9 | [6 empty] | 9 | Active Infrared Alarms | nr | nr |  |  | T13 – Communication, Security and Controls
4 | 5.12.2.10 | [6 empty] | 10 | Walk-Through Metal Detectors | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.2.11 | [6 empty] | 11 | X-Ray Scanners | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.2.12 | [6 empty] | 12 | Ultraviolet (UV) Scanners | nr | nr |  |  | T13 – Communication, Security and Controls
4 | 5.12.2.13 | [6 empty] | 13 | Personal Safety Alarms | nr | nr |  |  | T13 – Communication, Security and Controls
4 | 5.12.2.14 | [6 empty] | 14 | Passive Infrared Alarms | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.2.15 | [6 empty] | 15 | Microwave Motion Sensors | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.2.16 | [6 empty] | 16 | Access control systems
5 | 5.12.2.16.1 | [8 empty] | m²/nr | m² | 1 | Access Control | T13 – Communication, Security and Controls
4 | 5.12.2.16.2 | [8 empty] | nr | nr | 2 | Clocks - Mains and Battery Types | T13 – Communication, Security and Controls
5 | 5.12.2.16.3 | [8 empty] | nr (m²) | nr | 3 | Automated doors and barriers | T13 – Communication, Security and Controls
5 | 5.12.2.17 | [6 empty] | 17 | Door entry systems
3 | 5.12.2.17.1 | [8 empty] | nr | nr | 1 | Video Door Intercoms | T13 – Communication, Security and Controls
4 | 5.12.2.18 | [6 empty] | 18 | Security lighting
5 | 5.12.2.18.1 | [8 empty] | nr | nr | 1 | Outdoor Lighting (Security) | T13 – Communication, Security and Controls
5 | 5.12.2.18.2 | [8 empty] | nr | nr | 2 | Searchlights and Floodlights | T13 – Communication, Security and Controls
5 | 5.12.2.19 | [6 empty] | 19 | Biometric Identification Systems | nr | nr |  |  | T13 – Communication, Security and Controls
4 | 5.12.2.20 | [6 empty] | 20 | Security Patrol Tracking | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.2.21 | [6 empty] | 21 | Electric Locking Systems | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.2.22 | [6 empty] | 22 | Automated doors and gates
4 | 5.12.2.22.1 | [8 empty] | nr | nr | 1 | Sliding Gates - Powered | T13 – Communication, Security and Controls
4 | 5.12.2.22.2 | [8 empty] | nr | nr | 2 | Swing Gates - Powered | T13 – Communication, Security and Controls
4 | 5.12.2.22.3 | [8 empty] | nr | nr | 3 | Revolving Pedestrian Doors - Powered | T13 – Communication, Security and Controls
4 | 5.12.2.22.4 | [8 empty] | nr | nr | 4 | Roller Shutter Doors - Powered | T13 – Communication, Security and Controls
4 | 5.12.2.22.5 | [8 empty] | nr | nr | 5 | Sliding Pedestrian Doors - Powered | T13 – Communication, Security and Controls
4 | 5.12.2.22.6 | [8 empty] | nr | nr | 6 | Swing Pedestrian Doors - Powered | T13 – Communication, Security and Controls
4 | 5.12.2.22.7 | [8 empty] | nr | nr | 7 | Tripod Turnstile - Powered | T13 – Communication, Security and Controls
4 | 5.12.2.22.8 | [8 empty] | nr | nr | 8 | High Security Doors | T13 – Communication, Security and Controls
4 | 5.12.2.22.9 | [8 empty] | nr | nr | 9 | Folding Doors - High Speed - Powered | T13 – Communication, Security and Controls
4 | 5.12.2.22.10 | [8 empty] | nr | nr | 10 | Sectional Overhead Doors - Powered | T13 – Communication, Security and Controls
4 | 5.12.2.22.11 | [8 empty] | nr | nr | 11 | Roller Security Grilles - Powered | T13 – Communication, Security and Controls
4 | 5.12.2.22.12 | [8 empty] | nr | nr | 12 | PVC Roll-Up Doors - High Speed - Powered | T13 – Communication, Security and Controls
4 | 5.12.2.22.13 | [8 empty] | nr | nr | 13 | Hydraulic Door Gear and Pump | T13 – Communication, Security and Controls
4 | 5.12.2.23 | [6 empty] | 23 | Pegging system (monitoring security guard rounds) | System | System |  |  | T13 – Communication, Security and Controls
5 | 5.12.3 |  |  |  |  | 3 | Central control/building management systems
5 | 5.12.3.1 | [6 empty] | 1 | BMS - Central Operator Station | m²/nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.3.2 | [6 empty] | 2 | BMS - Communications | m²/nr | nr |  |  | T13 – Communication, Security and Controls
4 | 5.12.3.3 | [6 empty] | 3 | BMS -Outstations | m²/nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.3.4 | [6 empty] | 4 | BMS - Software Functions | m²/nr | nr |  |  | T13 – Communication, Security and Controls
4 | 5.12.3.5 | [6 empty] | 5 | BMS - Sensors | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.12.3.6 | [6 empty] | 6 | BMS - Actuators | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 5.13 |  |  | 13 | Specialist installations
4 | 5.13.1 |  |  |  |  | 1 | Specialist piped supply systems
4 | 5.13.1.1 | [6 empty] | 1 | Medical and laboratory gas supply systems Eng & Wales
4 | 5.13.1.1.1 | [8 empty] | nr/m² | nr | 1 | Terminal Units - General Areas | T16 – Specialist
4 | 5.13.1.1.2 | [8 empty] | nr/m² | nr | 2 | Terminal Units - High Acuity Areas | T16 – Specialist
5 | 5.13.1.1.3 | [8 empty] | nr/m² | nr | 3 | Central Alarm Panels | T16 – Specialist
5 | 5.13.1.1.4 | [8 empty] | nr/m² | nr | 4 | Local Alarms - High Acuity Areas | T16 – Specialist
5 | 5.13.1.1.5 | [8 empty] | nr/m² | nr | 5 | Area Valve Service Units (AVSU) | T16 – Specialist
5 | 5.13.1.1.6 | [8 empty] | nr/m² | nr | 6 | Pressure Reducing Sets | T16 – Specialist
5 | 5.13.1.1.7 | [8 empty] | nr/m² | m² | 7 | Medical Gases Piped Distribution System and Line Valves | T16 – Specialist
5 | 5.13.1.1.8 | [8 empty] | nr/m² | nr | 8 | Automatic Cylinder Manifolds - Including Headers and Tailpipes | T16 – Specialist
5 | 5.13.1.1.9 | [8 empty] | nr/m² | nr | 9 | Manual Standby Manifolds - Including Headers and Tailpipes | T16 – Specialist
5 | 5.13.1.1.10 | [8 empty] | nr/m² | nr | 10 | Medical and Surgical Compressed Air Plant | T16 – Specialist
5 | 5.13.1.1.11 | [8 empty] | nr/m² | nr | 11 | Air Dryer and Regulator Assembly | T16 – Specialist
5 | 5.13.1.1.12 | [8 empty] | nr/m² | nr | 12 | Medical Vacuum Plant | T16 – Specialist
5 | 5.13.1.1.13 | [8 empty] | nr/m² | nr | 13 | Anaesthetic Gas Scavenging (AGS) Systems | T16 – Specialist
5 | 5.13.1.1.15 | [8 empty] | nr/m² | nr | 15 | Cylinder Stores | T16 – Specialist
5 | 5.13.1.1.18 | [8 empty] | nr/m² | nr | 18 | Emergency Supply Manifolds/Emergency Reserve Manifolds (ESM/ERM) | T16 – Specialist
4 | 5.13.1.1.19 | [8 empty] | nr/m² | nr | 19 | Oxygen Systems | T16 – Specialist
3 | 5.13.1.1.20 | [8 empty] | nr/m² | nr | 20 | Dental Compressed Air Plant | T16 – Specialist
4 | 5.13.1.1.21 | [8 empty] | nr/m² | nr | 21 | Dental Vacuum System and Amalgam Separators | T16 – Specialist
4 | 5.13.1.1.22 | [8 empty] | nr/m² | nr | 22 | Pathology Laboratory Gas Systems (PLGS) | T16 – Specialist
4 | 5.13.1.1.23 | [8 empty] | nr/m² | nr | 23 | Pathology Laboratory Compressed Air Plant | T16 – Specialist
4 | 5.13.1.1.24 | [8 empty] | nr/m² | nr | 24 | Pathology Laboratory Central Vacuum Plant | T16 – Specialist
4 | 5.13.1.2 | [6 empty] | 2 | Medical and laboratory gas supply systems Scotland
4 | 5.13.1.2.1 | [8 empty] | nr/m² | nr | 1 | Terminal Units - General Areas | T16 – Specialist
2 | 5.13.1.2.2 | [8 empty] | nr/m² | nr | 2 | Terminal Units - High Acuity Areas | T16 – Specialist
3 | 5.13.1.2.3 | [8 empty] | nr/m² | nr | 3 | Central Alarm Panels | T16 – Specialist
4 | 5.13.1.2.4 | [8 empty] | nr/m² | nr | 4 | Local Alarms - High Acuity Areas | T16 – Specialist
5 | 5.13.1.2.5 | [8 empty] | nr/m² | nr | 5 | Area Valve Service Units (AVSU) | T16 – Specialist
5 | 5.13.1.2.6 | [8 empty] | nr/m² | nr | 6 | Pressure Reducing Sets | T16 – Specialist
5 | 5.13.1.2.7 | [8 empty] | nr/m² | nr | 7 | Medical Gases Piped Distribution System and Line Valves | T16 – Specialist
5 | 5.13.1.2.8 | [8 empty] | nr/m² | nr | 8 | Automatic Cylinder Manifolds - Including Headers and Tailpipes | T16 – Specialist
5 | 5.13.1.2.9 | [8 empty] | nr/m² | nr | 9 | Manual Standby Manifolds - Including Headers and Tailpipes | T16 – Specialist
5 | 5.13.1.2.10 | [8 empty] | nr/m² | nr | 10 | Medical and Surgical Compressed Air Plant | T16 – Specialist
5 | 5.13.1.2.11 | [8 empty] | nr/m² | nr | 11 | Air Dryer and Regulator Assembly | T16 – Specialist
5 | 5.13.1.2.12 | [8 empty] | nr/m² | nr | 12 | Medical Vacuum Plant | T16 – Specialist
5 | 5.13.1.2.13 | [8 empty] | nr/m² | nr | 13 | Anaesthetic Gas Scavenging (AGS) Systems | T16 – Specialist
5 | 5.13.1.2.15 | [8 empty] | nr/m² | nr | 15 | Cylinder Stores | T16 – Specialist
5 | 5.13.1.2.18 | [8 empty] | nr/m² | nr | 18 | Emergency Supply Manifolds/Emergency Reserve Manifolds (ESM/ERM) | T16 – Specialist
5 | 5.13.1.2.19 | [8 empty] | nr/m² | nr | 19 | Oxygen Systems | T16 – Specialist
5 | 5.13.1.2.20 | [8 empty] | nr/m² | nr | 20 | Dental Compressed Air Plant | T16 – Specialist
5 | 5.13.1.2.21 | [8 empty] | nr/m² | nr | 21 | Dental Vacuum System and Amalgam Separators | T16 – Specialist
5 | 5.13.1.2.22 | [8 empty] | nr/m² | nr | 22 | Pathology Laboratory Gas Systems (PLGS) | T16 – Specialist
5 | 5.13.1.2.23 | [8 empty] | nr/m² | nr | 23 | Pathology Laboratory Compressed Air Plant | T16 – Specialist
5 | 5.13.1.2.24 | [8 empty] | nr/m² | nr | 24 | Pathology Laboratory Central Vacuum Plant | T16 – Specialist
5 | 5.13.1.3 | [6 empty] | 3 | Centralised vacuum cleaning systems | nr/m² | nr |  |  | T16 – Specialist
5 | 5.13.1.4 | [6 empty] | 4 | Swimming Pools - Water Quality and Electrical Testing | nr/m² | nr |  |  | T16 – Specialist
5 | 5.13.1.5 | [6 empty] | 5 | Swimming Pools - Filters | nr/m² | nr |  |  | T16 – Specialist
5 | 5.13.1.6 | [6 empty] | 6 | Swimming Pools - Operating Equipment and Services. | nr/m² | nr |  |  | T16 – Specialist
4 | 5.13.1.7 | [6 empty] | 7 | Swimming Pool Winterisation - Water Level Method | nr/m² | nr |  |  | T16 – Specialist
5 | 5.13.1.8 | [6 empty] | 8 | Swimming Pool Equipment and Features | nr/m² | nr |  |  | T16 – Specialist
5 | 5.13.1.9 | [6 empty] | 9 | Swimming Pool Winterisation - Filter Pump Method | nr/m² | nr |  |  | T16 – Specialist
5 | 5.13.1.10 | [6 empty] | 10 | Compressed air systems | nr/m² | nr |  |  | T16 – Specialist
5 | 5.13.1.11 | [6 empty] | 11 | Vacuum installations
5 | 5.13.1.11.1 | [8 empty] | nr/m² | nr | 1 | Vacuum Systems - Air | T16 – Specialist
5 | 5.13.1.11.2 | [8 empty] | nr/m² | nr | 2 | Vacuum Leak Detector | T16 – Specialist
5 | 5.13.1.11.3 | [8 empty] | nr/m² | nr | 3 | Vacuum Systems - Liquid | T16 – Specialist
5 | 5.13.1.12 | [6 empty] | 12 | Pipework In General
5 | 5.13.1.12.X | [8 empty] | nr/m² | m² | X | See SUP - Pipework | T16 – Specialist
5 | 5.13.1.13 | [6 empty] | 13 | Thermal insulation
5 | 5.13.1.13.1 | [8 empty] | m²/nr | m² | 1 | Thermal Insulation - Sheet | T16 – Specialist
5 | 5.13.1.13.2 | [8 empty] | m²/nr | m² | 2 | Thermal Insulation - Pipe | T16 – Specialist
5 | 5.13.1.14 | [6 empty] | 14 | Attenuators | nr | nr |  |  | T16 – Specialist
5 | 5.13.1.15 | [6 empty] | 15 | Control components
5 | 5.13.1.15.X | [8 empty] | nr | nr / System | X | See SUP - Controllers and sensors | T16 – Specialist
5 | 5.13.2 |  |  |  |  | 2 | Specialist refrigeration systems
5 | 5.13.2.1 | [6 empty] | 1 | Cold Rooms | nr/m² | nr |  |  | T16 – Specialist
5 | 5.13.2.2 | [6 empty] | 2 | Cold Room Heater Mat System | nr | nr |  |  | T16 – Specialist
5 | 5.13.2.3 | [6 empty] | 3 | Cold Rooms - GMP-Compliant | nr | nr |  |  | T16 – Specialist
5 | 5.13.2.4 | [6 empty] | 4 | Ice pads | nr | nr |  |  | T16 – Specialist
5 | 5.13.2.5 | [6 empty] | 5 | Refrigerated Display Cabinets | nr | nr |  |  | T16 – Specialist
4 | 5.13.2.6 | [6 empty] | 6 | Ice Storage Systems | nr | nr |  |  | T16 – Specialist
4 | 5.13.3 |  |  |  |  | 3 | Specialist mechanical installations
4 | 5.13.3.1 | [6 empty] | 1 | Wave machines | nr/m² | nr |  |  | T16 – Specialist
4 | 5.13.3.2 | [6 empty] | 2 | Saunas | nr | nr |  |  | T16 – Specialist
4 | 5.13.3.3 | [6 empty] | 3 | Jacuzzis | nr/m² | nr |  |  | T16 – Specialist
4 | 5.13.3.4 | [6 empty] | 4 | Specialist pools | nr | nr |  |  | T16 – Specialist
4 | 5.13.3.5 | [6 empty] | 5 | Water Purification and Demineralisation Equipment | nr | nr |  |  | T16 – Specialist
4 | 5.13.4 |  |  |  |  | 4 | Specialist electrical installations
4 | 5.13.4.1 | [6 empty] | 1 | Radio and television studio equipment | nr | nr |  |  | T16 – Specialist
5 | 5.13.4.2 | [6 empty] | 2 | Recording studio equipment | nr | nr |  |  | T16 – Specialist
5 | 5.13.4.3 | [6 empty] | 3 | Home cinemas | nr | nr |  |  | T16 – Specialist
5 | 5.13.4.4 | [6 empty] | 4 | Multi-room audio and video | nr | nr |  |  | T16 – Specialist
4 | 5.13.4.5 | [6 empty] | 5 | Automated curtains and blinds
4 | 5.13.4.5.1 | [8 empty] | nr | nr | 1 | Motorised Curtain Closer | T16 – Specialist
5 | 5.13.4.5.2 | [8 empty] | nr | nr | 2 | Motorised Blinds | T16 – Specialist
5 | 5.13.5 |  |  |  |  | 5 | Water features
4 | 5.13.5.1 | [6 empty] | 1 | Water features
4 | 5.13.5.1.1 | [8 empty] | nr | nr | 1 | Fountains Outdoor - Ornamental | T16 – Specialist
5 | 5.13.5.1.2 | [8 empty] | nr | nr | 2 | Fountains Indoor - Ornamental | T16 – Specialist
3 | 5.13.5.2 | [6 empty] | 2 | Water filtration equipment
4 | 5.13.5.2.1 | [8 empty] | nr | nr | 1 | Water Filtration and Conditioning - Active Carbon Cartridge Filter | T16 – Specialist
4 | 5.13.5.2.2 | [8 empty] | nr | nr | 2 | Duplex Water Strainers | T16 – Specialist
4 | 5.13.5.2.3 | [8 empty] | nr | nr | 3 | Magnetic Water Filter | T16 – Specialist
4 | 5.13.5.2.4 | [8 empty] | nr | nr | 4 | Basket Water Strainers | T16 – Specialist
4 | 5.13.5.2.5 | [8 empty] | nr | nr | 5 | Water Filtration and Conditioning - Bacterial Removal Filters | T16 – Specialist
4 | 5.13.5.2.6 | [8 empty] | nr | nr | 6 | Water Filtration and Conditioning - Sealed or Combined Type | T16 – Specialist
3 | 5.13.5.2.7 | [8 empty] | nr | nr | 7 | Water Filtration and Conditioning - Sediment Removal Filters | T16 – Specialist
4 | 5.13.5.2.8 | [8 empty] | nr | nr | 8 | Water Filtration and Conditioning - Magnetic Water Conditioners | T16 – Specialist
4 | 5.13.5.3 | [6 empty] | 3 | Nutrient treatment and equipment
4 | 5.13.5.3.1 | [8 empty] | nr | nr | 1 | Water Treatment - pH Correction | T16 – Specialist
4 | 5.13.5.3.2 | [8 empty] | nr | nr | 2 | Water Treatment - Activated Carbon Filtration | T16 – Specialist
4 | 5.13.5.3.3 | [8 empty] | nr | nr | 3 | Water Treatment - Turbidity Treatment | T16 – Specialist
3 | 5.13.5.4 | [6 empty] | 4 | Control components
4 | 5.13.5.4.X | [8 empty] | nr | nr / System | X | See SUP - Controllers and sensors | T16 – Specialist
4 | 5.13.6 |  |  |  |  | 6 | Workshop Equipment
4 | 5.13.6.1 | [6 empty] | 1 | Laser Cutting Machine | nr | nr |  |  | T16 – Specialist
4 | 5.13.6.2 | [6 empty] | 2 | Machine Tools - General | nr | nr |  |  | T16 – Specialist
4 | 5.13.6.3 | [6 empty] | 3 | Fixed Position Grinding Machines and Abrasive Wheels | nr | nr |  |  | T16 – Specialist
5 | 5.13.6.4 | [6 empty] | 4 | Pillar Drill | nr | nr |  |  | T16 – Specialist
5 | 5.13.6.5 | [6 empty] | 5 | Circular Bench Saw | nr | nr |  |  | T16 – Specialist
3 | 5.13.6.6 | [6 empty] | 6 | Electric Hacksaw | nr | nr |  |  | T16 – Specialist
4 | 5.13.6.7 | [6 empty] | 7 | Key Cutting Machine | nr | nr |  |  | T16 – Specialist
5 | 5.13.6.8 | [6 empty] | 8 | Mortice Cutter | nr | nr |  |  | T16 – Specialist
5 | 5.13.6.9 | [6 empty] | 9 | Radial Arm Saw | nr | nr |  |  | T16 – Specialist
4 | 5.13.6.10 | [6 empty] | 10 | Wood Thickness Planer | nr | nr |  |  | T16 – Specialist
5 | 5.13.6.11 | [6 empty] | 11 | Underfloor Wheel Lathes | nr | nr |  |  | T16 – Specialist
5 | 5.13.6.12 | [6 empty] | 12 | Hand Held Grinding Machines and Abrasive Wheels | nr | nr |  |  | T16 – Specialist
5 | 5.13.6.13 | [6 empty] | 13 | Industrial Sewing Machines | nr | nr |  |  | T16 – Specialist
5 | 5.13.6.14 | [6 empty] | 14 | Wash Station - 3D Print Cleaning | nr | nr |  |  | T16 – Specialist
5 | 5.13.6.15 | [6 empty] | 15 | Weighing Equipment - Industrial Scales | nr | nr |  |  | T16 – Specialist
5 | 5.13.6.16 | [6 empty] | 16 | Ultrasonic Cleaning Bath | nr | nr |  |  | T16 – Specialist
5 | 5.13.6.17 | [6 empty] | 17 | Metal Inert Gas (MIG) Welder | nr | nr |  |  | T16 – Specialist
5 | 5.13.6.18 | [6 empty] | 18 | Tungsten Inert Gas (TIG) Welder | nr | nr |  |  | T16 – Specialist
4 | 5.13.6.19 | [6 empty] | 19 | Compressors
5 | 5.13.6.19.X | [8 empty] | nr | nr | X | See SUP - Compressors | T16 – Specialist
5 | 5.13.6.20 | [6 empty] | 20 | Kiln - Electric | nr | nr |  |  | T16 – Specialist
5 | 5.13.7 |  |  |  |  | 7 | Laboratory Equipment
4 | 5.13.7.1 | [6 empty] | 1 | Air Showers | nr | nr |  |  | T16 – Specialist
5 | 5.13.7.2 | [6 empty] | 2 | Drying and Heating Laboratory Oven | nr | nr |  |  | T16 – Specialist
3 | 5.13.7.3 | [6 empty] | 3 | Laboratory Glassware Washer | nr | nr |  |  | T16 – Specialist
4 | 5.13.7.4 | [6 empty] | 4 | Laboratory Rack Washer | nr | nr |  |  | T16 – Specialist
4 | 5.13.7.5 | [6 empty] | 5 | Laboratory Gas Systems (LGS) | nr | nr |  |  | T16 – Specialist
4 | 5.13.8 |  |  |  |  | 8 | Emergency Shower and Eye Wash Station
4 | 5.13.8.1 | [6 empty] | 1 | Shower and Eye Wash Station - Tank fed with Immersion | nr | nr |  |  | T12 – Safety Systems
4 | 5.13.8.2 | [6 empty] | 2 | Shower and Eye Wash Station - Mains fed with TMV | nr | nr |  |  | T12 – Safety Systems
4 | 5.14 |  |  | 14 | Builders' work in connection with services
4 | 5.14.1 |  |  |  |  | 1 | Builders' work in connection with services
4 | 5.14.1.1 | [6 empty] | 1 | Fuel bunds | nr | nr |  |  | T12 – Safety Systems
4 | 6 | 6 | Complete buildings and building units
4 | 6.1 |  |  | 1 | Complete buildings
4 | 6.1.1 |  |  |  |  | 1 | Complete buildings |  |  | N/A | N/A
4 | 6.1.2 |  |  |  |  | 2 | Building units |  |  | N/A | N/A
4 | 7 | 7 | Works to existing buildings
4 | 7.1 |  |  | 1 | Minor demolition works and alteration works
4 | 7.1.1 |  |  |  |  | 1 | Minor demolition and alteration works |  |  | N/A | N/A
4 | 7.2 |  |  | 2 | Repairs to existing services
4 | 7.2.1 |  |  |  |  | 1 | Existing services |  |  | N/A | N/A
4 | 7.3 |  |  | 3 | Damp proof courses/fungus and beetle eradication
4 | 7.3.1 |  |  |  |  | 1 | Damp proof courses
5 | 7.3.2 |  |  |  |  | 2 | Beetle eradication |  |  | N/A | N/A
4 | 7.4 |  |  | 4 | Facade retention
3 | 7.4.1 |  |  |  |  | 1 | Facade retention |  |  | N/A | N/A
4 | 7.5 |  |  | 5 | Cleaning existing surfaces |  |  |  |  | N/A
4 | 7.5.1 |  |  |  |  | 1 | Cleaning existing surfaces |  |  | N/A | N/A
4 | 7.5.2 |  |  |  |  | 2 | Protective coatings to existing surfaces |  |  | N/A | N/A
4 | 7.6 |  |  | 6 | Renovation works |  |  |  |  | N/A
4 | 7.6.1 |  |  |  |  | 1 | Masonry repairs |  |  | N/A | N/A
3 | 7.6.2 |  |  |  |  | 2 | Concrete repairs |  |  | N/A | N/A
4 | 7.6.3 |  |  |  |  | 3 | Metal repairs |  |  | N/A | N/A
4 | 7.6.4 |  |  |  |  | 4 | Timber repairs |  |  | N/A | N/A
2 | 7.6.5 |  |  |  |  | 5 | Plastics repairs |  |  | N/A | N/A
3 | 8 | 8 | External works
4 | 8.1 |  |  | 1 | Site clearance
1 | 8.1.1 |  |  |  |  | 1 | Site clearance
2 | 8.1.2 |  |  |  |  | 2 | Preparatory groundworks |  |  | N/A | N/A
3 | 8.2 |  |  | 2 | Roads¦ Paths and paving
3 | 8.2.1 |  |  |  |  | 1 | Roads¦ Paths and paving
1 | 8.2.1.1 | [6 empty] | 1 | Roads
2 | 8.2.1.1.1 | [8 empty] | m² | m² | 1 | In-situ concrete to roads and paths inc formwork | T14 – External Works
3 | 8.2.1.1.2 | [8 empty] | m² | m² | 2 | Coated macadam and asphalt, sub layers and edgings | T14 – External Works
2 | 8.2.1.1.3 | [8 empty] | m² | m² | 3 | Interlocking bricks and blocks | T14 – External Works
3 | 8.2.1.1.4 | [8 empty] | m² | m² | 4 | Sett and cobbled pavings | T14 – External Works
2 | 8.2.1.1.5 | [8 empty] | m² | m² | 5 | Gravel surfaces inc treatment and membranes | T14 – External Works
3 | 8.2.1.1.6 | [8 empty] | m² | m² | 6 | Uncoated stone chipping surfacing inc binder | T14 – External Works
3 | 8.2.1.1.7 | [8 empty] | m² | m² | 7 | Hoggin and woodchip surfacings inc treatment | T14 – External Works
2 | 8.2.1.1.8 | [8 empty] | m² | m² | 8 | Perforated unit to protect grassed areas | T14 – External Works
3 | 8.2.1.2 | [6 empty] | 2 | Kerbs, channels and haunchings etc | m | m |  |  | T14 – External Works
2 | 8.2.1.3 | [6 empty] | 3 | Traffic calming items | nr | nr |  |  | T14 – External Works
3 | 8.2.1.4 | [6 empty] | 4 | Paths |  |  |  |  | T14 – External Works
3 | 8.2.1.4.1 | [8 empty] | m | m² | 1 | Pavings slabs to paths inc sub layers | T14 – External Works
2 | 8.2.1.4.2 | [8 empty] | m | m² | 2 | External Ground Surfaces - Block and Brick Paving | T14 – External Works
3 | 8.2.1.4.3 | [8 empty] | m | m² | 3 | External Ground Surfaces - Flagstones | T14 – External Works
3 | 8.2.1.5 | [6 empty] | 5 | Frangible smoke outlet paving to basements | nr | nr |  |  | T14 – External Works
3 | 8.2.1.6 | [6 empty] | 6 | Road crossings | nr | nr |  |  | T14 – External Works
3 | 8.2.1.7 | [6 empty] | 7 | Steps | m | nr |  |  | T14 – External Works
3 | 8.2.1.8 | [6 empty] | 8 | Ramps | nr/m | nr |  |  | T14 – External Works
1 | 8.2.1.9 | [6 empty] | 9 | Tree grilles | nr | nr |  |  | T14 – External Works
2 | 8.2.1.10 | [6 empty] | 10 | Vehicle protection barriers | m | m |  |  | T14 – External Works
3 | 8.2.1.11 | [6 empty] | 11 | Bumpers | m | m |  |  | T14 – External Works
3 | 8.2.1.12 | [6 empty] | 12 | Pavement markings | nr/m | m |  |  | T14 – External Works
2 | 8.2.2 |  |  |  |  | 2 | Special surfaces and paving
3 | 8.2.2.1 | [6 empty] | 1 | Surfacings and paving for sports amenities |  |  |  |  | T14 – External Works
4 | 8.2.2.1.1 | [8 empty] | m² | m² | 1 | Sheet and liquid applied surfacings | T14 – External Works
5 | 8.2.2.1.2 | [8 empty] | m² | m² | 2 | Synthetic tufted surfacings for ski slopes | T14 – External Works
5 | 8.2.2.1.3 | [8 empty] | m² | m² | 3 | Proprietary coloured no fines concrete and shale surfacings | T14 – External Works
5 | 8.2.2.2 | [6 empty] | 2 | Markings to surfacings and paving | m² | m |  |  | T14 – External Works
5 | 8.3 |  |  | 3 | Soft landscaping¦ Planting and irrigation systems
5 | 8.3.1 |  |  |  |  | 1 | Seeding and turfing
5 | 8.3.1.1 | [6 empty] | 1 | Grassed areas | m² | m² |  |  | T14 – External Works
5 | 8.3.1.2 | [6 empty] | 2 | Reinforced grass proprietary systems | m² | m² |  |  | T14 – External Works
5 | 8.3.2 |  |  |  |  | 2 | External planting
4 | 8.3.2.1 | [6 empty] | 1 | Planting | m² | m² |  |  | T14 – External Works
4 | 8.3.2.2 | [6 empty] | 2 | Planting reed beds | m² | m² |  |  | T14 – External Works
4 | 8.3.2.3 | [6 empty] | 3 | Hedges | m | m |  |  | T14 – External Works
5 | 8.3.2.4 | [6 empty] | 4 | Trees | nr | nr |  |  | T14 – External Works
5 | 8.3.2.5 | [6 empty] | 5 | Woodland planting | m² | m² |  |  | T14 – External Works
5 | 8.3.3 |  |  |  |  | 3 | Irrigation systems
4 | 8.3.3.1 | [6 empty] | 1 | Pipework In General
4 | 8.3.3.1.X | [8 empty] | m | m² | X | See SUP - Pipework | T14 – External Works
4 | 8.3.3.2 | [6 empty] | 2 | Soil Moisture Watering System | nr/m² | m² |  |  | T14 – External Works
4 | 8.3.3.3 | [6 empty] | 3 | Electrical Trace Heating | nr | nr |  |  | T14 – External Works
4 | 8.3.3.4 | [6 empty] | 4 | Thermal Insulation |  |  |  |  | T14 – External Works
4 | 8.3.3.4.1 | [8 empty] | m²/nr | m² | 1 | Thermal Insulation - Sheet | T14 – External Works
4 | 8.3.3.4.2 | [8 empty] | m²/nr | m² | 2 | Thermal Insulation - Pipe | T14 – External Works
4 | 8.3.3.5 | [6 empty] | 5 | Cold Water Storage Tanks | nr | nr |  |  | T14 – External Works
3 | 8.3.3.6 | [6 empty] | 6 | Chemical storage vessels | m² | nr |  |  | T14 – External Works
4 | 8.3.3.7 | [6 empty] | 7 | Nutrient treatment and equipment
5 | 8.3.3.7.1 | [8 empty] | nr | nr | 1 | Chemical Dosing Pots - Manual Operation | T14 – External Works
5 | 8.3.3.7.2 | [8 empty] | nr | nr | 2 | Chemical Dosing Pots - Automatic Operation | T14 – External Works
5 | 8.3.3.7.3 | [8 empty] | nr | nr | 3 | Chemical Dosing - Probes | T14 – External Works
4 | 8.3.3.7.4 | [8 empty] | nr | nr | 4 | Chemical Dosing - Chemical Feed Units | T14 – External Works
2 | 8.3.3.7.5 | [8 empty] | nr | nr | 5 | Chemical Dosing - Automatic Units | T14 – External Works
3 | 8.3.3.8 | [6 empty] | 8 | Outlet pipes and nozzles | m² | nr |  |  | T14 – External Works
4 | 8.4 |  |  | 4 | Fencing, railing and walls
4 | 8.4.1 |  |  |  |  | 1 | Fencing and railings
3 | 8.4.1.1 | [6 empty] | 1 | Fencing
4 | 8.4.1.1.1 | [8 empty] | m | m | 1 | Fences - Anti-Scaling - Prison Mesh with Concrete Posts | T14 – External Works
4 | 8.4.1.1.2 | [8 empty] | m | m | 2 | Fences - Chain Link and Concrete Post | T14 – External Works
4 | 8.4.1.1.3 | [8 empty] | m | m | 3 | Fences - Concrete Post and Panel | T14 – External Works
4 | 8.4.1.1.4 | [8 empty] | m | m | 4 | Fences - Concrete Post and Rail | T14 – External Works
4 | 8.4.1.1.5 | [8 empty] | m | m | 5 | Fences - Concrete Post and Wire | T14 – External Works
3 | 8.4.1.1.6 | [8 empty] | m | m | 6 | Fences - Galvanized Weldmesh | T14 – External Works
4 | 8.4.1.1.7 | [8 empty] | m | m | 7 | Fences - Palisade - Galvanized Metal | T14 – External Works
4 | 8.4.1.1.8 | [8 empty] | m | m | 8 | Fences - Timber | T14 – External Works
4 | 8.4.1.2 | [6 empty] | 2 | Railings | m |  |  |  | T14 – External Works
4 | 8.4.1.2.1 | [8 empty] | m | m | 1 | Railings - Metal | T14 – External Works
5 | 8.4.1.3 | [6 empty] | 3 | Gates |  |  |  |  | T14 – External Works
5 | 8.4.1.3.1 | [8 empty] | nr | nr | 1 | Gates - Collapsible | T14 – External Works
4 | 8.4.1.3.2 | [8 empty] | nr | nr | 2 | Sliding Gates - Powered | T14 – External Works
4 | 8.4.1.3.3 | [8 empty] | nr | nr | 3 | Swing Gates - Powered | T14 – External Works
4 | 8.4.2 |  |  |  |  | 2 | Walls and screens
5 | 8.4.2.1 | [6 empty] | 1 | Walls | m | m |  |  | T14 – External Works
5 | 8.4.2.2 | [6 empty] | 2 | Screens | m | m |  |  | T14 – External Works
5 | 8.4.2.3 | [6 empty] | 3 | Gates |  |  |  |  | T14 – External Works
5 | 8.4.2.3.1 | [8 empty] | nr | nr | 1 | Sliding Gates - Powered | T14 – External Works
5 | 8.4.2.3.2 | [8 empty] | nr | nr | 2 | Swing Gates - Powered | T14 – External Works
4 | 8.4.3 |  |  |  |  | 3 | Retaining walls
2 | 8.4.3.1 | [6 empty] | 1 | Retaining walls | m | m |  |  | T14 – External Works
3 | 8.4.3.2 | [6 empty] | 2 | Copings and the like | m | m |  |  | T14 – External Works
4 | 8.4.4 |  |  |  |  | 4 | Barriers and guardrails
5 | 8.4.4.1 | [6 empty] | 1 | Vehicle restraint systems | nr | nr |  |  | T14 – External Works
5 | 8.4.4.2 | [6 empty] | 2 | Bollards - Concrete | nr | nr |  |  | T14 – External Works
5 | 8.4.4.3 | [6 empty] | 3 | Safety Barriers - Fixed Position | m | m |  |  | T14 – External Works
5 | 8.4.4.4 | [6 empty] | 4 | Vehicle and pedestrian control barriers and gates
5 | 8.4.4.4.1 | [8 empty] | nr | nr | 1 | Automatic Vehicle Barrier | T14 – External Works
5 | 8.4.4.4.2 | [8 empty] | nr | nr | 2 | Automatic Rising Bollards | T14 – External Works
5 | 8.4.4.4.3 | [8 empty] | nr | nr | 3 | Manual Vehicle Barrier | T14 – External Works
5 | 8.4.4.4.4 | [8 empty] | nr | nr | 4 | Safety Barriers - Moveable Barriers | T14 – External Works
4 | 8.4.4.4.5 | [8 empty] | nr | nr | 5 | Safety Barriers - With Glass Insert | T14 – External Works
5 | 8.4.4.4.6 | [8 empty] | m | m | 6 | Safety Hand Rails | T14 – External Works
4 | 8.5 |  |  | 5 | External fixtures
5 | 8.5.1 |  |  |  |  | 1 | Site/street furniture and equipment
5 | 8.5.1.1 | [6 empty] | 1 | Turnstiles
5 | 8.5.1.1.1 | [8 empty] | nr | nr | 1 | Tripod Turnstile - Powered | T14 – External Works
5 | 8.5.1.1.2 | [8 empty] | nr | nr | 2 | Full Height Turnstile - Powered | T14 – External Works
3 | 8.5.1.2 | [6 empty] | 2 | Bollards, including removable and collapsable
4 | 8.5.1.2.1 | [8 empty] | nr | nr | 1 | Automatic Rising Bollards | T14 – External Works
4 | 8.5.1.2.2 | [8 empty] | nr | nr | 2 | Bollards - Concrete | T14 – External Works
4 | 8.5.1.2.3 | [8 empty] | nr | nr | 3 | Bollards - Concrete with chains | T14 – External Works
5 | 8.5.1.2.4 | [8 empty] | nr | nr | 4 | Bollards - Illuminated | T14 – External Works
5 | 8.5.1.3 | [6 empty] | 3 | Seats, benches and tables | nr | nr |  |  | T14 – External Works
5 | 8.5.1.4 | [6 empty] | 4 | Litter bins, grit bins and dustbins | nr | nr |  |  | T14 – External Works
3 | 8.5.1.5 | [6 empty] | 5 | Poster display units and notice boards
4 | 8.5.1.5.1 | [8 empty] | nr | nr | 1 | Advertising Signage - Non Illuminated | T14 – External Works
4 | 8.5.1.5.2 | [8 empty] | nr | nr | 2 | Advertising Signage - Illuminated | T14 – External Works
3 | 8.5.1.6 | [6 empty] | 6 | Cycle stands | nr |  |  |  | T14 – External Works
4 | 8.5.1.6.1 | [8 empty] | nr | nr | 1 | Cycle Shelters | T14 – External Works
4 | 8.5.1.6.2 | [8 empty] | nr | nr | 2 | Ground-Mounted Cycle Stands | T14 – External Works
4 | 8.5.1.7 | [6 empty] | 7 | Directional signs inc reflective traffic signs | nr | nr |  |  | T14 – External Works
4 | 8.5.1.8 | [6 empty] | 8 | Flagpoles
5 | 8.5.1.8.1 | [8 empty] | nr | nr | 1 | Flagpole - Base-Hinged | T14 – External Works
5 | 8.5.1.8.2 | [8 empty] | nr | nr | 2 | Flagpole - Fixed | T14 – External Works
5 | 8.5.1.9 | [6 empty] | 9 | Outdoor Play Equipment | nr | nr |  |  | T14 – External Works
5 | 8.5.1.10 | [6 empty] | 10 | Sports and Play Equipment | nr | nr |  |  | T14 – External Works
5 | 8.5.1.11 | [6 empty] | 11 | Minor footbridges | nr | nr |  |  | T14 – External Works
5 | 8.5.1.12 | [6 empty] | 12 | Clothes drying fittings | nr | nr |  |  | T14 – External Works
5 | 8.5.1.13 | [6 empty] | 13 | Bus stops, shelters and phone boxes (non statutory owner) | nr | nr |  |  | T14 – External Works
2 | 8.5.1.14 | [6 empty] | 14 | Sculptures | nr | nr |  |  | T14 – External Works
3 | 8.5.1.15 | [6 empty] | 15 | Site/street furniture and equipment | nr | nr |  |  | T14 – External Works
4 | 8.5.2 |  |  |  |  | 2 | Ornamental features
5 | 8.5.2.1 | [6 empty] | 1 | Ornamental features |  |  |  |  | T14 – External Works
5 | 8.5.2.1.1 | [8 empty] | nr | nr | 1 | Water features | T14 – External Works
4 | 8.6 |  |  | 6 | External drainage
5 | 8.6.1 |  |  |  |  | 1 | Surface water and foul water drainage
5 | 8.6.1.1 | [6 empty] | 1 | Drainage runs below ground | Item | m |  |  | T7 – Sanitary and Plumbing Services
5 | 8.6.1.2 | [6 empty] | 2 | Gullies and gratings inc road types
5 | 8.6.1.2.1 | [8 empty] | m | m | 1 | Rainwater Drainage - Road Gutters and Road Gullies | T7 – Sanitary and Plumbing Services
4 | 8.6.1.2.2 | [8 empty] | m | m | 2 | Rainwater Drainage - Slot Drains | T7 – Sanitary and Plumbing Services
4 | 8.6.1.3 | [6 empty] | 3 | Rodding and access points | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 8.6.1.4 | [6 empty] | 4 | Packaged pumping stations
5 | 8.6.1.4.1 | [8 empty] | nr | nr | 1 | Interceptor traps | T7 – Sanitary and Plumbing Services
5 | 8.6.1.4.2 | [8 empty] | nr | nr | 2 | Inspection chambers | T7 – Sanitary and Plumbing Services
4 | 8.6.1.4.3 | [8 empty] | nr | nr | 3 | Soakaways | T7 – Sanitary and Plumbing Services
5 | 8.6.1.4.4 | [8 empty] | nr | nr | 4 | Retention/storage tanks and vessels | T7 – Sanitary and Plumbing Services
5 | 8.6.1.4.5 | [8 empty] | nr | nr | 5 | Cesspools and septic tanks | T7 – Sanitary and Plumbing Services
4 | 8.6.1.4.6 | [8 empty] | nr | nr | 6 | Petrol interceptor units | T7 – Sanitary and Plumbing Services
4 | 8.6.1.5 | [6 empty] | 5 | Surface Water Balancing Ponds
5 | 8.6.1.5.1 | [8 empty] | m² | m² | 1 | Surface Water Balancing Ponds - Concrete | T7 – Sanitary and Plumbing Services
5 | 8.6.1.5.2 | [8 empty] | m² | m² | 2 | Surface Water Balancing Ponds - Grass | T7 – Sanitary and Plumbing Services
4 | 8.6.1.5.3 | [8 empty] | m² | m² | 3 | Surface Water Balancing - Ditches | T7 – Sanitary and Plumbing Services
4 | 8.6.2 |  |  |  |  | 2 | Ancillary drainage systems
4 | 8.6.2.1 | [6 empty] | 1 | Pumping stations | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 8.6.2.2 | [6 empty] | 2 | Control components located externally
4 | 8.6.2.2.X | [8 empty] | nr | nr | X | See SUP - Controllers and sensors | T7 – Sanitary and Plumbing Services
4 | 8.6.2.3 | [6 empty] | 3 | Monitoring equipment located externally | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 8.6.2.4 | [6 empty] | 4 | Ejector stations | nr | nr |  |  | T7 – Sanitary and Plumbing Services
3 | 8.6.2.5 | [6 empty] | 5 | Storage/retention tanks and vessels | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 8.6.2.6 | [6 empty] | 6 | Sewerage treatment systems
5 | 8.6.2.6.1 | [8 empty] | nr | nr | 1 | Package Systems | T7 – Sanitary and Plumbing Services
2 | 8.6.2.6.2 | [8 empty] | nr | nr | 2 | Extended Aeration and Oxidation Ditch Systems | T7 – Sanitary and Plumbing Services
3 | 8.6.2.6.3 | [8 empty] | nr | nr | 3 | Rotating Biological Contactors and Percolating Filters | T7 – Sanitary and Plumbing Services
4 | 8.6.2.6.4 | [8 empty] | nr | nr | 4 | Sequencing Batch Reactors | T7 – Sanitary and Plumbing Services
4 | 8.6.2.6.5 | [8 empty] | m² | m² | 5 | Constructed Wetlands | T7 – Sanitary and Plumbing Services
5 | 8.6.2.6.6 | [8 empty] | nr | nr | 6 | Separator Systems | T7 – Sanitary and Plumbing Services
5 | 8.6.2.7 | [6 empty] | 7 | Enzyme systems | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 8.6.2.8 | [6 empty] | 8 | Drainage Fields | m² | m² |  |  | T7 – Sanitary and Plumbing Services
4 | 8.6.3 |  |  |  |  | 3 | External laboratory and industrial liquid waste drainage
5 | 8.6.3.1 | [6 empty] | 1 | Drainage runs below ground | m² | m² |  |  | T16 – Specialist
5 | 8.6.3.2 | [6 empty] | 2 | Drainage runs above ground | m | m |  |  | T16 – Specialist
5 | 8.6.3.3 | [6 empty] | 3 | Storage tanks and vessels | nr | nr |  |  | T16 – Specialist
5 | 8.6.3.4 | [6 empty] | 4 | Effluent treatment plant
5 | 8.6.3.4.1 | [8 empty] | nr | nr | 1 | Package Systems | T16 – Specialist
5 | 8.6.3.4.2 | [8 empty] | nr | nr | 2 | Extended Aeration and Oxidation Ditch Systems | T16 – Specialist
4 | 8.6.3.4.3 | [8 empty] | m² | m² | 3 | Drainage Fields | T16 – Specialist
5 | 8.6.3.4.4 | [8 empty] | nr | nr | 4 | Settlement Tanks | T16 – Specialist
5 | 8.6.3.4.5 | [8 empty] | nr | nr | 5 | Separator Systems | T16 – Specialist
5 | 8.6.3.4.6 | [8 empty] | nr | nr | 6 | Rotating Biological Contactors and Percolating Filters | T16 – Specialist
3 | 8.6.3.4.7 | [8 empty] | nr | nr | 7 | Sequencing Batch Reactors | T16 – Specialist
4 | 8.6.3.4.8 | [8 empty] | m² | m² | 8 | Constructed Wetlands | T16 – Specialist
4 | 8.6.3.5 | [6 empty] | 5 | Dosing equipment
5 | 8.6.3.5.1 | [8 empty] | nr | nr | 1 | Chemical Dosing Pots - Manual Operation | T16 – Specialist
4 | 8.6.3.5.2 | [8 empty] | nr | nr | 2 | Chlorine Dioxide Low Dosing Domestic Water Systems | T16 – Specialist
4 | 8.6.3.5.3 | [8 empty] | nr | nr | 3 | Chemical Dosing Pots - Automatic Operation | T16 – Specialist
4 | 8.6.3.5.4 | [8 empty] | nr | nr | 4 | Chemical Dosing - Probes | T16 – Specialist
4 | 8.6.3.5.5 | [8 empty] | nr | nr | 5 | Chemical Dosing - Chemical Feed Units | T16 – Specialist
5 | 8.6.3.5.6 | [8 empty] | nr | nr | 6 | Chemical Dosing - Automatic Units | T16 – Specialist
5 | 8.6.3.5.7 | [8 empty] | nr | nr | 7 | Bacterial and Enzyme Drain Dosing Systems | T16 – Specialist
5 | 8.6.3.6 | [6 empty] | 6 | Sterilisation equipment | nr | nr |  |  | T16 – Specialist
5 | 8.6.4 |  |  |  |  | 4 | Land drainage
5 | 8.6.4.1 | [6 empty] | 1 | Soakaways | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 8.6.4.2 | [6 empty] | 2 | Storage tanks and vessels | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 8.6.4.3 | [6 empty] | 3 | Drainage blankets | m² | m² |  |  | T7 – Sanitary and Plumbing Services
4 | 8.7 |  |  | 7 | External services
3 | 8.7.1 |  |  |  |  | 1 | Water mains supply
4 | 8.7.1.1 | [6 empty] | 1 | Fire hydrants | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 8.7.1.2 | [6 empty] | 2 | Electrical Trace Heating | nr | nr |  |  | T7 – Sanitary and Plumbing Services
4 | 8.7.1.3 | [6 empty] | 3 | Thermal insulation
4 | 8.7.1.3.1 | [8 empty] | m² | m² | 1 | Thermal Insulation - Sheet | T7 – Sanitary and Plumbing Services
5 | 8.7.1.3.2 | [8 empty] | m² | m² | 2 | Thermal Insulation - Pipe | T7 – Sanitary and Plumbing Services
5 | 8.7.1.4 | [6 empty] | 4 | Mains supply and distribution
5 | 8.7.1.4.1 | [8 empty] | m | m | 1 | Copper | T7 – Sanitary and Plumbing Services
5 | 8.7.1.4.2 | [8 empty] | m | m | 2 | Steel galvanised (closed) | T7 – Sanitary and Plumbing Services
5 | 8.7.1.4.3 | [8 empty] | m | m | 3 | Plastic | T7 – Sanitary and Plumbing Services
5 | 8.7.1.5 | [6 empty] | 5 | Rainwater harvesting systems | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 8.7.1.6 | [6 empty] | 6 | Grey water systems | nr | nr |  |  | T7 – Sanitary and Plumbing Services
5 | 8.7.2 |  |  |  |  | 2 | Electricity mains supply
4 | 8.7.2.1 | [6 empty] | 1 | Transformer substations | nr | nr |  |  | T9 – Electrical Services
5 | 8.7.2.2 | [6 empty] | 2 | Standby Generator
5 | 8.7.2.2.1 | [8 empty] | nr | nr | 1 | Power Generation - Standby Generator | T9 – Electrical Services
5 | 8.7.2.2.2 | [8 empty] | nr | nr | 2 | Power Generation - Standby Generator with Life Safety System Duties | T9 – Electrical Services
5 | 8.7.3 |  |  |  |  | 3 | External mains transformation devices
5 | 8.7.3.1 | [6 empty] | 1 | Wind turbines | nr | nr |  |  | T9 – Electrical Services
5 | 8.7.3.2 | [6 empty] | 2 | Photovoltaic devices
5 | 8.7.3.2.1 | [8 empty] | nr | nr | 1 | Solar Panels - Photovoltaic (PV) - Energy Storage | T9 – Electrical Services
4 | 8.7.3.2.2 | [8 empty] | nr | nr | 2 | Photovoltaic (PV) System - Grid Connected | T9 – Electrical Services
3 | 8.7.3.2.3 | [8 empty] | nr | nr | 3 | Large solar systems - Photovoltaic (PV) - Grid Connected | T9 – Electrical Services
4 | 8.7.4 |  |  |  |  | 4 | Electricity distribution to external plant and equipment |  |  | nr | N/A |  |  | T9 – Electrical Services
4 | 8.7.5 |  |  |  |  | 5 | Gas mains supply
4 | 8.7.5.1 | [6 empty] | 1 | Mains gas supply to external plant inc pipes and fittings | m | m |  |  | T10 – Fuel Installations
2 | 8.7.5.2 | [6 empty] | 2 | Governing stations | nr | nr |  |  | T10 – Fuel Installations
3 | 8.7.5.3 | [6 empty] | 3 | Storage Tanks - Liquefied Petroleum Gas (LPG) | nr | nr |  |  | T10 – Fuel Installations
4 | 8.7.6 |  |  |  |  | 6 | Telecommunications and other communication system connections |  |  | nr | N/A |  |  | T16 – Specialist
4 | 8.7.7 |  |  |  |  | 7 | External fuel storage and piped distribution systems
4 | 8.7.7.1 | [6 empty] | 1 | Oil Storage Tanks
5 | 8.7.7.1.1 | [8 empty] | nr | nr | 1 | Oil Storage Tanks - Above Ground | T10 – Fuel Installations
5 | 8.7.7.1.2 | [8 empty] | nr | nr | 2 | Oil Storage Tanks - Underground | T10 – Fuel Installations
4 | 8.7.7.2 | [6 empty] | 2 | Distribution pipelines
4 | 8.7.7.2.1 | [8 empty] | Item | m | 1 | Pipework for Low Pressure Natural Gas, Liquefied Petroleum Gas (LPG) or Oil | T10 – Fuel Installations
4 | 8.7.7.2.2 | [8 empty] | Item | m | 2 | Fuel Oil Distribution and Pipework using Medium (220/960 Sec) Oil | T10 – Fuel Installations
3 | 8.7.7.3 | [6 empty] | 3 | Thermal insulation
4 | 8.7.7.3.1 | [8 empty] | m²/nr | m² | 1 | Thermal Insulation - Sheet | T10 – Fuel Installations
4 | 8.7.7.3.2 | [8 empty] | m²/nr | m² | 2 | Thermal Insulation - Pipe | T10 – Fuel Installations
5 | 8.7.7.4 | [6 empty] | 4 | Meters
5 | 8.7.7.4.1 | [8 empty] | nr | nr | 1 | Flow Meter | T10 – Fuel Installations
3 | 8.7.7.4.2 | [8 empty] | nr | nr | 2 | Heat Meter | T10 – Fuel Installations
4 | 8.7.8 |  |  |  |  | 8 | External security systems
4 | 8.7.8.1 | [6 empty] | 1 | Surveillance equipment
5 | 8.7.8.1.1 | [8 empty] | nr | nr | 1 | Video Surveillance System (VSS) | T13 – Communication, Security and Controls
5 | 8.7.8.2 | [6 empty] | 2 | Security detection equipment
5 | 8.7.8.2.1 | [8 empty] | nr | nr | 1 | Fence Topping Systems | T13 – Communication, Security and Controls
3 | 8.7.8.2.2 | [8 empty] | nr | nr | 2 | Fence-Mounted Sensing Cable | T13 – Communication, Security and Controls
3 | 8.7.8.2.3 | [8 empty] | nr | nr | 3 | Fibre Optic Security Mesh | T13 – Communication, Security and Controls
4 | 8.7.8.2.4 | [8 empty] | nr | nr | 4 | Fibre Optic Wall Sensors | T13 – Communication, Security and Controls
4 | 8.7.8.2.5 | [8 empty] | nr | nr | 5 | Microwave Motion Sensors | T13 – Communication, Security and Controls
4 | 8.7.8.2.6 | [8 empty] | nr | nr | 6 | Mobile Phone Detection | T13 – Communication, Security and Controls
3 | 8.7.8.2.7 | [8 empty] | nr | nr | 7 | Perimeter Monitoring Systems | T13 – Communication, Security and Controls
3 | 8.7.8.2.8 | [8 empty] | nr | nr | 8 | Security Patrol Tracking | T13 – Communication, Security and Controls
4 | 8.7.8.3 | [6 empty] | 3 | Security alarm equipment
5 | 8.7.8.3.1 | [8 empty] | nr | nr | 1 | Active Infrared Alarms | T13 – Communication, Security and Controls
5 | 8.7.8.3.2 | [8 empty] | nr | nr | 2 | Laser Alarm Systems | T13 – Communication, Security and Controls
4 | 8.7.8.3.3 | [8 empty] | nr | nr | 3 | Passive Infrared Alarms | T13 – Communication, Security and Controls
5 | 8.7.8.4 | [6 empty] | 4 | Gate access control systems | nr | nr |  |  | T13 – Communication, Security and Controls
5 | 8.7.8.5 | [6 empty] | 5 | Gate entry systems | nr | nr |  |  | T13 – Communication, Security and Controls
4 | 8.7.8.6 | [6 empty] | 6 | Security lights and lighting systems
5 | 8.7.8.6.1 | [8 empty] | nr | nr | 1 | Outdoor Lighting (Security) | T13 – Communication, Security and Controls
5 | 8.7.8.6.2 | [8 empty] | nr | nr | 2 | Searchlights and Floodlights | T13 – Communication, Security and Controls
4 | 8.7.9 |  |  |  |  | 9 | Site/street lighting systems
5 | 8.7.9.1 | [6 empty] | 1 | External lighting | nr | nr |  |  | T9 – Electrical Services
5 | 8.7.9.2 | [6 empty] | 2 | Luminaries/lamps
3 | 8.7.9.2.1 | [8 empty] | nr | nr | 1 | Lamps - Tungsten Filament | T9 – Electrical Services
4 | 8.7.9.2.2 | [8 empty] | nr | nr | 2 | Lamps - LED | T9 – Electrical Services
5 | 8.7.9.2.3 | [8 empty] | nr | nr | 3 | Lamps - Fluorescent | T9 – Electrical Services
4 | 8.7.9.2.4 | [8 empty] | nr | nr | 4 | Lamps - Discharge | T9 – Electrical Services
5 | 8.7.9.3 | [6 empty] | 3 | Lighting control points | nr | nr |  |  | T9 – Electrical Services
5 | 8.7.9.4 | [6 empty] | 4 | Illuminated traffic signs | nr | nr |  |  | T9 – Electrical Services
5 | 8.7.9.5 | [6 empty] | 5 | Traffic Light Systems | nr | nr |  |  | T9 – Electrical Services
5 | 8.7.10 |  |  |  |  | 10 | Local/district heating installations |  |  | T/E | T/E
5 | 8.7.11 |  |  |  |  | 11 | Builders work in connection with external services |  |  | nr/m | N/A
5 | 8.8 |  |  | 8 | Minor building works and ancillary buildings
5 | 8.8.1 |  |  |  |  | 1 | Minor building works |  |  | Excluded | Excluded
5 | 8.8.2 |  |  |  |  | 2 | Ancillary buildings and structures
4 | 8.8.2.1 | [6 empty] | 1 | Minor ancillary buildings
5 | 8.8.2.1.1 | [8 empty] | nr | nr | 1 | Substation buildings where not supplied by statutory undertaker | T1 - Building Structure
5 | 8.8.2.1.2 | [8 empty] | nr | nr | 2 | Fuel storage buildings | T1 - Building Structure
5 | 8.8.2.1.3 | [8 empty] | nr | nr | 3 | Specialist structures | T1 - Building Structure
4 | 8.8.2.1.4 | [8 empty] | nr | nr | 4 | Bicycle stores | T1 - Building Structure
5 | 8.8.2.1.5 | [8 empty] | nr | nr | 5 | Prefabricated/Timber Workshops, Sheds, Stores and the like | T1 - Building Structure
5 | 8.8.2.1.6 | [8 empty] | nr | nr | 6 | Guard huts and the like | T1 - Building Structure
4 | 8.8.2.1.7 | [8 empty] | nr | nr | 7 | Canopies to external areas | T1 - Building Structure
4 | 8.8.3 |  |  |  |  | 3 | Underpinning to external site boundary walls |  |  | N/A | N/A
5 | 9 | 9 | Maintenance contractor's management and administration costs
5 | 9.1 |  |  | 1 | Employer's requirements
3 | 9.1.1 |  |  |  |  | 1 | Site accommodation |  |  | T/E | T/E
4 | 9.1.2 |  |  |  |  | 2 | Site records |  |  | T/E | T/E
4 | 9.1.3 |  |  |  |  | 3 | Completion and post-completion requirements |  |  | T/E | T/E
5 | 9.1.4 |  |  |  |  | 4 | Management tasks – specific types
5 | 9.1.4.1 | [6 empty] | 1 | Air conditioning inspections
5 | 9.1.4.1.1 | [8 empty] | nr | nr | 1 | England, Wales and Northern Ireland | T17 – Management & Operations
5 | 9.1.4.1.2 | [8 empty] | nr | nr | 2 | Scotland | T17 – Management & Operations
4 | 9.1.4.2 | [6 empty] | 2 | Building logbooks and O&M Manuals | nr | nr |  |  | T17 – Management & Operations
4 | 9.1.4.3 | [6 empty] | 3 | Display energy certificates (DEC) | nr | nr |  |  | T17 – Management & Operations
4 | 9.1.4.4 | [6 empty] | 4 | Electrical installations – management audits | nr | nr |  |  | T17 – Management & Operations
3 | 9.1.4.5 | [6 empty] | 5 | Electrical lighting certificates logbook | nr | nr |  |  | T17 – Management & Operations
3 | 9.1.4.6 | [6 empty] | 6 | Energy performance certificates (EPC) | nr | nr |  |  | T17 – Management & Operations
2 | 9.1.4.7 | [6 empty] | 7 | Evaporating cooling systems – management audit | nr | nr |  |  | T17 – Management & Operations
3 | 9.1.4.8 | [6 empty] | 8 | Fire risk assessments | nr | nr |  |  | T17 – Management & Operations
3 | 9.1.4.9 | [6 empty] | 9 | Fire safety logbook | nr | nr |  |  | T17 – Management & Operations
4 | 9.1.4.10 | [6 empty] | 10 | Inventory of Greenhouses Gases (F-Gases) | nr | nr |  |  | T17 – Management & Operations
5 | 9.1.4.11 | [6 empty] | 11 | Lifting equipment – management audit | nr | nr |  |  | T17 – Management & Operations
5 | 9.1.4.12 | [6 empty] | 12 | Lifts and escalators – management audit | nr | nr |  |  | T17 – Management & Operations
5 | 9.1.4.13 | [6 empty] | 13 | Local extract ventilation – management audit | nr | nr |  |  | T17 – Management & Operations
5 | 9.1.4.14 | [6 empty] | 14 | Noise assessment and records | nr | nr |  |  | T17 – Management & Operations
5 | 9.1.4.15 | [6 empty] | 15 | Pressure systems – management audits | nr | nr |  |  | T17 – Management & Operations
5 | 9.1.4.16 | [6 empty] | 16 | Smoke control and pressurisation – management audits | nr | nr |  |  | T17 – Management & Operations
5 | 9.1.4.17 | [6 empty] | 17 | Tree reports | nr | nr |  |  | T17 – Management & Operations
3 | 9.1.4.18 | [6 empty] | 18 | Waste disposal | nr | nr |  |  | T17 – Management & Operations
1 | 9.1.4.19 | [6 empty] | 19 | Waste electrical and electronic equipment (WEEE) – management audit | nr | nr |  |  | T17 – Management & Operations
2 | 9.1.4.20 | [6 empty] | 20 | Water systems – management audit | nr | nr |  |  | T17 – Management & Operations
3 | 9.1.4.21 | [6 empty] | 21 | Asbestos | nr | nr |  |  | T17 – Management & Operations
3 | 9.1.4.22 | [6 empty] | 22 | Water Safety Plan (WSP) | nr | nr |  |  | T17 – Management & Operations
3 | 9.1.4.23 | [6 empty] | 23 | Polychlorinated Biphenyls (PCBs) - Identification, Registration, Labelling and Disposal | nr | nr |  |  | T17 – Management & Operations
3 | 9.1.4.24 | [6 empty] | 24 | Checklist for Renting Out Accommodation | nr | nr |  |  | T17 – Management & Operations
4 | 9.1.4.25 | [6 empty] | 25 | Condition Appraisal and Inventory Check | nr | nr |  |  | T17 – Management & Operations
5 | 9.1.4.26 | [6 empty] | 26 | Landlord Electrical Safety Checks - England | nr | nr |  |  | T17 – Management & Operations
5 | 9.1.4.27 | [6 empty] | 27 | Landlord Electrical Safety Checks - Northern Ireland | nr | nr |  |  | T17 – Management & Operations
4 | 9.1.4.28 | [6 empty] | 28 | Landlord Electrical Safety Checks - Scotland | nr | nr |  |  | T17 – Management & Operations
4 | 9.1.4.29 | [6 empty] | 29 | Landlord Electrical Safety Checks - Wales | nr | nr |  |  | T17 – Management & Operations
4 | 9.1.4.30 | [6 empty] | 30 | Landlord Gas Safety Checks | nr | nr |  |  | T17 – Management & Operations
4 | 9.1.4.31 | [6 empty] | 31 | Fire Alarms and Associated Equipment - Premises Management | nr | nr |  |  | T17 – Management & Operations
4 | 9.2 |  |  | 2 | Maintenance contractor's cost items
4 | 9.2.1 |  |  |  |  | 1 | Management and staff |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.2 |  |  |  |  | 2 | Site establishment |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.3 |  |  |  |  | 3 | Temporary services |  |  | T/E | T/E
4 | 9.2.4 |  |  |  |  | 4 | Security |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.5 |  |  |  |  | 5 | Safety and environmental protection |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.6 |  |  |  |  | 6 | Control and protection |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.7 |  |  |  |  | 7 | Mechanical plant |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.8 |  |  |  |  | 8 | Temporary works – in with work items |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.9 |  |  |  |  | 9 | Site records |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.10 |  |  |  |  | 10 | Transition and exit requirements |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.11 |  |  |  |  | 11 | Cleaning |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.12 |  |  |  |  | 12 | Fees and charges |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.13 |  |  |  |  | 13 | Site services |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.14 |  |  |  |  | 14 | Insurance, bonds, guarantees and warranties |  |  | Item | Item |  |  | T17 – Management & Operations
4 | 9.2.15 |  |  |  |  | 15 | Operational Tasks
4 | 9.2.15.1 | [6 empty] | 1 | Asbestos register | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.2 | [6 empty] | 2 | Emergency and panic escape doors and fire exits | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.3 | [6 empty] | 3 | Emergency lighting – power supply and maintained fittings inspections | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.4 | [6 empty] | 4 | Emergency Lighting - Centrally Powered | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.5 | [6 empty] | 5 | Emergency Lighting - Self-Contained Fittings | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.6 | [6 empty] | 6 | Fire alarm system – daily /weekly inspections | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.7 | [6 empty] | 7 | Automatic doors release mechanisms – electronic secure escape doors and fire exits
4 | 9.2.15.7.1 | [8 empty] | nr | nr | 1 | Automatic doors release mechanisms – electronic secure escape doors and fire exits | T17 – Management & Operations
4 | 9.2.15.7.2 | [8 empty] | nr | nr | 2 | Automatic Door Release Mechanisms - Electrically Held Open Fire Doors | T17 – Management & Operations
4 | 9.2.15.8 | [6 empty] | 8 | Fire evacuation drill | nr | nr |  |  | T17 – Management & Operations
2 | 9.2.15.9 | [6 empty] | 9 | Fire exit signage | nr | nr |  |  | T17 – Management & Operations
3 | 9.2.15.10 | [6 empty] | 10 | Fire hydrant – weekly checks | nr | nr |  |  | T17 – Management & Operations
3 | 9.2.15.11 | [6 empty] | 11 | Hose reels – daily, monthly and annual checks | nr | nr |  |  | T17 – Management & Operations
3 | 9.2.15.12 | [6 empty] | 12 | Insurance periodic inspections | nr | nr |  |  | T17 – Management & Operations
3 | 9.2.15.13 | [6 empty] | 13 | Independent water risk assessment (legionella) | nr | nr |  |  | T17 – Management & Operations
3 | 9.2.15.14 | [6 empty] | 14 | Meter reading
3 | 9.2.15.14.1 | [8 empty] | nr | nr | 1 | Meter Reading - Electric | T17 – Management & Operations
3 | 9.2.15.14.2 | [8 empty] | nr | nr | 2 | Meter Reading - Gas | T17 – Management & Operations
3 | 9.2.15.14.3 | [8 empty] | nr | nr | 3 | Meter Reading/Tank Dip - Oil | T17 – Management & Operations
3 | 9.2.15.14.4 | [8 empty] | nr | nr | 4 | Meter Reading - Water | T17 – Management & Operations
3 | 9.2.15.14.5 | [8 empty] | nr | nr | 5 | Meter Reading - Heat | T17 – Management & Operations
3 | 9.2.15.15 | [6 empty] | 15 | Oil storage tanks – above ground | nr | nr |  |  | T17 – Management & Operations
3 | 9.2.15.16 | [6 empty] | 16 | Plant room checks | nr | nr |  |  | T17 – Management & Operations
3 | 9.2.15.17 | [6 empty] | 17 | Portable appliance testing . PAT user checks | nr | nr |  |  | T17 – Management & Operations
3 | 9.2.15.18 | [6 empty] | 18 | Portable fire extinguishers – weekly checks | nr | nr |  |  | T17 – Management & Operations
3 | 9.2.15.19 | [6 empty] | 19 | Smoke control systems – daily 3 monthly and annual checks | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.20 | [6 empty] | 20 | Sprinkler systems – inspections | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.21 | [6 empty] | 21 | Visual inspections of voids, cavities & the like | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.22 | [6 empty] | 22 | Water risk assessment (legionella) | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.23 | [6 empty] | 23 | Water sampling and testing – closed systems | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.24 | [6 empty] | 24 | Other operational tasks (type to be stated) | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.25 | [6 empty] | 25 | Fire Blankets | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.26 | [6 empty] | 26 | Steam Boilers - Daily and Weekly Checks and Tests | nr | nr |  |  | T17 – Management & Operations
5 | 9.2.15.27 | [6 empty] | 27 | Air Conditioning Inspection (ACI) also known as TM44 Inspection - England, Wales and NI | nr | nr |  |  | T17 – Management & Operations
5 | 9.2.15.28 | [6 empty] | 28 | Air Conditioning Inspection (ACI) also known as TM44 Inspection - Scotland | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.29 | [6 empty] | 29 | Display Energy Certificates (DEC's) - England and Wales | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.30 | [6 empty] | 30 | Energy Performance Certificates (EPC's) | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.31 | [6 empty] | 31 | Bird Excrement and Associated Material Removal | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.32 | [6 empty] | 32 | Compressed Gas Cylinders (External Storage) | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.33 | [6 empty] | 33 | Gas Safety Checks, Tightness Testing and Reporting Procedures | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.15.34 | [6 empty] | 34 | Air Compressors and Receivers - Operational Checks | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.16 |  |  |  |  | 16 | Periodic maintenance
5 | 9.2.16.1 | [6 empty] | 1 | Ducting – volume control dampers (5 yearly) | nr | nr |  |  | T17 – Management & Operations
5 | 9.2.16.2 | [6 empty] | 2 | Electrical Fixed wiring testing (2 to 5 yearly) | nr | nr |  |  | T17 – Management & Operations
5 | 9.2.16.3 | [6 empty] | 3 | Hose reels – static and swinging (5 yearly) | nr | nr |  |  | T17 – Management & Operations
5 | 9.2.16.4 | [6 empty] | 4 | Main switch panel at supply intake (2 yearly) | nr | nr |  |  | T17 – Management & Operations
5 | 9.2.16.5 | [6 empty] | 5 | Portable appliance testing – (2 yearly) | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.16.6 | [6 empty] | 6 | Sprinkler systems (3 yearly, 5 yearly etc) | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.16.7 | [6 empty] | 7 | Suspended façade access equipment (10 yearly) | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.16.8 | [6 empty] | 8 | Insurance periodic inspections (2 yearly) | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.16.9 | [6 empty] | 9 | Vertical platform lifts (2 yearly) | nr | nr |  |  | T17 – Management & Operations
4 | 9.2.16.10 | [6 empty] | 10 | Redecorations programme - Internal
4 | 9.2.16.10.1 | [8 empty] | Item/m2 | Item/m2 | 1 | Walls | T15 – Redecorations
4 | 9.2.16.10.2 | [8 empty] | Item/m2 | Item/m2 | 2 | Ceilings | T15 – Redecorations
4 | 9.2.16.10.3 | [8 empty] | Item/m2 | Item/m2 | 3 | Floors | T15 – Redecorations
4 | 9.2.16.10.4 | [8 empty] | Item/m2 | Item/m2 | 4 | Windows | T15 – Redecorations
4 | 9.2.16.10.5 | [8 empty] | Item/m2 | Item/m2 | 5 | Doors | T15 – Redecorations
4 | 9.2.16.11 | [6 empty] | 11 | Redecorations programme - External
4 | 9.2.16.11.1 | [8 empty] | Item/m2 | Item/m2 | 1 | Walls | T15 – Redecorations
4 | 9.2.16.11.2 | [8 empty] | Item/m2 | Item/m2 | 2 | Ceilings | T15 – Redecorations
4 | 9.2.16.11.3 | [8 empty] | Item/m2 | Item/m2 | 3 | Floors | T15 – Redecorations
4 | 9.2.16.11.4 | [8 empty] | Item/m2 | Item/m2 | 4 | Windows | T15 – Redecorations
4 | 9.2.16.11.5 | [8 empty] | Item/m2 | Item/m2 | 5 | Doors | T15 – Redecorations
4 | 9.2.16.12 | [6 empty] | 12 | Cleaning of Roof Walkways | Item/m2 | Item/m2 |  |  | T2 - Roofing
4 | 9.2.17 |  |  |  |  | 17 | Specialist piped supply systems
4 | 9.2.17.1 | [6 empty] | 1 | Medical and laboratory gas supply systems Eng & Wales
4 | 9.2.17.1.1 | [8 empty] | nr | nr | 1 | Medical Gases - Refresher Training and Reassessment | T16 – Specialist
3 | 9.2.17.1.2 | [8 empty] | nr | nr | 2 | Vacuum Insulated Evaporator (VIE) Plant - Daily and Weekly Tasks | T16 – Specialist
4 | 9.2.17.1.3 | [8 empty] | nr | nr | 3 | Emergency Supply Kits - Operational Test | T16 – Specialist
4 | 9.2.17.2 | [6 empty] | 2 | Medical and laboratory gas supply systems Scotland
4 | 9.2.17.2.1 | [8 empty] | nr | nr | 1 | Medical Gases - Refresher Training and Reassessment | T16 – Specialist
4 | 9.2.17.2.2 | [8 empty] | nr | nr | 2 | Vacuum Insulated Evaporator (VIE) Plant - Daily and Weekly Tasks | T16 – Specialist
4 | 9.2.17.2.3 | [8 empty] | nr | nr | 3 | Emergency Supply Kits - Operational Test | T16 – Specialist
4 | 10 | 10 | Maintenance contractor's overhead and profit
4 | 10.1 |  |  | 1 | Maintenance contractor's overhead
4 | 10.1.1 |  |  |  |  | 1 | Maintenance contractor's overhead |  |  | Item | Item |  |  | T18 – Contractors Overheads & Profit
4 | 10.2 |  |  | 2 | Maintenance contractor's profit
4 | 10.2.2 |  |  |  |  | 2 | Maintenance contractor's profit |  |  | Item | Item |  |  | T18 – Contractors Overheads & Profit
5 | 11 | 11 | Consultant and specialist fees
5 | 11.1 |  |  | 1 | Consultant's and specialist fees
5 | 11.1.1 |  |  |  |  | 1 | Consultant's and specialist fees |  |  | Item | Item |  |  | T19 - Specialist Fees
5 | 11.1.2 |  |  |  |  | 2 | Other consultant's fees |  |  | Item | Item |  |  | T19 - Specialist Fees
5 | 11.1.3 |  |  |  |  | 3 | Site investigation fees |  |  | Item | Item |  |  | T19 - Specialist Fees
4 | 11.1.4 |  |  |  |  | 4 | Specialist support consultant's fees |  |  | Item | Item |  |  | T19 - Specialist Fees
5 | 11.2 |  |  | 2 | Maintenance contractor's tender / pre-contract fees
5 | 11.2.1 |  |  |  |  | 1 | Management and staff fees |  |  | Item | Item |  |  | T19 - Specialist Fees
5 | 11.2.2 |  |  |  |  | 2 | Specialist support services fees |  |  | Item | Item |  |  | T19 - Specialist Fees
5 | 11.2.3 |  |  |  |  | 3 | Temporary accommodation, services and facilities charges |  |  | Item | Item |  |  | T19 - Specialist Fees
5 | 11.2.4 |  |  |  |  | 4 | Main contractor's overhead and profit |  |  | Item | Item |  |  | T19 - Specialist Fees
4 | 11.3 |  |  | 3 | Maintenance contractor's design fees
3 | 11.3.1 |  |  |  |  | 1 | Main contractor's design consultant's fees |  |  | Item | Item |  |  | T19 - Specialist Fees
4 | 12 | 12 | Employer definable maintenance related costs
5 | 12.1 |  |  | 1 | Employer definable maintenance related costs
5 | 12.1.1 |  |  |  |  | 1 | Land acquisition costs |  |  | Item | Item |  |  | T20 - Employers Costs
5 | 12.1.2 |  |  |  |  | 2 | Employer finance costs |  |  | Item | Item |  |  | T20 - Employers Costs
4 | 12.1.3 |  |  |  |  | 3 | Fees |  |  | Item | Item |  |  | T20 - Employers Costs
5 | 12.1.4 |  |  |  |  | 4 | Charges |  |  | Item | Item |  |  | T20 - Employers Costs
5 | 12.1.5 |  |  |  |  | 5 | Planning contributions |  |  | Item | Item |  |  | T20 - Employers Costs
5 | 12.1.6 |  |  |  |  | 6 | Insurances |  |  | Item | Item |  |  | T20 - Employers Costs
1 | 12.1.7 |  |  |  |  | 7 | Archaeological field work |  |  | Item | Item |  |  | T20 - Employers Costs
2 | 12.1.8 |  |  |  |  | 8 | Other specialist fieldwork |  |  | Item | Item |  |  | T20 - Employers Costs
3 | 12.1.9 |  |  |  |  | 9 | Decanting and relocation costs |  |  | Item | Item |  |  | T20 - Employers Costs
2 | 12.1.10 |  |  |  |  | 10 | Fittings, furnishings and equipment |  |  | Item | Item |  |  | T20 - Employers Costs
3 | 12.1.11 |  |  |  |  | 11 | Tenant's costs/contributions |  |  | Item | Item |  |  | T20 - Employers Costs
1 | 12.1.12 |  |  |  |  | 12 | Marketing costs |  |  | Item | Item |  |  | T20 - Employers Costs
2 | 12.1.13 |  |  |  |  | 13 | Other employer costs |  |  | Item | Item |  |  | T20 - Employers Costs
3 | 12.1.14 |  |  |  |  | 14 | Allowances |  |  | Item | Item |  |  | T20 - Employers Costs
3 | 12.1.15 |  |  |  |  | 15 | Energy efficiency |  |  | Item | Item |  |  | T20 - Employers Costs
3 | 12.1.16 |  |  |  |  | 16 | Office churn |  |  | Item | Item |  |  | T20 - Employers Costs
3 | 12.1.17 |  |  |  |  | 17 | Soft services – operations |  |  | Item | Item |  |  | T20 - Employers Costs
2 | 12.1.18 |  |  |  |  | 18 | End of life |  |  | Item | Item |  |  | T20 - Employers Costs
3 | 12.1.19 |  |  |  |  | 19 | Third party income |  |  | Item | Item |  |  | T20 - Employers Costs
3 | 12.1.20 |  |  |  |  | 20 | Loss of income |  |  | Item | Item |  |  | T20 - Employers Costs
3 | 13 | 13 | Risks
3 | 13.1 |  |  | 1 | Design and installation risks
2 | 13.1.1 |  |  |  |  | 1 | Design development and standards |  |  | Item | Item |  |  | T21 - Risks
3 | 13.1.2 |  |  |  |  | 2 | Construction installation legacy risks |  |  | Item | Item |  |  | T21 - Risks
1 | 13.1.3 |  |  |  |  | 3 | Handover |  |  | Item | Item |  |  | T21 - Risks
2 | 13.1.4 |  |  |  |  | 4 | Legislation and changing future regulations, e.g. Health & Safety at work |  |  | Item | Item |  |  | T21 - Risks
3 | 13.2 |  |  | 2 | Maintenance risks | [8 empty] | T21 - Risks
3 | 13.2.1 |  |  |  |  | 1 | Procurement |  |  | Item | Item |  |  | T21 - Risks
3 | 13.2.2 |  |  |  |  | 2 | Maintenance delivery |  |  | Item | Item |  |  | T21 - Risks
3 | 13.2.3 |  |  |  |  | 3 | Life cycle replacement works |  |  | Item | item |  |  | T21 - Risks
3 | 13.3 |  |  | 3 | Employer change risks
3 | 13.3.1 |  |  |  |  | 1 | Project brief |  |  | Item | Item |  |  | T21 - Risks
3 | 13.3.2 |  |  |  |  | 2 | Scope creep |  |  | Item | Item |  |  | T21 - Risks
3 | 13.3.3 |  |  |  |  | 3 | System redundancy |  |  | Item | Item |  |  | T21 - Risks
3 | 13.3.4 |  |  |  |  | 4 | Timescales |  |  | item | Item |  |  | T21 - Risks
3 | 13.4 |  |  | 4 | Employer other risks
3 | 13.4.1 |  |  |  |  | 1 | Maintenance brief |  |  | Item | Item |  |  | T21 - Risks
3 | 13.4.2 |  |  |  |  | 2 | Timescales |  |  | item | Item |  |  | T21 - Risks
3 | 13.4.3 |  |  |  |  | 3 | Third party |  |  | Item | Item |  |  | T21 - Risks
3 | 13.4.4 |  |  |  |  | 4 | Management |  |  | Item | item |  |  | T21 - Risks
3 | 13.4.5 |  |  |  |  | 5 | Financial |  |  | Item | item |  |  | T21 - Risks
3 | 13.4.6 |  |  |  |  | 6 | Other |  |  | Item | item |  |  | T21 - Risks
3 | 14 | 14 | Inflation
3 | 14.1 |  |  | 1 | Tender inflation |  |  |  |  | Item | Item |  |  | T22 - Inflation
3 | 14.2 |  |  | 2 | Construction inflation |  |  |  |  | Item | item |  |  | T22 - Inflation
3 | 14.3 |  |  | 3 | Life cycle renewal inflation |  |  |  |  | Item | item |  |  | T22 - Inflation
1 | 14.4 |  |  | 4 | Life cycle discount rate |  |  |  |  | Item | item |  |  | T22 - Inflation

## 4A Supplementary Table
BUILDING FABRIC & CIBSE Guide M SERVICES
Supplementary List - Version January 2026
Supplementary lists of building fabric sub components and ancillaries and building services sub components and ancillaries (applicable to various systems)
Below is a list of sub components which have a BESA SFG20 maintenance task schedule (as at August 2025)
Applicable components are to be included with the relevant systems or components (e.g. ceiling tiles (referred to in the group tables 3.3.2)
Part 6 of these rules) and pumps, valves, fans, filters, controls (referred to in the group tables 5.1 to 5.13 and in Part 6 of these rules))
SL L2 | SUP-Type | Included components or subcomponent - List of Supplementary or Ancillaries sub- components | Unit of measure
| Actuators | Actuators
1 | Actuators | Thermal actuators | Nr
2 | Actuators | Pneumatic actuators | Nr
3 | Actuators | Hydraulic actuators | Nr
4 | Actuators | Motor driven actuators | Nr
5 | Actuators | Power fail - motor return actuators | Nr
6 | Actuators | Power fail - spring return actuators | Nr
7 | Actuators | Building Management Systems
| Compressors | Compressors
1 | Compressors | Compressors – refrigeration - reciprocal | Nr
2 | Compressors | Compressor - screw | Nr
3 | Compressors | Compressor refrigeration - centrifugal | Nr
4 | Compressors | Compressor – scroll | Nr
5 | Compressors | Air compressors and receivers | Nr
6 | Compressors | Air compressors – compressed air dryers | Nr
7 | Compressors | Compressors air network distribution | Nr
8 | Compressors | Air Compressors Compressed Air Dryers - Water Cooled After Coolers | System
9 | Compressors | Air Compressors Compressed Air Dryers - Water Absorption Type | Nr
10 | Compressors | Compressed Gas Cylinders (External Storage) | Nr
11 | Compressors | Air Compressors and Receivers - Operational Checks | System
| Controllers and sensors | Controllers and sensors
1 | Controllers and sensors | Magnahelic Gauge Panel and Manometers | Nr
2 | Controllers and sensors | Multiple boilers – sequence control | Nr
3 | Controllers and sensors | Boiler controls – single boiler on/off | Nr
4 | Controllers and sensors | Boiler protection controls | Nr
5 | Controllers and sensors | Boilers – space temperature controls | Nr
6 | Controllers and sensors | Boilers – fire and safety circuits | Nr
7 | Controllers and sensors | Control panels – electrical services | Nr
8 | Controllers and sensors | Control panels – lamps, meters, alarms | Nr
9 | Controllers and sensors | Control optimiser | Nr
10 | Controllers and sensors | Heating control - compensator type | Nr
11 | Controllers and sensors | Controller single input type | Nr
12 | Controllers and sensors | Controller unit and sensor type | Nr
13 | Controllers and sensors | Controller - timer type | Nr
14 | Controllers and sensors | Step controllers | Nr
15 | Controllers and sensors | Time switches | Nr
16 | Controllers and sensors | Multi input controllers | Nr
17 | Controllers and sensors | Indicator and displays | Nr
18 | Controllers and sensors | Alarm modules | Nr
19 | Controllers and sensors | Level controllers | Nr
20 | Controllers and sensors | Speed controllers | Nr
21 | Controllers and sensors | Transducers | Nr
22 | Controllers and sensors | Direct Current (DC) Drives | Nr
23 | Controllers and sensors | Emergency stop button | Nr
24 | Controllers and sensors | Access Control | Nr
25 | Controllers and sensors | Emergency Assistance Alarm | Nr
26 | Controllers and sensors | Instrument Control Panel | Nr
27 | Controllers and sensors | Local Control Panel/Local Control Station | Nr
28 | Controllers and sensors | Motor Control Centre | Nr
29 | Controllers and sensors | Water Leak Detection Systems | Nr
30 | Controllers and sensors | Lighting Control Module | Nr
31 | Controllers and sensors | Controller Timers - Electronic | Nr
32 | Controllers and sensors | Step Controllers - Electronic | Nr
33 | Controllers and sensors | Time Switches - Electronic | Nr
34 | Controllers and sensors | Control dampers | Nr
35 | Controllers and sensors | Ducting - Motorised Volume Control Dampers (VCDs) | Nr
36 | Controllers and sensors | Flue Gas Oxygen Control | System
37 | Controllers and sensors | Calorifier and Heat Exchange Controls | System
38 | Controllers and sensors | Controller - flow meter | Nr
39 | Controllers and sensors | Pneumatic relays | Nr
40 | Controllers and sensors | Digital Bus Power Supply | Nr
41 | Controllers and sensors | Door Access Control | System
42 | Controllers and sensors | Switches and sensors | Nr
43 | Controllers and sensors | Pressure measurement sensors | Nr
44 | Controllers and sensors | Temperature measurement sensors | Nr
45 | Controllers and sensors | Relative humidity sensor | Nr
46 | Controllers and sensors | Absolute humidity sensor | Nr
47 | Controllers and sensors | Air quality sensor | Nr
48 | Controllers and sensors | Carbon dioxide sensor | Nr
49 | Controllers and sensors | Velocity sensor | Nr
50 | Controllers and sensors | Occupancy and light sensors | Nr
51 | Controllers and sensors | Smoke Detectors | Nr
52 | Controllers and sensors | Gas Detector Sensors/Carbon Monoxide Sensors | Nr
53 | Controllers and sensors | Wind Speed and Wind Direction Sensors | Nr
54 | Controllers and sensors | Gas Detection Panel | Nr
55 | Controllers and sensors | Magnetic Level Sensors/Switch | Nr
56 | Controllers and sensors | Float Switch | Nr
57 | Controllers and sensors | Portable Refrigerant Leak Detectors | Nr
58 | Controllers and sensors | Absolute Humidity Sensors - Duct-Mounted | Nr
59 | Controllers and sensors | Air Quality Sensors - Duct-Mounted | Nr
60 | Controllers and sensors | Gas Sensors - Carbon Dioxide - Duct-Mounted | Nr
61 | Controllers and sensors | Light Level Sensors | Nr
62 | Controllers and sensors | Temperature Sensors - External | Nr
63 | Controllers and sensors | Temperature Sensors - Duct-Mounted | Nr
64 | Controllers and sensors | Temperature Sensors - Immersion | Nr
65 | Controllers and sensors | Temperature Sensors - Clamp-On and Surface-Mounted | Nr
66 | Controllers and sensors | Gas Sensors - Oxygen | Nr
67 | Controllers and sensors | Gas Sensors - Carbon Monoxide | Nr
68 | Controllers and sensors | Relative Humidity Sensors - External | Nr
69 | Controllers and sensors | Relative Humidity Sensors - Duct-Mounted | Nr
70 | Controllers and sensors | On/off switching devices | Nr
71 | Controllers and sensors | Control Relays | Nr
72 | Controllers and sensors | Automatic Transfer Switch | Nr
73 | Controllers and sensors | Mobile Electronically Controlled Cyclone Separator | Nr
74 | Controllers and sensors | Ammonia Leak Detection System | Nr
75 | Controllers and sensors | Chlorine Analyser/Controller System | System
76 | Controllers and sensors | Fibre Optic Wall Sensors | Nr
77 | Controllers and sensors | Microwave Motion Sensors | System
78 | Controllers and sensors | Voltage optimisation unit | Nr
| Ductwork | Ductwork
1 | Ductwork | Ductwork system – general | Nr
2 | Ductwork | Ductwork ancillaries – various | Nr
3 | Ductwork | Ducting - volume control dampers and fire/ smoke dampers | Nr
4 | Ductwork | Ducting – attenuators and acoustics | Nr
5 | Ductwork | Ducting - Fire Dampers - Fusible Link Type | Nr
6 | Ductwork | Ducting - Combined Fire/Smoke Dampers used in Smoke Control Systems for Means of Escape | Nr
7 | Ductwork | Ducting - Combined Fire/Smoke Dampers used in Ventilation Systems | Nr
8 | Ductwork | Ductwork – cleaning hygiene, inspections and monitoring | Nr
9 | Ductwork | External louvers (anodised aluminium) | Nr
10 | Ductwork | External louvers (steel painted) | Nr
11 | Ductwork | Grilles /diffusers (anodised aluminium) | Nr
12 | Ductwork | Grilles /diffusers (painted metal) | Nr
13 | Ductwork | Heat Exchangers - Water to Air | Nr
14 | Ductwork | Plate recuperator | Nr
15 | Ductwork | Thermal wheels | Nr
16 | Ductwork | Run around heat recovery coil | Nr
17 | Ductwork | Plate heat exchangers | Nr
18 | Ductwork | Heat Exchangers - Indirect Gas Fired to Air | Nr
19 | Ductwork | Heat Exchangers - Steam to Air | Nr
20 | Ductwork | Heat Exchangers - Water to Water | Nr
| Electrical ancillaries | Electrical ancillaries
1 | Electrical ancillaries | Control relays | Nr
2 | Electrical ancillaries | Isolators/ starters/ fuse switches | Nr
3 | Electrical ancillaries | Motors - drive elements | Nr
| Fans | Fans
1 | Fans | Fans | Nr
2 | Fans | Fans - Ventilating general | Nr
3 | Fans | Fans – High temperature (boiler combustion) | Nr
4 | Fans | Fans – Roof mounted units | Nr
5 | Fans | Fans - Centrifugal | Nr
6 | Fans | Fans - Axial | Nr
7 | Fans | Fans - Propeller | Nr
8 | Fans | Fans - Mixed flow | Nr
9 | Fans | Fans - Bifurcated | Nr
10 | Fans | Fans – Extract - (domestic purposes) | Nr
11 | Fans | Fans – Extract – including fire/smoke units | Nr
12 | Fans | Ammonia Extract Fan | Nr
13 | Fans | Hazardous Area Extract Fan | Nr
14 | Fans | Extract Fans - Twin Toilet | Nr
15 | Fans | Fans - Window or Wall Mounted | Nr
| Filters | Filters
1 | Filters | Air handling unit - filters | Nr
2 | Filters | Air Filters - Disposal | Nr
3 | Filters | Electrostatic filters | Nr
4 | Filters | Ductwork ancillaries – filters: | Nr
5 | Filters | Air Filters - Reusable | Nr
6 | Filters | Air Filters - Absorption Type | Nr
7 | Filters | Air Filters - Automatic Roll Band Type | Nr
8 | Filters | Air Filters - Grease | Nr
9 | Filters | Air Filters - High Efficiency - HEPA | Nr
| Humidifiers/dehumidifiers | Humidifiers/dehumidifiers
1 | Humidifiers/dehumidifiers | Humidifier – cold water evaporator drum type | Nr
2 | Humidifiers/dehumidifiers | Humidifier – direct stream injection type | Nr
3 | Humidifiers/dehumidifiers | Humidifier – electrode boiler | Nr
4 | Humidifiers/dehumidifiers | Humidifier – compressed air type | Nr
5 | Humidifiers/dehumidifiers | Humidifier – ultrasonic | Nr
6 | Humidifiers/dehumidifiers | Humidifier – resistance heater type | Nr
7 | Humidifiers/dehumidifiers | Humidifiers – spray | Nr
8 | Humidifiers/dehumidifiers | Humidifiers – Spirax Sarco direct steam injection type | Nr
9 | Humidifiers/dehumidifiers | Humidifiers – steam humidifier (VAPAC type) | Nr
10 | Humidifiers/dehumidifiers | Dehumidifier - Desiccant Type | Nr
11 | Humidifiers/dehumidifiers | Dehumidifier - Heat Pump Type | Nr
12 | Humidifiers/dehumidifiers | Humidifiers - Gas-fired | Nr
| Pumps | Pumps
1 | Pumps | Pumps – general | Nr
2 | Pumps | Circulating pumps | Nr
3 | Pumps | Centrifugal pumps | Nr
4 | Pumps | Pressurisation pumps | Nr
5 | Pumps | Rotary hand pumps | Nr
6 | Pumps | Secondary hot water circulation pumps | Nr
7 | Pumps | Sewage or drainage pumps submersible | Nr
8 | Pumps | Sewage and drainage pumps – drywell | Nr
9 | Pumps | Sewage pumps – compressed air | Nr
10 | Pumps | Sump pumps – extended shaft | Nr
11 | Pumps | Domestic water accelerators | Nr
12 | Pumps | Water booster pumps | Nr
13 | Pumps | Steam driven pumps | Nr
14 | Pumps | Condensate pumps | Nr
15 | Pumps | Fuel oil transfer pumps | Nr
16 | Pumps | Twin set pumps | Nr
17 | Pumps | Shower booster pumps | Nr
| Starters | Starters
1 | Starters | Drive element – starters | Nr
2 | Starters | Starters – star delta | Nr
3 | Starters | Starters – two speed – dual wound | Nr
4 | Starters | Starters – two speed – pole change | Nr
5 | Starters | Starters – reversing | Nr
6 | Starters | Starters – auto transformer | Nr
7 | Starters | Starters – quick transition electric heater | Nr
8 | Starters | Starters – electrolyte type | Nr
9 | Starters | Starters – air break and contactors | Nr
10 | Starters | Motors – drive elements | Nr
11 | Starters | Direct current drives | Nr
12 | Starters | Speed Controllers - Auto-Transformer | Nr
13 | Starters | Speed Controllers - Variable Transformer | Nr
14 | Starters | Speed Controllers - Eddy Current Type | Nr
15 | Starters | Speed Controllers - Inverter Type | Nr
| Taps and outlet fittings | Taps and outlet fittings
1 | Taps and outlet fittings | Taps and outlet fittings | Nr
2 | Taps and outlet fittings | Taps and outlet fittings – sluice valves | Nr
3 | Taps and outlet fittings | Taps and outlet fittings – stop cocks and stop taps | Nr
4 | Taps and outlet fittings | Combination tap assemblies – non-thermostatic mixing valves (type 1) | Nr
5 | Taps and outlet fittings | Combination tap assemblies – thermostatic mixing valves (type 2) | Nr
6 | Taps and outlet fittings | Combination tap assemblies – thermostatic mixing valves (type 3) | Nr
7 | Taps and outlet fittings | Automatic (sensor) taps | Nr
8 | Taps and outlet fittings | Spray taps | Nr
| Valves | Valves
1 | Valves | Free fall fire valves – gas and oil | Nr
2 | Valves | Solenoid gas/oil shut-off (safety) valves | Nr
3 | Valves | Air admittance valves | Nr
4 | Valves | Shower valves | Nr
5 | Valves | Steam boiler water level control valves (Mobrey) | Nr
6 | Valves | Butterfly and ball valves | Nr
7 | Valves | Valves – boiler valves | Nr
8 | Valves | Valves – diaphragm valves | Nr
9 | Valves | Valves – float operated valve | Nr
10 | Valves | Valves – gate | Nr
11 | Valves | Valves – globe valves | Nr
12 | Valves | Valves – lubricated plug valves | Nr
13 | Valves | Valves – multiport valves | Nr
14 | Valves | Valves – parallel slide valves | Nr
15 | Valves | Valves – sluice valves | Nr
16 | Valves | Valves – steam pressure reducing valves | Nr
17 | Valves | Valves – steam safety valves | Nr
18 | Valves | Valves – thermostatic radiator valves (TRVs) | Nr
19 | Valves | Combination tap assemblies, mixing valves/taps | Nr
20 | Valves | Automatic Air Vent (AAV) | Nr
21 | Valves | Double Regulating Valve (DRV) | Nr
22 | Valves | Valves – automatic control | Nr
23 | Valves | Rotary valves – shoe or slipper | Nr
24 | Valves | Self acting and thermal valves | Nr
25 | Valves | Solenoid valves | Nr
26 | Valves | Pressure control valves | Nr
27 | Valves | Seat valves | Nr
28 | Valves | Reduced Pressure Zone (RPZ) valves | Nr
| Pipework | Pipework
1 | Pipework | Copper | m/m²
2 | Pipework | Steel galvanised (closed) | m/m²
3 | Pipework | Steel galvanised (open) | m/m²
4 | Pipework | Plastic or non-metallic | m/m²

## 5. NRM 3 List of Function Types
NRM 3 - Excel extract from the published 1st edition effective from 1st January 2015
Appendix C: Commonly used functional units and functional units of measurement
Function | Functional unit of measurement
Car parking
Car parking | per car parking space
Administrative facilities
Offices | per m² of Gross internal area (GIA)
Commercial facilities
Shops | per m² of retail area (m²)
Department stores | per m² of retail area (m²)
Shopping centres | per m² of retail area (m²)
Retail warehouses | per m² of retail area (m²)
Industrial facilities
Factories | per m² of Gross internal area (GIA)
Warehouses/stores | per m² of Gross internal area (GIA)
Livestock buildings – farms (pig pens, milking parlours and the like) | per animal
Residential facilities
Houses (private developer and affordable) | per house type (based on number of bedrooms)
Bungalows (private developer and affordable) | per bedroom
Apartments/flats (private developer and affordable) | per apartment/flat type (based on number of bedrooms)
Hotels/motels | per bedroom
Hotel furniture, fittings and equipment | per bedroom
Student accommodation | per bedroom
Youth hostels | per bedroom
Religious
Churches, chapels, temples, mosques and the like | per pew or per seat
Education, scientific, information facilities
Schools | per child or per student
Universities, colleges and the like | per student
Conference centres | per m² of Gross internal floor area (GIA)
Health and welfare facilities
Hospitals | per bed space
Nursing homes | per bed space
Doctors’ surgeries | per doctor consulting room
Dentists’ surgeries | per dentist workspace
Police
Aviation Hangars and Servicing | per m² of Gross internal area (GIA)
Boatyard (Wapping) | per m² of Gross internal area (GIA)
Classrooms/Lecture Theatre | per m² of Gross internal area (GIA)
Command and Control Centres (X3) | per m² of Gross internal area (GIA)
Courtroom | per m² of Gross internal area (GIA)
Firearms & Public Order Training Units | per m² of Gross internal area (GIA)
Gyms | per m² of Gross internal area (GIA)
Housing | per house/flat
Kennels | per m² of Gross internal area (GIA)
Kitchen & Messing | per m² of Gross internal area (GIA)
Laboratories | per m² of Gross internal area (GIA)
Office Accommodation | per m² of Gross internal area (GIA)
Police Stations | per m² of Gross internal area (GIA)
Sports clubs | per club
Retail units (Safer neighbourhood centres) | per m² of Gross internal area (GIA)
Stables | per m² of Gross internal area (GIA)
Vehicle Patrol Bases | per m² of Gross internal area (GIA)
Vehicle Repair Shops | per m² of Gross internal area (GIA)
Workshops | per m² of Gross internal area (GIA)
Protective facilities
Fire stations | per fire tender space
Ambulance stations | per ambulance vehicle space
Law courts | per courtroom
Prisons | per prisoner
Recreational facilities
Theatre | per seat
Cinemas | per seat or per screen
Concert halls | per seat
Restaurants | per seat
Squash courts, tennis courts and the like | per court
Football stadia | per seat
Military facilities
Barracks | per m² of Gross internal floor area (GIA)
Mess Halls | per m² of Gross internal floor area (GIA)
Hangers | per m² of Gross internal floor area (GIA)
Education blocks | per m² of Gross internal floor area (GIA)
Gymnasiums / Fitness facilities | per m² of Gross internal floor area (GIA)
Staff housing | per house
Parade grounds | per m² of external area
Workshops | per m² of Gross internal floor area (GIA)

## 6. NRM 3 Elemental Structure
NRM 3 - Excel extract from the published 1st edition effective from 1st January 2015
Table 3.2 Elemental structure for elemental method of cost estimating
| Group element | Element
| 0 Facilitating works | 0.0 Facilitating works
| 1 Structures | 1.0 Substructures
| 2 Superstructures | 2.1 Frame
2.2 Upper floors
2.3 Roof
2.4 Stairs and ramps
2.5 External walls
2.6 Windows and external doors
2.7 Internal walls and partitions
2.8 Internal doors
| 3 Internal finishes | 3.1 Wall finishes
3.2 Floor finishes
3.3 Ceiling finishes
| 4 Fittings, furnishings and equipment | 4.1 Fittings, furnishings and equipment
| 5 Services | 5.1 Sanitary installations
5.2 Services equipment
5.3 Disposal installations
5.4 Water installations
5.5 Heat source
5.6 Space heating and air conditioning
5.7 Ventilation
5.8 Electrical installations
5.9 Fuel installations
5.10 Lift and conveyor installations/systems
5.11 Fire and lightning protection
5.12 Communication, security and control systems
5.13 Special installations/systems
5.14 Builder’s work in connection with services
6 Prefabricated buildings and building units Not covered by NRM 3 rules
7 Works to existing buildings
| 8 External works | 8.1 Site preparation works (N/A to NRM 3)
8.2 Roads, paths and pavings
8.3 Planting (i.e. grounds maintenance)
8.4 Fencing, railings and walls
8.5 External fittings
8.6 External drainage
8.7 External services

## 7. NRM3 Table 3.4 OrderEstimate
NRM 3 - Excel extract from the published 1st edition effective from 1st January 2015
3.4 Constituents of an order of estimate
The key constituents of an order of estimate for building maintenance works are as follows:
Table 3.4 - Constituents of an order of estimate
Constituents (Cost Centre) | £Y1 | £Y2 | £Y3 |  | £Yn | Reference / Notes
| £k | £k | £k | £k | £k
Renewal costs estimate (1) | £Y1 | £Y2 | £Y3 |  | £Yn | See paragraphs 3.5 to 3.9
Maintain costs estimate (2) | £Y1 | £Y2 | £Y3 |  | £Yn | See paragraphs 3.5 to 3.9
Sub total (3) [(3) = (1) + (2)] | £Y1 | £Y2 | £Y3 |  | £Yn
Maintenance contractor's management and admin costs estimate (4) | £Y1 | £Y2 | £Y3 |  | £Yn | See paragraph 3.10
Sub total (5) [(5) = (3) + (4)] | £Y1 | £Y2 | £Y3 |  | £Yn
Maintenance contractor's overheads and profit estimate (6) | £Y1 | £Y2 | £Y3 |  | £Yn | See paragraph 3.11
Maintenance Cost Estimate (7) Sub total (7) [(7) = (6) + (5)] | £Y1 | £Y2 | £Y3 |  | £Yn
Consultant's / specialist fees estimate (8) | £Y1 | £Y2 | £Y3 |  | £Yn | See paragraph 3.12
Other employer definable maintenance related costs estimate (9) | £Y1 | £Y2 | £Y3 |  | £Yn | See paragraph 3.13
Base Cost Estimate (10) Sub total (10) [(10) = (7) + (8) + (9)] | £Y1 | £Y2 | £Y3 |  | £Yn
Risk allowance estimate (11) | [5 empty] | See paragraph 3.14
a) Design installation risks (11a) | £Y1 | £Y2 | £Y3 |  | £Yn
b) Maintenance risks (11b) | £Y1 | £Y2 | £Y3 |  | £Yn
c) Employer change risks (11c) | £Y1 | £Y2 | £Y3 |  | £Yn
d) Employer other risks (11d) | £Y1 | £Y2 | £Y3 |  | £Yn
Risk Allowance Estimate (11) Sub total (11) [(11) = (11a) + (11b) + 11c + 11d)] | £Y1 | £Y2 | £Y3 |  | £Yn
Cost limit (at current price levels) (12)
[(12) = (10) + (11) ] | £Y1 | £Y2 | £Y3 |  | £Yn
Discount factor (DF) (13) | DF1 | DF2 | Df3 |  | DFn | See paragraph 3.19
Present Value (PV) (14)
[ (14) = (12) x (13) ] | £Y1 | £Y2 | £Y3 |  | £Yn | See paragraph 3.19
Net Present Value (NPV) Total Cost Limit - (15)
[ (15) = Z(PV) (14) ] | £Y1 | £Y2 | £Y3 |  | £Yn | See paragraph 3.19
Notes
VAT and other taxation incentives are excluded - see paragraph 3.16 and 3.17
Other considerations (as defined in paragraph 3.18 are to be taken into account if required
£Y1 = Year 1 costs
£Y2 = Year 2 costs
£Y3 = Year 3 costs
£Yn = Final year costs in which either maintenance or renewal works are to be undertaken (or in period of analysis)
DF1 = Year 1 discount factor
DF2 = Year 2 discount factor
DF3 = Year 3 discount factor
DFn = Discount factor for final year in which either maintenance or renewal works are to be undertaken (or in period of analysis)

## 8. NRM 3 Table 4.3 Cost Plan T
NRM 3 - Excel extract from the published 1st edition effective from 1st January 2015
4.3 Constituents of a maintenance cost plan
The key constituents of a maintenance cost plan are as follows:
Table 4.3: Constituents of a cost plan
Constituents (Cost Centre) | £Y1 | £Y2 | £Y3 | … | £Yn | Reference / Notes
| £k | £k | £k |  | £k
Renewal (R ) annualised costs:
(1a) Facilitating works | £Y1 | £Y2 | £Y3 | … | £Yn
(1b) Substructure | £Y1 | £Y2 | £Y3 | … | £Yn
(1c) Superstructure | £Y1 | £Y2 | £Y3 | … | £Yn
(1d) Internal finishes | £Y1 | £Y2 | £Y3 | … | £Yn
(1e) Fittings, furniture and equipment | £Y1 | £Y2 | £Y3 | … | £Yn
(1f) Services | £Y1 | £Y2 | £Y3 | … | £Yn
(1g) Work to existing buildings | £Y1 | £Y2 | £Y3 | … | £Yn | If not covered in 1e to 1f.
(1h) External works | £Y1 | £Y2 | £Y3 | … | £Yn
Total - Renewal costs estimate (1)
[(1) = Σ (1a) + (1b) + (…) + (1h)] | £Y1 | £Y2 | £Y3 | … | £Yn | See paragraphs 4.8 to 4.11
Maintain (M) annualised costs
(2a) Facilitating works | £Y1 | £Y2 | £Y3 | … | £Yn
(2b) Substructure | £Y1 | £Y2 | £Y3 | … | £Yn
(2c) Superstructure | £Y1 | £Y2 | £Y3 | … | £Yn
(2d) Internal finishes | £Y1 | £Y2 | £Y3 | … | £Yn
(2e) Fittings, furniture and equipment | £Y1 | £Y2 | £Y3 | … | £Yn
(2f) Services | £Y1 | £Y2 | £Y3 | … | £Yn
(2g) Work to existing buildings (not covered in 2a-2f) | £Y1 | £Y2 | £Y3 | … | £Yn
(2h) External works | £Y1 | £Y2 | £Y3 | … | £Yn | See paragraph 4.1.2
Total - Maintain costs estimate (2)
[(2) = Σ (2a) + (2b) + (…) + (2h)] | £Y1 | £Y2 | £Y3 | … | £Yn | See paragraphs 4.8 to 4.11 and 4.13
Sub-total (3) [(3) = (1) + (2)] | £Y1 | £Y2 | £Y3 | … | £Yn
Maintenance contractor's management & administration costs
(4a) Renewal works | £Y1 | £Y2 | £Y3 | … | £Yn | See paragraph 4.1.4
(4b) Maintain works | £Y1 | £Y2 | £Y3 | … | £Yn | See paragraph 4.1.4
Maintenance contractor's management and administration cost estimate (4) | £Y1 | £Y2 | £Y3 | … | £Yn
[(4) = (4a + (4b)]
Sub-total (5) [(5) = (3) + (4)] | £Y1 | £Y2 | £Y3 | … | £Yn
Maintenance contractor's overheads and profit (6) | £Y1 | £Y2 | £Y3 | … | £Yn | See paragraph 4.1.5
Maintenance cost estimate (7)
Sub-total (7) [(7) = (5) + (6)] | £Y1 | £Y2 | £Y3 | … | £Yn
(8) Consultants'/specialists' fees estimate | £Y1 | £Y2 | £Y3 | … | £Yn | See paragraph 4.1.6
(9) Employer-definable maintenance-related costs estimate | £Y1 | £Y2 | £Y3 | … | £Yn | See paragraph 4.1.7
Base cost estimate (10) | £Y1 | £Y2 | £Y3 | … | £Yn
[(10) = (7 + (8) + (9)]
Sub-total (10) [(10) = (7) + (8) + (9)] | £Y1 | £Y2 | £Y3 | … | £Yn
Risks | [5 empty] | See paragraph 4.1.8
(11a) Design and installation risks | £Y1 | £Y2 | £Y3 | … | £Yn
(11b) Maintenance risks | £Y1 | £Y2 | £Y3 | … | £Yn
(11c) Employers change order risks | £Y1 | £Y2 | £Y3 | … | £Yn
(11d) Employer other risk | £Y1 | £Y2 | £Y3 | … | £Yn
Risk allowance estimate (11)
[(11) = (11a) + (11b) + (11c) + (11d)] | £Y1 | £Y2 | £Y3 | … | £Yn
Cost limit (at current price levels) (12)
[(12) = (10) + (11)] | £Y1 | £Y2 | £Y3 | … | £Yn
Discount factor (13) | DF1 | DF2 | DF3 | … | DFn | See paragraph 4.1.9
Present value (14)
[(14) = (12) X (13)] | £Y1 | £Y2 | £Y3 | … | £Yn | See paragraph 4.1.9
Net present value (Total cost limit) (15)
[(15) = Σ(PV) (14))] | £Y1 | £Y2 | £Y3 | … | £Yn | See paragraph 4.1.9
Notes:
VAT and other taxation incentives are excluded (see paragraph 4.20)
Other considerations (as defined in paragraph 4.21) are to taken into account, if required in scope
£Y1 = Year 1 costs
£Y2 = Year 2 costs
£Y3 = Year 3 costs
£Yn = Final year costs in which either maintenance or replacement works are to undertaken
DF1 = Year 1 discount factor
DF2 = Year 2 discount factor
DF3 = Year 3 discount factor
DFn = Discount factor for final year in which either maintenance or replacement works are to undertaken

## 9.NRM3 Maintain off ARegister
NRM 3 - Excel extract from the published 1st edition effective from 1st January 2015
Informative Worked Example |  | Reproduced with the permsion of BESA publications (2015)
NRM 3 - MAINTAIN COST PLAN generated from an 'Asset Maintenance Register - (Worked example includes a few typical maintainable asset types) | [13 empty] | BLUE boxes - relate to information obtained from SFG20 (BESA)
COST DATA STRUCTURE |  | BUILT ASSET DATA |  |  | QUANTIFICATION OF MAINTAIN (M) WORKS | [8 empty] | EVENT CYCLE |  | TASK SKILLING BY TRADE | ANNUAL LABOUR HOURS CALCULATED BY TRADE (as SFG20 resource modeller)
Group Element / Element / Sub-element / Components & Cost Codes / Maintain Descriptor |  | Component Specification / Attributes (type/ make and material, sizing etc) | Quantity | Unit of Measure | In Maintain (M) Plan Scope (Yes / No) | Maintain (M) PPM Task Descriptor (SFG20 task) | Action Required (SFG20 code) | Maintain (M) Quantity | Maintain (M) Unit of Measure | Task Time (Industry Standard PPM - Coal Face Times (In Minutes Examples) | Amended Task Time (PPM Minutes) | Access Adjustment Factor | Out of Normal Hours Working (Minutes) | Task Frequency | Interval (Number of occurrences per year) | Trade Description | Gas Safe |  | Mechanical |  | Electrical
[17 empty] | Normal Working Hours | Out of Hours Working | Normal Working Hours | Out of Hours Working | Normal Working Hours | Out of Hours Working
5 | Services | [8 empty] | SFG20 Task Times |  | % | Exceptions
5.5 | Heat Source (HS) | B1 | B2 | B3 | C | D | E | F1 | F2 | G | H | I | J | K | L | M | N1 | N2 | N3 | N4 | N5 | N6
5.5 | Introductory procedures | Permits and risk assessments etc | 1 | Item | Yes | as B1 | 05-01 & 02 | 1 | Item | 20 | 0 | 0% | 0 | 12 monthly | 1 | MECHANICAL | 0 | 0 | 0.33333 | 0 | 0 | 0
5.5.1 | Heat source
5.5.1.2 | Boiler - gas/oil | Atmospheric gas burner, boiler, free standing boiler | 2 | nr | Yes | as B1 | 05-03 | 2 | nr | 180 | 120 | 0% | 0 | 12 monthly | 1 | GAS SAFE | 4 | 0 | 0 | 0 | 0 | 0
[7 empty] | 05-03 | 2 | nr | 30 | 30 | 0% | 0 | 3 monthly | 4 | GAS SAFE | 4 | 0 | 0 | 0 | 0 | 0
|  | Forced draught gas burner condensing boiler | 2 | nr | Yes | as B1 | 05-12 | 2 | nr | 120 | 60 | 0% | 60 | 12 monthly | 1 | GAS SAFE | 0 | 2 | 0 | 0 | 0 | 0
[7 empty] | 05-12 | 2 | nr | 60 | 0 | 0% | 60 | 6 monthly | 2 | GAS SAFE | 0 | 4 | 0 | 0 | 0 | 0
5.5.1.19 | Flue system | Flues inside (mild steel) | 4 | nr | Yes | as B1 | 24-01 | 4 | nr | 60 | 60 | 0% | 0 | 12 monthly | 1 | MECHANICAL | 0 | 0 | 4 | 0 | 0 | 0
[7 empty] | 24-01 | 4 | nr | 15 | 15 | 0% | 0 | 1 monthly | 12 | MECHANICAL | 0 | 0 | 12 | 0 | 0 | 0
5.6 | Space Heating and Air Conditioning (SHAC)
5.6 | Introductory procedures | Permits and risk assessments etc | 1 | Item | Yes | as B1 | 09-01 | 1 | Item | 20 | 0 | 0% | 0 | 12 monthly | 1 | MECHANICAL | 0 | 0 | 0.33333 | 0 | 0 | 0
5.6.3 | Central cooling
5.6.3.5 | Chillers | Packaged chillers units - air cooled | 4 | nr | Yes | as B1 | 09-02 | 4 | nr | 240 | 180 | 0% | 0 | 3 monthly | 4 | MECHANICAL | 0 | 0 | 48 | 0 | 0 | 0
[7 empty] | 09-02 | 4 | nr | 180 | 180 | 0% | 0 | 12 monthly | 1 | ELECTRICAL | 0 | 0 | 0 | 0 | 12 | 0
5.6.7 | Central air conditioning
5.6.7.8 | Air handling units | Air handling units (AHUs) - (state sizing) | 1 | nr | Yes | as B1 | 03-01 | 1 | nr | 120 | 100 | 0% | 0 | 12 monthly | 1 | MECHANICAL | 0 | 0 | 1.6667 | 0 | 0 | 0
[7 empty] | 03-01 | 1 | nr | 30 | 20 | 0% | 0 | 6 monthly | 2 | MECHANICAL | 0 | 0 | 0.66667 | 0 | 0 | 0
[7 empty] | 03-01 | 1 | nr | 15 | 10 | 0% | 0 | 3 monthly | 4 | ELECTRICAL | 0 | 0 | 0 | 0 | 0.66667 | 0
[7 empty] | 03-01 | 1 | nr | 15 | 10 | 0% | 0 | 1 monthly | 12 | MECHANICAL | 0 | 0 | 2 | 0 | 0 | 0
|  | Belts | 1 | nr | Yes | as B1 | 04-01 | 1 | nr | 30 | 0 | 0% | 0 | 3 monthly | 4 | MECHANICAL | 0 | 0 | 2 | 0 | 0 | 0
5.6.8 | Local air conditioning
5.6.8.1 | Air conditioning units1 | Room air conditioners | 10 | nr | Yes | as B1 | 47-01 | 10 | nr | 60 | 30 | 0% | 15 | 12 monthly | 1 | ELECTRICAL | 0 | 0 | 0 | 0 | 2.5 | 2.5
[6 empty] | as B1 | 47-01 | 10 | nr | 30 | 15 | 0% | 15 | 6 monthly | 2 | MECHANICAL | 0 | 0 | 0 | 5 | 0 | 0
5.6.8.5 | Pumps | Split systems heat pumps | 5 | nr | Yes | as B1 | 47-01 | 5 | nr | 30 | 30 | 0% | 0 | 6 monthly | 2 | MECHANICAL | 0 | 0 | 5 | 0 | 0 | 0
5.8 | Electrical Installations (EI)
5.8 | Introductory procedures | Permits and risk assessments etc | 1 | Item | Yes | as B1 | 44-01 | 1 | Item | 20 | 0 | 0% | 0 | 12 monthly | 1 | ELECTRICAL | 0 | 0 | 0 | 0 | 0.33333 | 0
5.8.3 | Lighting installations
5.8.3.1 | Luminaires | Office light fittings - Atrium area | 10 | m2 | Yes | as B1 | 36-03 | 10 | m2 | 5 | 0 | 200% | 5 | 12 monthly | 1 | ELECTRICAL | 0 | 0 | 0 | 0 | 0 | 1.6667
|  | Office light fittings - Office areas | 30 | m2 | Yes | as B1 | 36-03 | 30 | m2 | 5 | 0 | 0% | 0 | 12 monthly | 1 | ELECTRICAL | 0 | 0 | 0 | 0 | 2.5 | 0
Note - Other applicable asset types (as project specific asset register)
| Note 1 - Introductory procedures include for obtaining permits to works, undertaking risk assessments, complying with written procedures and the like | [14 empty] | Net Total Annual Labour Hours by Trade | 8 | 6 | 76 | 5 | 18 | 4.1667
| Note 2 - Task time SFG20 PPM task times (coal face* times as an industry norm or standard) | [14 empty] | Reactive Hours Annualised (if in scope) | 3 | 1 | 19 | 1 | 4 | 0
*Coal face times equates to the actual time that is spent working on the equipment and does not include travel, arranging access or the erection or removal of any access equipment that may be required
[16 empty] | Site Adjustment / Access Factor (%) | 19% | 19% | 19% | 19% | 19% | 19%
Note 3 - Amend PPM task time industry norms for minimum standards required by manufacturers, statute and good practice
[14 empty] | Gross Total Labour Hours by Trade | 152.32 | 20.4283 | 13.09 | 8.33 | 113.05 | 7.14 | 26.18 | 4.9583
Note 4 - Access adjustment factor on an asset specific basis (e.g. roof access restrictions) or alternatively taken with site adjustment
[16 empty] | Trade Labour Rate (Normal Working Hours / Out of Normal Working Hours) | 65 | 97.5 | 57 | 85.5 | 53 | 79.5
Note 5 - Out of normal hours working (identify the time in minutes if the works are required to be carried out outside of normal working hours)
[14 empty] | Total Annualised Trade Labour Cost | 10499.0725 |  | 850.85 | 812.175 | 6443.85 | 610.47 | 1387.54 | 394.1875
Note 6 - Reactive hours (include project specific allowance for unscheduled hours by trade, if in scope)
[14 empty] | Annualised Consumables / Plant & Equipment | 3000 |  | 500 | 500 | 500 | 500 | 500 | 500
Note 7 - Site adjustment / access factor % for arranging PTW, access and permission to isolate where required.
[14 empty] | Total Annualised Maintain (M) Cost | 13499.0725 |  | 1350.85 | 1312.175 | 6943.85 | 1110.47 | 1887.54 | 894.1875
| Note 8 - Trade labour rate (all inclusive rate including costs for tools applicable to carry out the task in hand) | [12 empty] | Excludes VAT and any future years price inflation provision
Note 9 - Annualised Consumables / Plant & Equipment (provision for consumables and plant and equipment such as AHU filters and belts or as part of total annualised allowance)
Note 10 - Excludes any specific contractual obligations or risks (e.g. Comprehensive cover)
NOTE: All lighting is treated with the same task but adjusted to allow for a disruption factor when dealing with situations such as atrium lighting. This factor would allow for access equipment, out of hours, erection of barriers etc

## 10. NRM 3 Renewal off CapitalCP
NRM 3 - Excle extract from the published 1st edition effective from 1st January 2015
Informative worked example for calculating the cost of renewal (R) works
WINDOWS AND EXTERNAL DOORS |  |  |  | Construction cost plan base date | 2011 | Index | 211 | [13 empty] | Period of analysis | 20
|  |  |  | Reporting renewal cost base date | 2011 | Index | 211
Group Element / Element / Sub-element / Component |  | CAPITAL BUILDING WORKS COST PLAN |  |  |  |  | QUANTIFICATION OF RENEWAL (R) WORKS | [5 empty] | EVENT CYCLE |  |  | RENEWAL (R) COSTS |  |  |  |  | RENEWAL CASH FLOW
|  | Component Specification | Quantity | Unit of Measurement | Construction Unit Rate (CUR) | Total | In Renewal (R) Plan Scope (Yes / No) | Renewal (R) Descriptor | Action Required | Scale of Renewal (R) | Renewal (R) Quantity | Renewal (R) Unit of Measurement | Reference Service Life (RSL) | Life Factor | Interval | Adjustment to Construction Unit Rate | Renewal (R) Uplift | Renewal (R) Unit Rate | Cost Per Event | Total Renewal (R) Cost (over 20 year period) | Total 1-20 | 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
2 | Superstructure | [19 empty] | 101788.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11880 | 0 | 0 | 0 | 89908.5
2.6 | Windows and external doors
2.6.1 | External windows
2.6.1.1 | Windows | Aluminium; polyester powder coated; double glazed units | 1181 | nr | 400 | 472400 | Yes | External windows; aluminium | Replace double glazed window | 100% | 1181 | m2 | 40 | 0.8 | 32 | 85% | 10% | 374 | 441694 | 0 | 0 | 1: 0
[8 empty] | Ironmongery | Replace ironmongery | 100% | 1181 | m2 | 20 | 1 | 20 | 15% | 10% | 66 | 77946 | 77946 | 77946 | 1: 0; 20: 77946
2.6.2 | External doors
2.6.2.1 | External doors | Aluminium; double; 1 hr fire rated | 138 | nr | 500 | 69000 | Yes | Entrance doors / frames | Replace external doors | 100% | 138 | nr | 40 | 0.8 | 32 | 80% | 10% | 440 | 60720 | 0 | 0 | 1: 0
[8 empty] | Ironmongery | Replace ironmongery | 50% | 69 | nr | 20 | 1 | 20 | 15% | 10% | 82.5 | 5692.5 | 5692.5 | 5692.5 | 1: 0; 20: 5692.5
[8 empty] | Sundry item - seals | Replace seals | 100% | 138 | nr | 20 | 1 | 20 | 5% | 10% | 27.5 | 3795 | 3795 | 3795 | 1: 0; 20: 3795
|  | Double doors to main entrance; aluminium | 20 | nr | 300 | 6000 | Yes | Entrance doors / frames | Replace double doors | 100% | 20 | nr | 20 | 0.8 | 16 | 80% | 10% | 264 | 5280 | 5280 | 5280 | 1: 0; 16: 5280
[8 empty] | Ironmongery | Replace ironmongery | 50% | 10 | nr | 20 | 1 | 20 | 15% | 10% | 49.5 | 495 | 495 | 495 | 1: 0; 20: 495
[8 empty] | Sundry item - seals | Replace seals | 100% | 20 | nr | 20 | 1 | 20 | 5% | 10% | 16.5 | 330 | 330 | 330 | 1: 0; 20: 330
|  | Main entrance door arrangement; aluminium | 1 | nr | 7500 | 7500 | Yes | Entrance doors / frames | Replace main entrance door arrangement | 100% | 1 | nr | 20 | 0.8 | 16 | 80% | 10% | 6600 | 6600 | 6600 | 6600 | 1: 0; 16: 6600
[8 empty] | Sundry item - door controls | Replace door controls | 100% | 1 | nr | 20 | 1 | 20 | 20% | 10% | 1650 | 1650 | 1650 | 1650 | 1: 0; 20: 1650
A, B, C & D |  | E | F | G | H | (Calculated) [FxH] | I | J | K | L | M (Calculated) [FxL] | N | O | P | Q (Calculated) [OxP] | R | S | T (Calculated / Substituted rate) [HxRx(1+S)] | U (Calculated) [MxT] | V
INTERNAL DOORS |  |  |  | Construction cost plan base date | 2Q11 | Index | 221 | [13 empty] | Period of analysis | 1: 20
|  |  |  | Reporting renewal cost base date | 2Q11 | Index | 221
Group Element / Element / Sub-element / Component |  | CAPITAL BUILDING WORKS COST PLAN |  |  |  |  | QUANTIFICATION OF RENEWAL (R) WORKS | [5 empty] | EVENT CYCLE |  |  | RENEWAL (R) COSTS |  |  |  |  | RENEWAL CASH FLOW
|  | Component Specification | Quantity | Unit of Measurement | Construction Unit Rate (CUR) | Total | In Renewal (R) Plan Scope (Yes / No) | Renewal (R) Descriptor | Action Required | Scale of Renewal (R) | Renewal (R) Quantity | Renewal (R) Unit of Measurement | Reference Service Life (RSL) | Life Factor | Interval | Adjustment to Construction Unit Rate | Renewal (R) Uplift | Renewal (R) Unit Rate | Cost Per Event | Total Renewal (R) Cost (over 20 year period) | Total 1-20 | 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
2 | Superstructure | [19 empty] | 10051.25 | 1039.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1039.5 | 0 | 0 | 0 | 0 | 0 | 357.5 | 1039.5 | 6600 | 0 | 0 | 0 | 0 | 1014.75
2.8 | Internal doors
2.8.1 | Internal doors
2.8.1.1 | Internal doors | Internal standard timber door & frame; paint finish; single; 1/2 hr fire rated | 6 | nr | 150 | 900 | Yes | Internal door - standard; timber | Replace door & frame | 100% | 6 | nr | 40 | 1 | 40 | 100% | 10% | 165 | 990 | 0 | 0 | 1: 0
[8 empty] | Paint doors | Painting to door | 100% | 6 | nr | 7 | 1 | 7 | 3% | 10% | 4.95 | 29.7 | 59.4 | 59.4 | 1: 29.7; 7: 29.7; 14: 29.7
[8 empty] | Paint door frames | Painting to door frames | 100% | 6 | nr | 7 | 1 | 7 | 2% | 10% | 3.3 | 19.8 | 39.6 | 39.6 | 1: 19.8; 7: 19.8; 14: 19.8
[8 empty] | Ironmongery | Replace ironmongery | 50% | 3 | nr | 20 | 1 | 20 | 15% | 10% | 24.75 | 74.25 | 74.25 | 74.25 | 1: 0; 20: 74.25
[8 empty] | Sundry item - seals | Replace seals | 100% | 6 | nr | 20 | 1 | 20 | 5% | 10% | 8.25 | 49.5 | 49.5 | 49.5 | 1: 0; 20: 49.5
|  | Automatic sliding door; aluminium glazed; one and a half leaf; 1/2 hr fire rated | 1 | nr | 6000 | 6000 | Yes | Sliding doors; aluminium | Replace automatic sliding door | 100% | 1 | nr | 15 | 1 | 15 | 100% | 10% | 6600 | 6600 | 6600 | 6600 | 1: 0; 15: 6600
[8 empty] | Sundry item - overhaul | Overhaul | 100% | 1 | nr | 7 | 1 | 7 | 15% | 10% | 990 | 990 | 1980 | 1980 | 1: 990; 7: 990; 14: 990
|  | Internal standard timber door & frame; single; self finish; 1/2 hr fire rated | 36 | nr | 180 | 6480 | Yes | Internal door - standard; timber | Replace door and frame | 100% | 36 | nr | 40 | 1 | 40 | 100% | 10% | 198 | 7128 | 0 | 0 | 1: 0
[8 empty] | Ironmongery | Replace ironmongery | 50% | 18 | nr | 20 | 1 | 20 | 15% | 10% | 29.7 | 534.6 | 534.6 | 534.6 | 1: 0; 20: 534.6
[8 empty] | Sundry item - seals | Replace seals | 100% | 36 | nr | 20 | 1 | 20 | 5% | 10% | 9.9 | 356.4 | 356.4 | 356.4 | 1: 0; 20: 356.4
|  | Internal roller shutter door; self finished | 1 | nr | 1300 | 1300 | Yes | Internal roller shutter doors and frames | Replace roller shutter door | 100% | 1 | nr | 25 | 1 | 25 | 100% | 10% | 1430 | 1430 | 0 | 0 | 1: 0
[8 empty] | Sundry item - overhaul | Overhaul | 100% | 1 | nr | 13 | 1 | 13 | 25% | 10% | 357.5 | 357.5 | 357.5 | 357.5 | 1: 0; 13: 357.5
A, B, C & D |  | E | F | G | H | (Calculated) [FxH] | I | J | K | L | M (Calculated) [FxL] | N | O | P | Q (Calculated) [OxP] | R | S | T (Calculated / Substituted rate) [HxRx(1+S)] | U (Calculated) [MxT] | V
** | Note: The 'Renewal Rate' for these items have not been calculated using the CUR, but has been substituted with a rate derived from either a schedule of rates or a specific estimate / quotation.
FLOOR FINISHES Example |  |  |  | Construction cost plan base date | 2Q25 | Index | 221
|  |  |  | Reporting renewal cost base date | 2Q25 | Index | 221
Group Element / Element / Sub-element / Component |  | CAPITAL BUILDING WORKS COST PLAN |  |  |  |  | QUANTIFICATION OF RENEWAL (R) WORKS | [5 empty] | EVENT CYCLE |  |  | RENEWAL (R) COSTS |  |  |  |  | RENEWAL CASH FLOW
|  | Component Specification | Quantity | Unit of Measurement | Construction Unit Rate (CUR) | Total | In Renewal (R) Plan Scope (Yes / No) | Renewal (R) Descriptor | Action Required | Scale of Renewal (R) | Renewal (R) Quantity | Renewal (R) Unit of Measurement | Reference Service Life (RSL) | Life Factor | Interval | Adjustment to Construction Unit Rate | Renewal (R) Uplift | Renewal (R) Unit Rate | Cost Per Event | Total Renewal (R) Cost (over 20 year period) | Total 1-20 | 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
3 | Internal Finishes | [19 empty] | 126656 | 61234.36 | 0 | 0 | 0 | 0 | 850.5 | 4080 | 0 | 65.56 | 0 | 56238.3 | 0 | 4080 | 0 | 0 | 850.5 | 172.84 | 0 | 4080 | 0 | 56238.3
3.2 | Floor finishes
3.2.1 | Finishes to floors
3.2.1.1 | Finishes to floors | Vinyl sheet: non-slip | 82 | m2 | 30.6 | 2509.2 | Yes | Vinyl sheet covering; non slip | Replace floor finishes: lift existing and lay new non-slip vinyl sheet | 100% | 82 | m2 | 10 | 1 | 10 | 100% | 50% | 45.9 | 3763.8 | 7527.6 | 7527.6 | 1: 3763.8; 10: 3763.8; 20: 3763.8
|  | Vinyl sheet: standard | 133 | m2 | 21 | 2793 | Yes | Vinyl sheet covering; standard | Replace floor finishes: lift existing and lay new standard vinyl sheet | 80% | 106 | m2 | 10 | 1 | 10 | 100% | 50% | 31.5 | 3339 | 6678 | 6678 | 1: 3339; 10: 3339; 20: 3339
[8 empty] | Vinyl sheet covering; standard | Repair floor finishes: lift existing and lay new standard vinyl sheet | 20% | 27 | m2 | 5 | 1 | 5 | 100% | 50% | 31.5 | 850.5 | 3402 | 3402 | 1: 1701; 5: 850.5; 10: 850.5; 15: 850.5; 20: 850.5
|  | Carpeting: heavy duty / general areas | 1073 | m2 | 37.5 | 40237.5 | Yes | Fixed carpeting | Replace floor finishes: lift existing and lay new fitted carpet - heavy duty | 100% | 1073 | m2 | 10 | 1 | 10 | 100% | 20% | 45 | 48285 | 96570 | 96570 | 1: 48285; 10: 48285; 20: 48285
3.2.1.3 | Skirtings and the like | Skirting: softwood, painted | 816 | m | 13 | 10608 | Yes | Skirtings; softwood | Replace softwood skirting | 100% | 816 | m | 50 | 1 | 50 | 100% | 50% | 19.5 | 15912 | 0 | 0 | 1: 0
[8 empty] | Paint skirting | Decorate skirtings: reapply gloss paint | 100% | 816 | m | 6 | 1 | 6 | n/a** | n/a** | 5 | 4080 | 12240 | 12240 | 1: 4080; 6: 4080; 12: 4080; 18: 4080
3.2.1.4 | Mat wells and mats | Mat wells; metal framed | 1 | nr | 149 | 149 | Yes | Mat well matting | Replace matting | 100% | 1 | nr | 8 | 1 | 8 | 40% | 10% | 65.56 | 65.56 | 131.12 | 131.12 | 1: 65.56; 8: 65.56; 16: 65.56
[8 empty] | Mat well frame | Replace mat well frame | 100% | 1 | nr | 16 | 1 | 16 | 60% | 20% | 107.28 | 107.28 | 107.28 | 107.28 | 1: 0; 16: 107.28
A, B, C & D |  | E | F | G | H | (Calculated) [FxH] | I | J | K | L | M (Calculated) [FxL] | N | O | P | Q (Calculated) [OxP] | R | S | T (Calculated / Substituted rate) [HxRx(1+S)] | U (Calculated) [MxT] | V
** | Note: The 'Renewal Rate' for these items have not been calculated using the CUR, but has been substituted with a rate derived from either a schedule of rates or a specific estimate / quotation.
1-11
1-11
1-11
1-11
1-11
1-11

## 11. NRM3 RenewalsoffAsBuiltData
NRM 3 - Excel extract from the published 1st edition effective from 1st January 2015
Informative worked example for calculating the cost of renewal (R) works using as-built information
WINDOWS & EXTERNAL DOORS |  | Asset condition survey base date | Date | Index | TBA | [14 empty] | Period of analysis | 20
|  | Reporting renewal cost base date | Date | Index | TBA
Group Element / Element / Sub-element / Component |  | BUILT ASSET DATA |  |  | QUANTIFICATION OF RENEWAL (R) WORKS | [7 empty] | EVENT CYCLE |  |  | RENEWAL COST |  |  | RENEWAL CASH FLOW
|  | Component Specification | Quantity | Unit of Measurement | In Renewal Plan Scope (Yes / No) | Renewal (R) Descriptor | Condition Asset Rating (CAR) | Action Required | Scale of Renewal (R) | Renewal (R) Quantity | Renewal (R) Unit of Measurement | Asset Remaining Life (PARL) | Reference Service Life (RSL) | Life Factor | Interval | Renewal (R) Unit Rate | Cost Per Event | Total Renewal (R) Cost (over 20 year period) | Total 1-20 | 1 - 11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
2 | Superstructure | [17 empty] | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0
2.6 | Windows and external doors
2.6.1 | External windows
2.6.1.1 | External windows | Aluminium; polyester powder coated; double glazed units | 1181 | m2 | Yes | External windows; aluminium | B | Replace double glazed window | 1 | 1181 | m2 | 25 | 40 | 0.8 | 32 | 374 | 441694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1181 | m2 | Yes | Ironmongery | B | Replace ironmongery | 1 | 1181 | m2 | 13 | 20 | 1 | 20 | 66 | 77946 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.6.2 | External doors
2.6.2.1 | External doors | Aluminium; double; 1 hr fire rated | 138 | nr | Yes | Entrance doors / frames | B | Replace external doors | 1 | 138 | nr | 25 | 40 | 0.8 | 32 | 440 | 60720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 69 | nr | Yes | Ironmongery | B | Replace ironmongery | 1 | 69 | nr | 17 | 20 | 1 | 20 | 82.5 | 5692.5 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0
|  |  | 138 | nr | Yes | Sundry item - seals | B | Replace seals | 1 | 138 | nr | 17 | 20 | 1 | 20 | 27.5 | 3795 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0
|  | Double doors to main entrance; aluminium | 20 | nr | Yes | Entrance doors / frames | B | Replace double doors | 1 | 20 | nr | 13 | 20 | 0.8 | 16 | 264 | 5280 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 10 | nr | Yes | Ironmongery | B | Replace ironmongery | 1 | 10 | nr | 17 | 20 | 1 | 20 | 49.5 | 495 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0
|  |  | 20 | nr | Yes | Sundry item - seals | B | Replace seals | 1 | 20 | nr | 17 | 20 | 1 | 20 | 16.5 | 330 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0
|  | Main entrance door arrangement; aluminium | 1 | nr | Yes | Entrance doors / frames | B | Replace main entrance door arrangement | 1 | 1 | nr | 13 | 20 | 0.8 | 16 | 6600 | 6600 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | nr | Yes | Sundry item - door controls | B | Replace door controls | 1 | 1 | nr | 17 | 20 | 1 | 20 | 1650 | 1650 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0
A, B,C & D |  | E | F | G | H | I | J | K | L | M (Calculated) [FxL] | N | O | P | Q | R (Calculated) [PxQ] | S | T (Calculated) [MxS] | U
INTERNAL DOORS |  | E: Asset condition survey base date; F: Date; G: Index; H: TBA | [9 empty] | Period of analysis | 20
|  | Reporting renewal cost base date | Date | Index | TBA
Group Element / Element / Sub-element / Component |  | E: BUILT ASSET DATA; H: QUANTIFICATION OF RENEWAL (R) WORKS |  |  |  | EVENT CYCLE |  |  | RENEWAL COST |  |  | RENEWAL CASH FLOW
|  | Component Specification | Quantity | Unit of Measurement | In Renewal Plan Scope (Yes / No) | Renewal (R) Descriptor | Condition Asset Rating (CAR) | Action Required | Scale of Renewal (R) | Renewal (R) Quantity | Renewal (R) Unit of Measurement | Asset Remaining Life (PARL) | Reference Service Life (RSL) | Life Factor | Interval | Renewal (R) Unit Rate | Cost Per Event | Total Renewal (R) Cost (over 20 year period) | Total 1-20 | 1 - 11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
2 | Superstructure | [17 empty] | #VALUE! | #VALUE! | 0 | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | #VALUE! | 0 | 0 | #VALUE! | 0 | 0 | 0 | #VALUE! | #VALUE!
2.8 | Internal doors
2.8.1 | Internal doors
2.8.1.1 | Internal doors | Internal standard timber door & frame; paint finish; single; 1/2 hr fire rated | 6 | nr | Yes | Internal door - standard; timber | A | Replace door | 1 | 6 | nr | 35 | 40 | 1 | 40 | 165 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting to door | 6 | nr | Yes | Paint doors | C | Repaint doors | 1 | 6 | nr | 2 | 7 | 1 | 7 | 4.95 | 29.7 | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0
|  | Painting to door frames | 6 | nr | Yes | Paint door frames | C | Repainting door frames | 1 | 6 | nr | 2 | 7 | 1 | 7 | 3.3 | 19.8 | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0
|  | Ironmongery | 3 | nr | Yes | Ironmongery | B | Replace ironmongery | 1 | 3 | nr | 15 | 20 | 1 | 20 | 24.75 | 74.25 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0
|  | Seals | 6 | nr | Yes | Sundry item - seals | B | Replace seals | 1 | 6 | nr | 15 | 20 | 1 | 20 | 8.25 | 49.5 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0
|  | Automatic sliding door; aluminium glazed; one and a half leaf; 1/2 hr fire rated | 1 | nr | Yes | Sliding doors; aluminium | B | Replace automatic sliding door | 1 | 1 | nr | 10 | 15 | 1 | 15 | 6600 | 6600 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | nr | Yes | Sundry item - overhaul | N/A | Overhaul | 1 | 1 | nr | 2 | 7 | 1 | 7 | 990 | 990 | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0
|  | Internal standard timber door & frame; single; self finish; 1/2 hr fire rated | 36 | nr | Yes | Internal door - standard; timber | A | Replace door | 1 | 36 | nr | 35 | 40 | 1 | 40 | 198 | 7128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ironmongery | 18 | nr | Yes | Ironmongery | B | Replace ironmongery | 1 | 18 | nr | 15 | 20 | 1 | 20 | 29.7 | 534.6 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0
|  | Seals | 36 | nr | Yes | Sundry item - seals | B | Replace seals | 1 | 36 | nr | 15 | 20 | 1 | 20 | 9.9 | 356.4 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0
|  | Internal roller shutter door; self finished | 1 | nr | Yes | Internal roller shutter doors and frames | B | Replace roller shutter door | 1 | 1 | nr | 20 | 25 | 1 | 25 | 1430 | 1430 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
|  |  | 1 | nr | Yes | Sundry item - overhaul | N/A | Overhaul | 1 | 1 | nr | 7 | 13 | 1 | 13 | 357.5 | 357.5 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
A, B,C & D |  | E | F | G | H | I | J | K | L | M (Calculated) [FxL] | N | O | P | Q | R (Calculated) [PxQ] | S | T (Calculated) [MxS] | U
FLOOR FINISHES Example |  | E: Asset condition survey base date; F: Date; G: Index; H: TBA
|  | Reporting renewal cost base date | Date | Index | TBA
Group Element / Element / Sub-element / Component |  | E: BUILT ASSET DATA; H: QUANTIFICATION OF RENEWAL (R) WORKS |  |  |  | EVENT CYCLE |  |  | RENEWAL COST |  |  | RENEWAL CASH FLOW
|  | Component Specification | Quantity | Unit of Measurement | In Renewal Plan Scope (Yes / No) | Renewal (R) Descriptor | Condition Asset Rating (CAR) | Action Required | Scale of Renewal (R) | Renewal (R) Quantity | Renewal (R) Unit of Measurement | Asset Remaining Life (PARL) | Reference Service Life (RSL) | Life Factor | Interval | Renewal (R) Unit Rate | Cost Per Event | Total Renewal (R) Cost (over 20 year period) | Total 1-20 | 1 - 11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
3 | Internal Finishes | [17 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0
3.2 | Floor finishes
3.2.1 | Finishes to floors
3.2.1.1 | Finishes to floors | Vinyl sheet: non-slip | 82 | m2 | Yes | Vinyl sheet covering; non slip | B | Replace floor finishes: lift existing and lay new non-slip vinyl sheet | 1 | 82 | m2 | 7 | 10 | 1 | 10 | 45.9 | 3763.8 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0
|  | Vinyl sheet: standard | 106 | m2 | Yes | Vinyl sheet covering; standard | B | Replace floor finishes: lift existing and lay new standard vinyl sheet | 1 | 106 | m2 | 7 | 10 | 1 | 10 | 31.5 | 3339 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0
|  |  | 27 | m2 | Yes | Vinyl sheet covering; standard | D | Repair floor finishes: lift existing and lay new standard vinyl sheet | 1 | 27 | m2 | 1 | 5 | 1 | 5 | 31.5 | 850.5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | #VALUE! | 0
|  | Carpeting: heavy duty / general areas | 1073 | m2 | Yes | Fixed carpeting | C | Replace floor finishes: lift existing and lay new fitted carpet - heavy duty | 1 | 1073 | m2 | 3 | 10 | 1 | 10 | 45 | 48285 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0
3.2.1.3 | Skirtings and the like | Skirting: softwood, painted | 816 | m | Yes | Skirtings; softwood | A | Replace softwood skirting | 1 | 816 | m | 47 | 50 | 1 | 50 | 19.5 | 15912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Yes | Paint skirting | C | Decorate skirtings: reapply gloss paint | 1 | 816 | m | 3 | 6 | 1 | 6 | 5 | 4080 | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0
3.2.1.4 | Mat wells and mats | Mat wells; metal framed | 1 | nr | Yes | Mat well matting | D | Replace matting | 1 | 1 | nr | 2 | 8 | 1 | 8 | 65.56 | 65.56 | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | nr | Yes | Mat well frame | B | Replace mat well frame | 1 | 1 | nr | 12 | 16 | 1 | 16 | 107.28 | 107.28 | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A, B,C & D |  | E | F | G | H | I | J | K | L | M (Calculated) [FxL] | N | O | P | Q | R (Calculated) [PxQ] | S | T (Calculated) [MxS] | U
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11
1-11

## 12. NRM 3 RenewaloffAsset CondS
NRM 3 - Excel extract from the published 1st edition effective from 1st January 2015
Life Cycle Renewal Cost Plan generated from an ASSET SPECIFIC CONDITION SURVEY INFORMATION Post-Construction (In Use)
Period of analysis - EXAMPLE shown over 20 years | [8 empty] | Base dates |  | TBA
[8 empty] | Asset condition survey base date | #REF! | Index | 221
[8 empty] | Reporting renewal cost base date | #REF! | Index | 221
GROUP ELEMENT / ELEMENT / SUB-ELEMENT |  |  | Cost | COMPONENT SPECIFICATION (ALIGNMENT WITH THE CONSTRUCT RULES) | CONDITION ASSET RATING | ACTION REQUIRED | Renewal (R) Quantity | Renewal (R) Unit of Measurement | Reference Service Life (RSL) | Life Factor | Renewal (R) Unit Rate | ASSET REMAINING LIFE | INTERVAL | COST PER EVENT | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | YEAR | 20 YEAR TOTAL | AVERAGE COST PER ANNUM
|  |  | ID | [11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
0 | Facilitating Works | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.1 | Toxic/hazardous material removal | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.1.1 | Toxic or hazardous material removal |  | 1 | Remedial works |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.1.2 | Contaminated land |  | 1 | Remedial works |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Substructure | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | Substructure | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Standard foundations |  | 1 | Remedial works |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2 | Specialist foundation system |  | 1 | Remedial works |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Superstructure | [13 empty] | 0 | 1039.5 | 0 | 0 | 0 | 0 | 357.5 | 0 | 1039.5 | 6600 | 0 | 1039.5 | 89826 | 0 | 1014.75 | 0 | 11962.5 | 0 | 1039.5 | 1787.5 | 115706.25 | 5785.3125
2.1 | Frame | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1 | Steel frames |  | 1 | Structural steel frame |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2 | Space decks |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Upper Floors | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1 | Floors |  | 1 | Concrete suspended floors |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2 | Balconies |  | 1 | Purpose made balconies |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 | Roof | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.1 | Roof structure |  | 1 | Pitched roof + state details |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.2 | Roof coverings |  | 1 | Tiled roof coverings |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4 | Stairs and Ramps | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4.1 | Stair / Ramp structures |  | 4 | Fire escape staircases |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4.2 | Stair / ramp finishes |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | External Walls | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5.1 | External enclosing walls above ground floor level |  | 9 | Profiled sheet cladding systems |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5.2 | External enclosing walls below ground floor level |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.6 | Windows and External Doors |  |  | SEE WORKED EXAMPLE | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89826 | 0 | 0 | 0 | 11962.5 | 0 | 0 | 0 | 101788.5 | 5089.425
2.6.1 | External windows |  | 1 | Aluminium; polyester powder coated; double glazed units | B | Replace double glazed window | 1181 | m2 | 40 | 0.8 | 374 | 25 | 32 | 441694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | B | Replace ironmongery | 1181 | m2 | 20 | 1 | 66 | 13 | 20 | 77946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77946 | 3897.3
2.6.2 | External doors |  | 1 | Aluminium; Double; 1 hr fire rated | B | Replace external doors | 138 | nr | 40 | 0.8 | 440 | 25 | 32 | 60720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | B | Replace ironmongery | 69 | nr | 20 | 1 | 82.5 | 17 | 20 | 5692.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5692.5 | 0 | 0 | 0 | 5692.5 | 284.625
[5 empty] | B | Replace seals | 138 | nr | 20 | 1 | 27.5 | 17 | 20 | 3795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3795 | 0 | 0 | 0 | 3795 | 189.75
|  |  | 2 | Double doors to main entrance | B | Replace double doors | 20 | nr | 20 | 0.8 | 264 | 13 | 16 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5280 | 264
[5 empty] | B | Replace ironmongery | 10 | nr | 20 | 1 | 49.5 | 17 | 20 | 495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495 | 0 | 0 | 0 | 495 | 24.75
[5 empty] | B | Replace seals | 20 | nr | 20 | 1 | 16.5 | 17 | 20 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 330 | 16.5
|  |  | 8 | Main entrance door arrangement and controls | B | Replace main entrance door arrangement | 1 | nr | 20 | 0.8 | 6600 | 13 | 16 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 330
[5 empty] | B | Replace door controls | 1 | nr | 20 | 1 | 1650 | 17 | 20 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 1650 | 82.5
2.7 | Internal Walls and Partitions | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.7.1 | Walls and partitions |  | 14 | Glazed partitioning |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.7.2 | Balustrades and handrails |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.8 | Internal Doors |  |  | SEE WORKED EXAMPLE | [10 empty] | 0 | 1039.5 | 0 | 0 | 0 | 0 | 357.5 | 0 | 1039.5 | 6600 | 0 | 1039.5 | 0 | 0 | 1014.75 | 0 | 0 | 0 | 1039.5 | 1787.5 | 13917.75 | 695.8875
2.8.1 | Internal doors |  | 1 | Internal standard timber door & frame; paint finish; single; 1/2 hr fire rated | A | Replace door | 6 | nr | 40 | 1 | 165 | 35 | 40 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | C | Painting to door frames | 6 | nr | 7 | 1 | 4.95 | 2 | 7 | 29.7 | 0 | 29.7 | 0 | 0 | 0 | 0 | 0 | 0 | 29.7 | 0 | 0 | 29.7 | 0 | 0 | 0 | 0 | 0 | 0 | 29.7 | 0 | 118.8 | 5.94
[5 empty] | C | Painting to door frames | 6 | nr | 7 | 1 | 3.3 | 2 | 7 | 19.8 | 0 | 19.8 | 0 | 0 | 0 | 0 | 0 | 0 | 19.8 | 0 | 0 | 19.8 | 0 | 0 | 0 | 0 | 0 | 0 | 19.8 | 0 | 79.2 | 3.96
[5 empty] | B | Replace ironmongery | 3 | nr | 20 | 1 | 24.75 | 15 | 20 | 74.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.25 | 0 | 0 | 0 | 0 | 0 | 74.25 | 3.7125
[5 empty] | B | Replace seals | 6 | nr | 20 | 1 | 8.25 | 15 | 20 | 49.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.5 | 0 | 0 | 0 | 0 | 0 | 49.5 | 2.475
|  |  | 6 | Automatic sliding door; aluminium glazed; one and a half leaf; 1/2 hr fire rated | B | Replace automatic sliding door | 1 | nr | 15 | 1 | 6600 | 10 | 15 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 330
[5 empty] | N/A | Overhaul | 1 | nr | 7 | 1 | 990 | 2 | 7 | 990 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 3960 | 198
|  |  | 1 | Internal standard timber door & frame; single; self finish; 1/2 hr fire rated | A | Replace door | 36 | nr | 40 | 1 | 198 | 35 | 40 | 7128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | B | Replace ironmongery | 18 | nr | 20 | 1 | 29.7 | 15 | 20 | 534.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534.6 | 0 | 0 | 0 | 0 | 0 | 534.6 | 26.73
[5 empty] | B | Replace seals | 36 | nr | 20 | 1 | 9.9 | 15 | 20 | 356.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356.4 | 0 | 0 | 0 | 0 | 0 | 356.4 | 17.82
|  |  | 7 | Internal roller shutter door; self finished | B | Replace roller shutter door | 1 | nr | 25 | 1 | 1430 | 20 | 25 | 1430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1430 | 1430 | 71.5
[5 empty] | N/A | Overhaul | 1 | nr | 13 | 1 | 357.5 | 7 | 13 | 357.5 | 0 | 0 | 0 | 0 | 0 | 0 | 357.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357.5 | 715 | 35.75
3 | Internal Finishes | [13 empty] | 850.5 | 65.56 | 52365 | 0 | 0 | 850.5 | 7102.8 | 0 | 4930.5 | 65.56 | 0 | 107.28 | 48285 | 916.06 | 4080 | 0 | 55387.8 | 0 | 850.5 | 0 | 175857.06 | 8792.853
3.1 | Wall Finishes | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.1 | Finishes to walls |  | 4 | Ceramic wall tiling |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 | Floor Finishes |  |  | SEE WORKED EXAMPLE | [10 empty] | 850.5 | 65.56 | 52365 | 0 | 0 | 850.5 | 7102.8 | 0 | 4930.5 | 65.56 | 0 | 107.28 | 48285 | 916.06 | 4080 | 0 | 55387.8 | 0 | 850.5 | 0 | 175857.06 | 8792.853
3.2.1 | Finishes to floors |  | 7 | Vinyl sheet: non-slip | B | Replace floor finishes: lift existing and lay new non-slip vinyl sheet | 82 | m2 | 10 | 1 | 45.9 | 7 | 10 | 3763.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3763.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3763.8 | 0 | 0 | 0 | 7527.6 | 376.38
|  |  | 7 | Vinyl sheet: standard | B | Replace floor finishes: lift existing and lay new standard vinyl sheet | 106 | m2 | 10 | 1 | 31.5 | 7 | 10 | 3339 | 0 | 0 | 0 | 0 | 0 | 0 | 3339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3339 | 0 | 0 | 0 | 6678 | 333.9
[5 empty] | D | Repair floor finishes: lift existing and lay new standard vinyl sheet | 27 | m2 | 5 | 1 | 31.5 | 1 | 5 | 850.5 | 850.5 | 0 | 0 | 0 | 0 | 850.5 | 0 | 0 | 850.5 | 0 | 0 | 0 | 0 | 850.5 | 0 | 0 | 0 | 0 | 850.5 | 0 | 4252.5 | 212.625
|  |  | 11 | Carpeting: heavy duty / general areas | C | Replace floor finishes: lift existing and lay new fitted carpet - heavy duty | 1073 | m2 | 10 | 1 | 45 | 3 | 10 | 48285 | 0 | 0 | 48285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48285 | 0 | 0 | 0 | 48285 | 0 | 0 | 0 | 144855 | 7242.75
|  |  | 17 | Skirting: softwood, painted | A | Replace softwood skirting | 816 | m | 50 | 1 | 19.5 | 47 | 50 | 15912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | C | Decorate skirtings: reapply gloss paint | 816 | m | 6 | 1 | 5 | 3 | 6 | 4080 | 0 | 0 | 4080 | 0 | 0 | 0 | 0 | 0 | 4080 | 0 | 0 | 0 | 0 | 0 | 4080 | 0 | 0 | 0 | 0 | 0 | 12240 | 612
|  |  | 18 | Matwells; metal framed | D | Replace matting | 1 | nr | 8 | 1 | 65.56 | 2 | 8 | 65.56 | 0 | 65.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.56 | 0 | 0 | 0 | 65.56 | 0 | 0 | 0 | 0 | 0 | 0 | 196.68 | 9.834
[5 empty] | B | Replace matwell frame | 1 | nr | 16 | 1 | 107.28 | 12 | 16 | 107.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.28 | 5.364
3.3 | Ceiling Finishes | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.1 | Finishes to ceilings |  | 5 | Painting and decorating to ceilings |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3.2 | False ceilings |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Fittings, Furnishings and Equipment | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Fittings, furnishings and equipment | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1 | General fittings, furnishings and equipment |  | 4 | Blinds and blind boxes |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2 | Domestic kitchen fittings and equipment |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Services | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 | Sanitary Installations | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.1 | Sanitary appliances |  | 1 | WC pans and cisterns |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.2 | Sanitary ancillaries |  | 1 | Shower cubicles |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2 | Services Equipment | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1 | Services equipment |  | 1 | Catering equipment |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3 | Disposal Installations | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.1 | Foul drainage above ground |  | 1 | Waste pipes and fittings |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3.2 | Chemical, toxic and industrial liquid waste drainage |  | 5 | Storage tanls and vessels |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4 | Water Installations | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.1 | Mains water supply |  | 3 | Water meters - internal |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.2 | Cold water distribution |  | 6 | Pressure booster sets |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.5 | Heat Source | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.5.1 | Heat source |  | 2 | Gas fired boiler - atmospheric |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.6 | Space Heating and Air Conditioning | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.6.1 | Central heating |  | 3 | Heating emission units - radiators |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.6.2 | Local heating |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.7 | Ventilation | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.7.1 | Central ventilation |  | 1 | Air extract systems |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.7.2 | Local and special ventilation |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.8 | Electrical Installations | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.8.1 | Electrical mains and sub-mains distribution |  | 3 | LV switchgear & distibution boards |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.8.2 | Power installations |  | 6 | Cables and wiring |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.9 | Fuel Installations / Systems | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.9.1 | Fuel storage |  | 2 | Storage tanks and vessels |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.9.2 | Fuel distribution systems |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.10 | Lift and Conveyor Installations / Systems | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.10.1 | Lift and enclosed hoists |  | 1 | Complete lift installations - refurbish |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.10.2 | Escalators |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.11 | Fire and Lightning Protection | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.11.1 | Fire fighting systems |  | 2 | Fire hise reels |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.11.2 | Fire suppression systems |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.12 | Communication, Security and Control Systems | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.12.1 | Communication systems |  | 4 | Public address systems |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.12.2 | Security systems |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.13 | Special Installations / Systems | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.13.1 | Specialist piped supply installations |  | 3 | Treated water systems - details ? |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.13.2 | Specialist refrigeration systems |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.14 | Builder’s Work in Connection with Services | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.14.1 | General builder's work |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Complete Buildings and Building Units | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 | Prefabricated buildings | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.1 | Complete buildings |  |  | NOT APPLICABLE |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1.2 | Building units |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Work to Existing Buildings | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.1 | Minor Demolition and Alteration Works | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.1.1 | Minor Demolition and Alteration Works |  | 1 | Strip out existing services inst. |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.2 | Repairs to Existing Services | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.2.1 | Existing Services |  | 3 | Fault finding |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.3 | Damp Proof Courses / Fungus and Beetle Eradication | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.3.1 | Damp proof courses |  | 1 | Chemical damp proof courses |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.3.2 | Fungus / beetle eradication |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.4 | Façade Retention | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.4.1 | Façade Retention |  | 3 | Shores - details to be stated |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.5 | Cleaning Existing Surfaces | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.5.1 | Cleaning existing surfaces |  | 1 | Removng efflorescence |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.5.2 | Protective coatings to existing surfaces |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.6 | Renovation Works | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.6.1 | Masonry repairs |  | 1 | Masonry repairs - details |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.6.2 | Concrete repairs |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | External Works | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.1 | Site Preparation Works |  |  | NOT APPLICABLE | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.2 | Roads, Paths and Pavings | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.2.1 | Roads, paths and pavings |  | 8 | Coated tarmacadam and asphalt |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.2.2 | Special surfacings and pavings |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.3 | Soft Landscaping, Planting and Irrigation Systems | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.3.1 | Seeding and turfing |  | 14 | Replacement seeding and turfing |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.3.2 | External planting |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.4 | Fencing, Railings and Walls | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.4.1 | Fencing and railings |  | 5 | Security gates |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.4.2 | Walls and screens |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.5 | External Fixtures | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.5.1 | Site / Street furniture and equipment |  | 3 | Bollards |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.5.2 | Ornamental features |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.6 | External Drainage | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.6.1 | Surface water and foul water drainage |  | 12 | inspection chambers - remedials? |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.6.2 | Ancillary drainage systems |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.7 | External Services | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.7.1 | Water mains supply |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.7.2 | Electricity mains supply |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.8 | Minor Building Works and Ancillary Buildings | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.8.1 | Minor building works |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.8.2 | Ancillary buildings and structures |  |  |  |  | Insert Action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.9 | Demolitions and work outside the site | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUB TOTAL: (A) |  |  | A | [11 empty] | 850.5 | 1105.06 | 52365 | 0 | 0 | 850.5 | 7460.3 | 0 | 5970 | 6665.56 | 0 | 1146.78 | 138111 | 916.06 | 5094.75 | 0 | 67350.3 | 0 | 1890 | 1787.5 | 291563.31 | 14578.1655
9 | Maintenance Contractor's management and administration (B) |  | B | [11 empty] | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 800000 | 40000
SUB TOTAL: (C) [C=A+B] |  |  | C | [11 empty] | 40850.5 | 41105.06 | 92365 | 40000 | 40000 | 40850.5 | 47460.3 | 40000 | 45970 | 46665.56 | 40000 | 41146.78 | 178111 | 40916.06 | 45094.75 | 40000 | 107350.3 | 40000 | 41890 | 41787.5 | 1091563.31 | 54578.1655
10 | Maintenance Contractor's overheads and profit (D) |  | D | [11 empty] | 4085.05 | 4110.506 | 9236.5 | 4000 | 4000 | 4085.05 | 4746.03 | 4000 | 4597 | 4666.556 | 4000 | 4114.678 | 17811.1 | 4091.606 | 4509.475 | 4000 | 10735.03 | 4000 | 4189 | 4178.75 | 109156.331 | 5457.8166
TOTAL: RENEWAL WORKS ESTIMATE (E) [E=C+D] |  |  | E | [11 empty] | 44935.55 | 45215.566 | 101601.5 | 44000 | 44000 | 44935.55 | 52206.33 | 44000 | 50567 | 51332.116 | 44000 | 45261.458 | 195922.1 | 45007.666 | 49604.225 | 44000 | 118085.33 | 44000 | 46079 | 45966.25 | 1200719.641 | 60035.9821
11 | Project costs / consultant fees (F) |  | F | [11 empty] | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 500000 | 25000
12 | Employer definable costs (G) |  | G | [11 empty] | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000 | 125000 | 6250
SUB TOTAL: (H) [H=E+F+G] |  |  | H | [11 empty] | 69935.55 | 70215.566 | 126601.5 | 69000 | 69000 | 94935.55 | 77206.33 | 69000 | 75567 | 101332.116 | 69000 | 95261.458 | 220922.1 | 70007.666 | 74604.225 | 69000 | 143085.33 | 94000 | 71079 | 95966.25 | 1825719.641 | 91285.9821
13 | Risk allowance (I) |  | I | [11 empty] | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 600000 | 30000
TOTAL: RENEWAL COST LIMIT |  |  | L | [11 empty] | 99935.55 | 100215.566 | 156601.5 | 99000 | 99000 | 124935.55 | 107206.33 | 99000 | 105567 | 131332.116 | 99000 | 125261.458 | 250922.1 | 100007.666 | 104604.225 | 99000 | 173085.33 | 124000 | 101079 | 125966.25 | 2425719.641 | 121285.982
DISCOUNT FACTOR @ |  | 3% |  | As agreed rate | [10 empty] | 0.97087 | 0.9426 | 0.91514 | 0.88849 | 0.86261 | 0.83748 | 0.81309 | 0.78941 | 0.76642 | 0.74409 | 0.72242 | 0.70138 | 0.68095 | 0.66112 | 0.64186 | 0.62317 | 0.60502 | 0.58739 | 0.57029 | 0.55368
PRESENT VALUE | [14 empty] | 97024.8058 | 94462.7825 | 143312.5566 | 87960.2177 | 85398.2697 | 104631.5562 | 87168.5569 | 78151.5142 | 80908.3152 | 97723.4283 | 71519.7064 | 87855.8664 | 170865.7402 | 66116.8487 | 67141.4716 | 61693.527 | 104719.4712 | 72836.9313 | 57643.9413 | 69744.4585
NET PRESENT VALUE | [14 empty] | 97024.8058 | 191487.5884 | 334800.1449 | 422760.3627 | 508158.6323 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## 13. NRM 3 L1 Reporting Template
NRM 3 - Excel extract from the published 1st edition effective from 1st January 2015
APPENDIX I:
Report template for elemental cost plans for renewal (R) and maintain (M) works
(condensed - based on level 1 codes)
Project Title: |  |  |  | Functional Unit: |  |  | Number of Storeys:
Cost Plan No: |  |  |  | Asset Classification: |  |  | Floor Area (GIFA m2):
Base Date |  |  |  | Space Utilisation: |  |  | Maintainable Area (m2):
Period of Analysis (Yrs) |  | X |  | Hours of Operation: |  |  | Location (BCIS Index)
COST CENTRE | RICS NRM 3 GROUP ELEMENT |  |  |  | £Y1 | £Y2 | £Y3 | ... | £Yn | X YEAR TOTAL | COST PER M2 GIFA PER ANNUM
[10 empty] | £ | £/m2pa
RENEWAL
0 | Facilitating works
1 | Substructure
2 | Superstructure
3 | Internal finishes
4 | Fittings, furnishings and equipment
5 | Services
6 | Prefabricated buildings and building units - included in elements 1-5
7 | Works to existing buildings - Maintenance included in elements 1-5
8 | External works
SUBTOTAL: RENEWAL
MAINTAIN
(i) Planned Preventative Maintenance (PPM)
0 | Facilitating works
1 | Substructure
2 | Superstructure
3 | Internal finishes
4 | Fittings, furnishings and equipment
5 | Services
6 | Prefabricated buildings and building units - Maintenance included in elements 1-5
7 | Works to existing buildings - Maintenance included in elements 1-5
8 | External works
SUBTOTAL: Planned Preventative Maintenance (PPM)
(ii) Reactive Maintenance (RM)
1 - 8 | Annualised reactive maintenance costs
SUBTOTAL: Reactive Maintenance (RM)
SUBTOTAL: MAINTAIN (PPM and RM) + RENEWAL (A)
9 | Maintenance contractor's preliminaries (B)
SUBTOTAL - MAINTAIN + RENEWAL (including maintenance contractor's preliminaries) (C) [C = A + B]
10 | Maintenance contractor's overheads and profit (D)
TOTAL - MAINTAIN + RENEWAL ESTIMATE (E) [E = C + D]
11 | Consultants fees (F)
12 | Employer definable costs (G)
TOTAL - CONSULTANTS FEES / EMPLOYER DEFINABLE COSTS (H) [H = F + G)
BASE ELEMENTAL COST ESTIMATE (I) [I = E + H]
13A - B | Risk allowances - as item 3.14
13C | Commercial and other considerations - as item 3.18
TOTAL - RISK ALLOWANCE ESTIMATE (J)
COST LIMIT (excluding inflation) (K) [K = I + J]
14 | Inflation / deflation to base dates - as item 3.15
TOTAL - INFLATION / DEFLATION (L)
COST LIMIT (excluding VAT assessment) (M) [M = K + L]
15 | VAT assessment EXCLUDED (see item 3.17)
DISCOUNT FACTOR @ |  | (see item 3.19) | %
NET PRESENT VALUE (NPV)
MAINTENANCE FUNCTIONAL UNIT RATE (FUR) £/m2pa
1. | Base date of cost plan: ........................
2. | All transfers are to be to / from the risk allowance cost centres and balanced by an equal but opposite adjustment to the risk allowance centres.
Note: | Value Added Tax (VAT) in relation to buildings is a complex area. Therefore, it is recommended that VAT be excluded from elemental cost estimates. It is recommended that specialist advice is sought on VAT matters to ensure that the correct rates are applied to the various aspects of a building project.

## 14. NRM 3 L2 Reporting Template
NRM 3 - Excel extract from the published 1st edition effective from 1st January 2015
APPENDIX J:
Report template for elemental cost plans for renewal (R) and maintain (M) works
(expanded - based on level 2 codes)
Project Title: |  |  |  | Functional Unit: |  |  | Number of Storeys:
Cost Plan No: |  |  |  | Asset Classification: |  |  | Floor Area (GIFA m2):
Base Date |  |  |  | Space Utilisation: |  |  | Maintainable Area (m2):
Period of Analysis (Yrs) |  | X |  | Hours of Operation: |  |  | Location (BCIS Index)
COST CENTRE | RICS NRM 3 GROUP ELEMENT / ELEMENT |  |  |  | £Y1 | £Y2 | £Y3 | ... | £Yn | X YEAR TOTAL | COST PER M2 GIFA PER ANNUM
[10 empty] | £ | £/m2pa
RENEWAL
0 | Facilitating works
0.1 | Toxic / hazardous / contaminated material treatment - excluded from maintenance works
0.2 | Major demolition works - excluded from maintenance works |  |  |  | Not covered by NRM 3
0.3 | Temporary support to adjacent structures - excluded from maintenance works |  |  |  | Not covered by NRM 3
0.4 | Specialist groundworks
0.5 | Temporary diversion works - excluded from maintenance works |  |  |  | Not covered by NRM 3
0.6 | Extraordinary site investigation works - excluded from maintenance works
1 | Substructure
1.1 | Substructure
2 | Superstructure
2.1 | Frame
2.2 | Upper floors
2.3 | Roof
2.4 | Stairs and ramps
2.5 | External walls
2.6 | Windows and external doors
2.7 | Internal walls and partitions
2.8 | Internal doors
3 | Internal finishes
3.1 | Wall finishes
3.2 | Floor finishes
3.3 | Ceiling finishes
4 | Fittings, furnishings and equipment
4.1 | Fittings, furnishings and equipment
5 | Services
5.1 | Sanitary installations
5.2 | Services equipment
5.3 | Disposal installations
5.4 | Water installations
5.5 | Heat source
5.6 | Sace heating and air conditioning
5.7 | Ventilation systems
5.8 | Electrical installations
5.9 | Fuel installations
5.1 | Lift and conveyor installations
5.11 | Fire and lightning protection
5.12 | Communication, security and control systems
5.13 | Special installations
5.14 | Builders’ work in connection with services
6 | Prefabricated buildings and building units
6.1 | Prefabricated buildings and building units - Maintenance included in elements 1-5 |  |  |  | Not covered by NRM 3
7 | Works to existing buildings
7.1 | Minor demolition and alteration works - Maintenance included in elements 1-5
7.2 | Repairs to existing services - Maintenance included in elements 1-5
7.3 | Damp-proof courses / fungus and beetle eradication - Maintenance included in elements 1-5
7.4 | Façade retention - Maintenance included in elements 1-5
7.5 | Cleaning existing surfaces - Maintenance included in elements 1-5
7.6 | Renovation works - Maintenance included in elements 1-5
8 | External works
8.1 | Site preparation works |  |  |  | Not covered by NRM 3
8.2 | Roads, paths and pavings and surfacings
8.3 | Soft landscaping, planting and irrigation systems
8.4 | Fencing, railings and walls
8.5 | External fixtures
8.6 | External drainage
8.7 | External services
8.8 | Minor building works and ancillary buildings
SUBTOTAL: RENEWAL
MAINTAIN
(i) Planned Preventative Maintenance (PPM)
0 | Facilitating works
0.1 | Toxic / hazardous / contaminated material treatment - excluded from maintenance works
0.2 | Major demolition works - excluded from maintenance works |  |  |  | Not covered by NRM 3
0.3 | Temporary support to adjacent structures - excluded from maintenance works |  |  |  | Not covered by NRM 3
0.4 | Specialist groundworks
0.5 | Temporary diversion works - excluded from maintenance works |  |  |  | Not covered by NRM 3
0.6 | Extraordinary site investigation works - excluded from maintenance works
1 | Substructure
1.1 | Substructure
2 | Superstructure
2.1 | Frame
2.2 | Upper floors
2.3 | Roof
2.4 | Stairs and ramps
2.5 | External walls
2.6 | Windows and external doors
2.7 | Internal walls and partitions
2.8 | Internal doors
3 | Internal finishes
3.1 | Wall finishes
3.2 | Floor finishes
3.3 | Ceiling finishes
4 | Fittings, furnishings and equipment
4.1 | Fittings, furnishings and equipment
5 | Services
5.1 | Sanitary installations
5.2 | Services equipment
5.3 | Disposal installations
5.4 | Water installations
5.5 | Heat source
5.6 | Sace heating and air conditioning
5.7 | Ventilation systems
5.8 | Electrical installations
5.9 | Fuel installations
5.1 | Lift and conveyor installations
5.11 | Fire and lightning protection
5.12 | Communication, security and control systems
5.13 | Special installations
5.14 | Builders’ work in connection with services
6 | Prefabricated buildings and building units
6.1 | Prefabricated buildings and building units - Maintenance included in elements 1-5 |  |  |  | Not covered by NRM 3
7 | Works to existing buildings
7.1 | Minor demolition and alteration works - Maintenance included in elements 1-5
7.2 | Repairs to existing services - Maintenance included in elements 1-5
7.3 | Damp-proof courses / fungus and beetle eradication - Maintenance included in elements 1-5
7.4 | Façade retention - Maintenance included in elements 1-5
7.5 | Cleaning existing surfaces - Maintenance included in elements 1-5
7.6 | Renovation works - Maintenance included in elements 1-5
8 | External works
8.1 | Site preparation works
8.2 | Roads, paths and pavings and surfacings
8.3 | Soft landscaping, planting and irrigation systems
8.4 | Fencing, railings and walls
8.5 | External fixtures
8.6 | External drainage
8.7 | External services
8.8 | Minor building works and ancillary buildings
SUBTOTAL: Planned Preventative Maintenance (PPM)
(ii) Reactive Maintenance (RM)
1 - 8 | Annualised reactive maintenance costs
SUBTOTAL: Reactive Maintenance (RM)
SUBTOTAL: MAINTAIN (PPM AND RM) + RENEWAL (A)
9 | Maintenance contractor's preliminaries (B)
SUBTOTAL: MAINTAIN + RENEWAL (including maintenance contractor's preliminaries) (C) [C = A + B]
10 | Maintenance contractor's overheads and profit (D)
TOTAL: MAINTAIN + RENEWAL ESTIMATE (E) [E = C + D]
11 | Consultants fees (F)
12 | Employer definable costs (G)
TOTAL: CONSULTANTS FEES / EMPLOYER DEFINABLE COSTS (H) [H = F + G)
BASE ELEMENTAL COST ESTIMATE (I) [I = E + H]
13A - B | Risk allowances - as item 3.14
13C | Commercial and other considerations - as item 3.18
TOTAL: RISK ALLOWANCE ESTIMATE (J)
COST LIMIT (excluding inflation) (K) [K = I + J]
14 | Inflation / deflation to base dates - as item 3.15
TOTAL: INFLATION / DEFLATION (L)
COST LIMIT (excluding VAT assessment) (M) [M = K + L]
15 | VAT assessment EXCLUDED (see item 3.17)
DISCOUNT FACTOR @ |  | (see item 3.19) | %
NET PRESENT VALUE (NPV)
MAINTENANCE FUNCTIONAL UNIT RATE (FUR) £/m2pa
1. | Base date of cost plan: ........................
2. | All transfers are to be to / from the risk allowance cost centres and balanced by an equal but opposite adjustment to the risk allowance centres.
Note: | Value Added Tax (VAT) in relation to buildings is a complex area. Therefore, it is recommended that VAT be excluded from elemental cost estimates. It is recommended that specialist advice is sought on VAT matters to ensure that the correct rates are applied to the various aspects of a building project.